## Sheet1
| ISG CDP ACTION LIST |  | Status : 2018-02-05
ID | Action Number | Who | What | date | status | Comments
1 | Action CDP#01_00 | David | Revise the one pager to be fresh |  | Active
2 | Action CDP#01_01 | David | Develop an CDP PowerPoint set one pager |  | Active | No progress (David will take the lead and circulate)
3 | Action CDP#01_02 | Paul | Develop initial skeleton for CDP White Paper |  | Active | Starting (Paul has the lead)
4 | Action CDP#01_03 | David | Develop initial FAQ and CDP value statement to put on ETSI web |  | Active | No progress (David will take the lead and circulate)
5 | Action CDP#01_04 | PC/ALL | Develop an initial work plan (list of deliverables that CDP need to develop and by when) |  | Active | No progress (need to start @ Feb meeting)
6 | Action CDP#01_05 | Lindsay | Identify ESSENTIAL conferences to attend, and find speakers |  | Active | (Lindsay has lead) currently identified OASC <Bxls> / London / Barcelona, ETSI IoT week -> possibly Bilbao, others will follow
7 | Action CDP#01_06 | ALL | Consider what cities to approach (a list) and how to get them inside CDP |  | Active | no documented progress
8 | Action CDP#01_07 | ALL | Consider what companies to approach (a list) and how to get them inside CDP |  | Active | No progress
9 | Action CDP#01_08 | ALL | Consider what organizations (a list) we wish to collaborate with |  | Active | No progress
10 | Action CDP#01_09 | ALL | Draft and send LSs to those organizations |  | Active | No progress
11 | Action CDP#01_10 | ALL | Draft some interesting smart city text for the ETSI website (technology area) |  | Active | No progress
12 | Action CDP#01_11 | ALL | Consider candidates for Vice chairs – who, how many, and to do what dedicated tasks? |  | Active | No progress
13 | Action CDP#01_12 | ALL | Consider what we wish to do with EU/EC resources (EIP-SCC / AIOTI / LSPs) and develop a plan |  | Active | starting
14 | Action CDP#01_13 | ALL | Help Rahim (Surrey) and Cisco to finish their ‘on boarding’ as CDP founding members |  | Completed
15 | Action CDP#01_14 | PC | Help Rahim (Surrey) and Cisco to finish their ‘on boarding’ as CDP founding members |  | Completed
16 | Action CDP#01_15 | PC/CM | Help Cisco to finish their "on boarding" as CDP founding members |  | Active | No progress
17 | Action CDP#01_16 | PC/CM | Develop the list of CDP meetings and ensure we have dates. Locations and hosts for all |  | Completed
18 | Action CDP#02_17
19 | Action CDP#02_18
20 | Action CDP#02_19