|  | ToR STF 413 (TB TISPAN /WG 6) |
| --- | --- |
|  | Version: 0.2 |
|  | Author: Eugen Mikoczy – Date: 13 October 2010 |
|  | Last updated by: Alberto Berrini – Date: 18 January 2011 |
|  | page 1 of 3 |

Terms of Reference for Specialist Task Force STF 413 
(TB TISPAN / WG 6) on ”Update of IMS-Based IPTV Interoperability Test specification to TISPAN Rel3”

Document status

| Status of these ToR | Approved TISPAN#25 – TISPAN(10)0181 and Board#80 |
| --- | --- |
| Work Items approved | RTS/TISPAN-06061-NGN-R3 |

# Reasons for proposing the Specialist Task Force (STF)

IMS is a key component of the Next-Generation Networks and IPTV has been identified as one of the first services to be merged with Voice/Data communications on IMS architecture.

Only a few basic use cases of IPTV have been defined in TISPAN Release 2. In the other hand, TISPAN Release 3 covers many new use cases and features for IPTV and the possible interactions with Voice/Data communications such as Social TV, Incoming Voice call management and notification on TV screen.

As a consequence, this update of the IMS-Based IPTV Interoperability Test Specification is a major step for this service and needs knowledge and expertise in many domains. ETSI members couldn’t individually gather all required skills for this task.

Currently, several standardization bodies and forums work on IPTV to define services as well as protocols. Moreover, different organizations have performed Interoperability Testing Sessions on IPTV. To be fully useable by the market and ETSI members, TISPAN Release 3 should be completed with up-to-date Interoperability Test Specification.

This STF work will also be linked to TC INT activities (IMS Core Network Testing) and 3GPP.

## Overview of the proposal

### Purpose of the work

This STF will update and greatly enhance ETSI TISPAN TS 186 020 (IMS-Based IPTV Interoperability Test Specification). The new test cases are linked to TISPAN Release 3, such as RACS integration and new IPTV service procedures.

### Relation with the ETSI strategic objectives

This STF is directly related to ETSI strategic objective "Major Strategic Topics - NGN" and “Service level interconnection of IP-Based Services”.

### Market impact, benefits to be gained

IPTV is one of the fast-growing IT services of the past years. Unfortunately, most of the deployed solutions are not standardized and all operators in the world will soon rethink their position before upgrading IPTV solutions for next generation TV (HD TV and 3D TV).

### Interest of ETSI Members and other stakeholders

An efficient and up-to-date Interoperability Test Specification for IMS-Based IPTV is one of the opportunities for solution providers and network operators to evaluate the different features and services.

Many ETSI members will be able to use the deliverables of this STF to compare different solutions and to provide fully interoperable IPTV platforms.

The following companies are committed to supporting this STF in terms of participation in the STF Steering Group and providing input and review to the STF: Slovak Telecom, France Telecom, Deutsche Telekom AG, Telekom Austria.

### Relation with other activities within ETSI and/or related organizations

This work is related to:

- ETSI TC INT

- ETSI TC MTS

- 3GPP CT1,CT3

### Priority within the TB

This STF is of medium priority within TC TISPAN / WG 6.

### Motivation why the work cannot be performed within the TB

As said in §1, the scope of this update is very large and requires skills in protocols as well as in user interface. Moreover, a good knowledge of IMS architecture is also needed. ETSI members cannot individually have the required skills in a reasonable time.

In order to reach the quality level which is required for this kind of technical documentation, testing expertise is also needed. That’s why an STF is crucial for TISPAN WG6 to be able to complete this task.

### Support from ETSI Members

The following ETSI Members support the creation of an STF to produce the deliverables listed in §3.14:

- Slovak Telekom, Operator - Company very active in IMS and IPTV

- France Telecom, Operator - Company very active in IPTV

- Telekom Austria, Operator - Company very active in IMS/NGN

- Deutsche Telekom AG, Operator - Company very active in IMS Testing

The ETSI Members supporting the creation of the STF are committed to supporting this STF in terms of participation in the STF Steering Group, providing input and review to the STF, and providing some voluntary resource to its efforts.

## Organization of the work

### Identification of tasks, phases, priorities, technical risk

There are 2 main tasks:

- Analysis of impacts of TISPAN Release 3

- Update of test specifications TS 186 020 (TISPAN IMS-based IPTV interoperability test specification)

### Outcome of the STF

The outcome of the STF will be one Technical Specifications (TS):

- 1 updated Technical Specification

# Consequences if not agreed:

Failure to agree to this STF will result in a gap between TISPAN Release 3 in IPTV domains and other IPTV specifications. The lack of a complete and up-to-date Interoperability Test Specification could also prevent ETSI to organize IPTV interoperability events in 2011. Without the availability of suitable test specifications, any IMS/NGN/IPTV interoperability testing activities will be of no technical value, and of little commercial or promotion value.

# Detailed description:

## Subject title:

Update of IMS-Based IPTV Interoperability Test Specification for TISPAN Release 3

## Reference Technical Body:

TB TISPAN / WG 6

## Other interested TBs:

- ETSI TC INT

- ETSI TC MTS

- 3GPP CT1,CT3

## Steering Committee

TISPAN / WG 6 will act as Steering Committee.

## Target date for the start of work:

Start:	24 January 2011

## Duration and target date for the conclusion of the work (TB approval):

Conclusion: 	TISPAN approval for publication 16-17 June 2011

## Resources required

The resources required are 25 200 EUR, corresponding to a total of 50 working days (which include at least 8 working days of voluntary contribution by the STF experts).

### Experts manpower

Total manpower required: 50 working days

- Analysis of TS 186 020 and TISPAN Rel 3			10 working days

- Update of Existing Test Cases by TISPAN Rel3			5 working days

- Creation of New Test Cases				35 working days

### Travel cost: None

### Other cost: None

## Experts qualification required, mix of skills

The following experts are required to perform the work.  The actual number of experts and mix of skills may depend on the actual applications received and will be decided when setting up the STF.

Number of experts required: 2-3

Relevant expertise required:

Expertise in Interoperability Testing

Expertise in IMS/TISPAN Standards

Expertise of IPTV/TISPAN Standards

## Scope of Terms of Reference:

See Section §1

## Task/phases planning:

There are 3 distinct tasks:

Analysis of impacts of TISPAN Release 3 should be done in a first time

Update of existing test cases impacted by TISPAN Rel 3 and Creation of new test cases defined by use cases introduced in TISPAN Rel3 could be done simultaneously

## Validation

Validation of this test specification will be managed in a separate task.

## Related activity in other bodies and co-ordination schedule

Not applicable

## Base documents and their availability

The STF work will be based upon the following documents:

- TISPAN Rel3 specifications

- ETSI TS 186 020 Version 2.1.1 (already published)

## Work Items to be produced by the STF

The STF will produce the following deliverables, for TB approval:

- RTS/TISPAN-06061-NGN-R3 (ETSI TS 186 020)

Scope: IMS-based IPTV interoperability test specification
Work Item approved by TISPAN (2010-05-28)

## Planned output schedule:

The STF will produce the deliverables according to the following time scale:

Work Item(s): RTS/TISPAN-06061-NGN-R3

- Start of the work 	24 January 2011

- ToC and Scope 	tbd mid February 2011
Audio conference with WG6 to review and confirm ToC and scope.  
Identify test cases of priority 1 and priority 2 that can be covered with resources available.

- First draft for WG review	14-17 March 2011	TISPAN#26-WGs

Progress Report #1, 1st draft with structure and template available for all test cases

- Second review	tbd in April	interim WG6 meeting
Test cases completed with signalling flows

- Final draft available for AbC	  2 May 2011

- WG approval (AbC)	16 May 2011

- Final draft for TB approval	16 May 2011

- TB approval	16-17 June 2011	TISPAN#27-Plenary

- Publication	July 2011

The STF will have the following milestones:

- Progress Report#1 to be approved by TISPAN#26-WGs 14-17 March 2011 and 1st draft of RTS/TISPAN-06061-NGN-R3 with structure and template available for all test cases.

- Final Report and RTS/TISPAN-06061-NGN-R3 to be approved by TISPAN#27-Plenary and accepted by ETSI Secretariat (editHelp) for publication.

# Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.0 | 13 Oct 10 | Mikoczy | TISPAN approved | Document Creation |
| 0.1 | 02 Nov 10 | Berrini | Approved Board#80 | Provisional code VS |
| 0.2 | 18 Jan 11 | Berrini | Prep. Meet. | Updated detailed time scale, milestones. |