Terms of Reference for Specialist Task Force STF290 (PA3), 
TC ESI on Relying Party Access to TSP Status List 
(TSL, defined in TS 102 231)

# 1	Reasons for proposing the Specialist Task Force (STF)

## 1.1	Overview of the proposal

### 1.1.1	Purpose of the work

The purpose of the STF deliverables is to:

- Implement a Protocol to securely and reliably localise, access and authenticate the TSL as defined in TS 102 231; this would allow wide use of this ETSI TS and facilitate TSL interoperability;

- Update the TS 101 231 according to the amendments that have already been proposed and to those that will be pointed out when developing the Protocol addressed in the previous item.

### 1.1.2	Relation with the ETSI Strategic Objectives

Electronic Signatures are covered by the item "security and privacy throughout networks", which is strategic for ETSI.

TSL is having a wide interest and acceptance in various countries and bodies (Germany, Italy, UNINFO the Italian ISO federated standardisation body, etc.)

If these deliverables are not developed, TSL accessing protocols will be implemented according to local needs and opinions, hence the TSL interoperability would be affected, as it is already beginning to happen. Additionally, should the TS 102 231 not to be upgraded, various changes to its format would be implemented, thus further hampering interoperability.

This would affect the ETSI ESI image and therefore its strategic objectives.

### 1.1.3	Relation with other activities within ETSI and/or related organizations

This Task shall build on the TS 102 231, developed under STF 220, which has already been endorsed or raised interest, where it has not been endorsed, by a number of governmental and private TSP governing schemes as well as national standardisation bodies.

### 1.1.4	Priority within the TB

This STF has been assigned High Priority by the ETSI TC ESI.

### 1.1.5	Motivation why the STF is urgently needed

A number of bodies are already implementing the TSL as per TS 102 231 (a few of them still in an experimental stage). Therefore there is an urgent need for a common TSL Localisation Access, Authentication Protocol (LAAP), to prevent interoperability problems among these separate TSL implementations.

As already mentioned in section 1.1.1, during the TSL LAAP development some amendments to TS 101 231 will be identified as necessary, as it is already emerging in some implementations, therefore a TS 101 231 update is also required.

## 1.2	Organization of the work

### 1.2.1	Confirmation of active support from the Members

The STF has the support of at least four ETSI Members:

- UNINFO

- TELIASONERA

- Studio Notarile Genghini

- Deutsche Telekom AG

### 1.2.3	Identification of tasks, phases, priorities, technical risk

The STF effort would produce two deliverables:

- A TSL Localisation Access, Authentication Protocol – LAAP

- An updated version of TS 101 231.

Given their strict interdependency, these two deliverables would be produced by the same STF and at the same time and have the same priority.

Various bodies have already undertaken the development either of the TSL, or of an LAAP mechanism, or of both, and they will most likely give their contribution based on their valuable experience. Therefore a low risk of not being able to finalize the deliverable is foreseen.

# 2	Consequences if not agreed

Should this STF be not activated, a number of different TSL access protocols may be developed, that would seriously hinder TSL interoperability. Being the TSL a valuable means to implement a cross – scheme TSP recognition, if its interoperability is not achieved, achieving most of the TS 102 231 benefits would be thwarted.

Additionally, a number of TSL amendments have already been requested by the early developers, which are to be accepted to correct / integrate the TS 101 231.

# 3	Detailed description:

## 3.1	Subject title:

Relying Party Access to TSP Status List

## 3.2	Reference Technical Body:

TC ESI

## 3.3	Other interested TBs (if any):

## 3.4	Steering Committee

The STF will report to the ESI plenary.

## 3.5	Support from ETSI Members

See under 1.2.1

## 3.6	Target date for the start of work:

February 2005

## 3.7	Duration and target date for the conclusion of the work (TB approval):

Duration: 		11 months.

Target date (TB approval): 	December 2005

## Resources required

Total resources required 48 600 EUR, split as follows in experts’ manpower and additional cost.

### 3.8.1	Experts manpower

Manpower resources required: 81 man-days (48 600 EUR), split as follows:

- Drafting deliverables:	39	man-days

- Drafting non-published documents:	12	man-days

- Attending Technical Body and WG meetings: 	8	man-days

- Attending other kind of meetings (including on-line commenting): 	22	man-days

### 3.8.2	Estimated cost, additional to the manpower:

No  additional cost

### 3.8.3	Estimated cost of Members’ contribution

Number of delegates at ESI meetings is commonly 20-25. STF tasks are discussed and progressed during meetings in plenary. Discussions are conducted between meetings electronically on two mail distribution lists, one internal and one public, with high participation from members and outsiders as well.

- Voluntary resource from members performing review of the deliverable (drafts to approval in TB) on the basis on a number of days: 40 man-days

## 3.9	Experts qualification required, mix of skills

The following experts are required to perform the work.  The actual number of experts and mix of skills may depend on the actual applications received and will be decided when setting up the STF.

- Number of experts required: 3 - 4

- Relevant expertise Development of electronic signature applications, X.500, TS 102 231

- Period over which the experts are required and duration of the secondment 11 months

## 3.10	Scope of Terms of Reference:

The aim of this task is to provide a common TSL localisation, access, authentication protocol (TSL LAAP) to enhance interoperability at least within EU Member States.

Requests for amendments have also been submitted to ETSI and, while working on the LAAP the need for amendments to TS 102 231 other requests are likely to arise, that shall have to be implemented too.

## 3.11	Organization of the work in tasks and/or phases:

There is no need to further separate this Task in subtasks, given the strict interdependency of its two main parts: defining the TSL LAAP and updating TS 102 231.

## 3.12	Related activity in other bodies and co-ordination of schedules:

## 3.13	Base documents and their availability

The STF work will be based upon the following documents:

| Work Item | Title | Current Status | Date TB approval |
| --- | --- | --- | --- |
| DTS/ESI-000010 | TS 102 231 – v. 1.1.1 | ISSUED | 24/9/2003 |

## 3.14	Work Items from the ETSI Work Programme (EWP) for which the STF is required:

The STF will produce the following deliverables, for TB approval:

- DTS/ESI-000037	Title: TSL Localisation, Access, Protocol (TSL LAAP)

Scope: common protocol to securely and reliably localise, access, authenticate TSL issued by any scheme, based on a relying parties’ trust on their scheme or TSP.

- RTS/ESI-000038	Title: TS 102 231 Electronic Signatures and Infrastructures (ESI); Provision of harmonized Trust Service Provider status information v1.2.1

Scope: Update TS 102 231 to meet the requirements raised by current users and during TSL LAAP development.

## 3.15	Planned output schedule:

The STF will produce the deliverables according to the following time scale:

Work Item(s): DTS/ESI-000037

- Start of the work 	February 2005

- ToC and scope 	March 2005

- First stable draft for WG review	April 2005

- Draft for WG approval	May 2005

- WG approval	June 2005

- Draft for TB approval	October 2005

- TB approval	November 2005

- Publication	December 2005

Work Item(s): RTS/ESI-000038

- Start of the work 	February 2005

- ToC and scope 	March 2005

- First stable draft for WG review	April 2005

- Draft for WG approval	May 2005

- WG approval	June 2005

- Draft for TB approval	October 2005

- TB approval	November 2005

- Publication	December 2005

In addition, the STF will produce the following reports for ETSI:

- Interim Report	June 2005

- Final Report 	December 2005

## Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.0.2 | Sept 04 | Ruggieri | 1st draft |  |
| 0.0.3 | 1 October | Endersz |  | submission to ETSI and distribution to TC ESI |
| 0.0.4 | 7 October | Desclercs Endersz | Draft | For endorsement by ESI and submission to ETSI |
| 0.0.5 | 12 Oct 04 | A. Berrini | Approved OCG#24bis/ Board#49 | Including Work Item codes and minor changes |
| 0.1.0 | 20 Dec 04 | R. Genghini | CfE | Reduced resources from 56kEUR to 48kEUR |
| 0.2.0 | 21 Feb 04 | A. Berrini | Prep. Meet | Merge travel cost in manpower. |