Terms of Reference for Specialist Task Force STF 328 
(TB TISPAN) on ”Interoperability Test Specifications for IMS NNI interworking”

# 1	Reasons for proposing the Specialist Task Force (STF)

IMS is a key component in the TISPAN NGN architecture. Interoperability between different core IMS networks is essential. Currently, no interoperability test specifications exist for the NNI.

TISPAN WG6 has identified an urgent need for interoperability test specifications for IMS NNI. This is confirmed by the Board ad hoc group IMS-TESTBED who have expressed a strong interest in IMS NNI testing but are reluctant to go ahead without some form of test specifications. This STF would fulfil that need.

## 1.1	Overview of the proposal

### 1.1.1	Purpose of the work

This STF will produce a basic set of interoperability test purposes and test descriptions for IMS interworking applicable at the IMS NNI, i.e. at the interface between two IMS networks. The tests will be driven by IMS end-to-end applications such as PoC or Presence.

### 1.1.2	Relation with the ETSI Strategic Objectives

This STF directly supports the ETSI strategic objectives "Interoperability" and "NGN".

### 1.1.3	Relation with other activities within ETSI and/or related organizations

This work is related to:

1) The Board IMS Testbed ad hoc group;

2) 3GPP IMS conformance testing (terminals);

3) MTS IPT activities such as interoperability testing methodologies and IMS Network Integration Testing;

4) ETSI Plugtests Service.

### 1.1.4	Priority within the TB

This STF is of high priority within TISPAN.  In particular, it should start and end as soon as possible, and preferably be completed in Q2 2007.

### 1.1.5	Motivation why the STF is urgently needed

It is essential that this work is done in a timely manner in order to synchronise with global testing activities, especially in the context of IMS (3GPP and TISPAN NGN). The expertise needed is specialised and should build on that already provided in earlier STFs. A contribution from the PTCC is essential.

## 1.2	Organization of the work

### 1.2.1	Confirmation of active support from the Members

The following companies are committed to supporting this STF in terms of participation in the STF Steering Group and providing input and review to the STF:

Deutsche Telekom, Telekom Austria, HP, Iskratel, Nokia, Telecom Italia.

The work will also be tracked by the Board IMS-TESTBED ad hoc group.

5 days voluntary expert contribution is anticipated.

### 1.2.3	Identification of tasks, phases, priorities, technical risk

This STF is of short duration and cannot be split into phases (the work needs to be done in as short a duration as possible).

There are  four main tasks:

Task 1) Analysis of relevant IMS specifications (base specs for the NNI and relevant IMS enabler specs);

Task 2) Analysis of existing test specifications (e.g. POC from the OMA);

Task 3) Development of IMS IOP Test Purposes.

Task 4) Development of IMS IOP Test descriptions.

### 1.2.4	Outcome of the STF

The outcome of the STF will be two Technical Specifications (TS).

DTS/TISPAN-06027-1 Test Purposes for IMS NNI Interworking

DTS/TISPAN-06027-2 Test Descriptions for IMS NNI Interworking

# 2	Consequences if not agreed:

Failure to agree to this STF will result in significant delay to the development of these two draft TSs.  It is likely that they would not be completed using voluntary contribution prior to the end of 2007.  Yet these TSs are urgently required in order to support expected ETSI and TISPAN activity in NGN IMS interoperability testing during 2007.

Without the availability of suitable test specifications, any NGN interoperability testing activities will be of no technical value, and of little commercial or promotion value.

# 3	Detailed description:

## 3.1	Subject title:

Interoperability Test Specifications for IMS NNI interworking.

## 3.2	Reference Technical Body:

TC TISPAN (WG6)

## 3.3	Other interested TBs (if any):

- 3GPP

- TC MTS

## 3.4	Steering Committee

A Steering Group (SG) for this activity will be put into place. Members of the SG are expected to come from the supporters of the WI (see 1.2.1) and Board IMS-TESTBED ad hoc group.

## 3.5	Support from ETSI Members

This STF has strong support from the ETSI membership. See 1.2.1

## 3.6	Target date for the start of work:

Start:	19 February 2007

## 3.7	Duration and target date for the conclusion of the work (TB approval):

Duration: 	3 months

Conclusion: 	May 2007

## Resources required

Total 65 person-days (60 person-days funded, 5 person-days voluntary)

Funding for manpower is 36 000 EUR (60 person-days @ 600 EUR/day).

### 3.8.1	Experts manpower

Total manpower resources required: 65 man-days split as follows:

- Developing the test specifications	60	man-days

- Drafting non-published documents:	3	man-days 1)

- Attending Technical Body and WG meetings: 	2	man-days 2)

Note 1) General STF management and writing Progress Reports etc.

Note 2)  The  PTCC will also attend meetings on behalf of the STF.

### 3.8.2	Estimated cost, additional to the manpower:

Total additional cost 0 EUR (i.e., no travel budget).

### 3.8.3	Estimated cost of Members’ contribution

Member voluntary effort in kind: 5 man-days. See 1.2.1..

## 3.9	Experts qualification required, mix of skills

1-2 experts are needed, with the following expertise:

- Expertise of IMS, especially the NNI and SIP.

- Expertise in interoperability testing.

- Knowledge of the OMA enabler tests for interoperability, e.g., PoC

- Support from the PTCC will be requested.

## 3.10	Scope of Terms of Reference:

The tests will be restricted to IMS NNI. Testing within an IMS network is outside the scope of this project.

Where possible use will be made of existing IOP tests (e.g., from OMA or GSMA) as a partial basis for these test specifications. The tests will be written in prose and where relevant, accompanied by sequence diagrams.

Formal test languages such as TTCN will not be used in this phase of the work.

## 3.11	Organization of the work in tasks and/or phases:

This STF is of short duration and cannot be split into phases (the work needs to be done in as short a duration as possible).

There are three main tasks:

Task 1) Analysis of relevant IMS specifications (base specs for the NNI and relevant IMS enabler specs);

Task 2) Analysis of existing test specifications for POC (from the OMA);

Task 3) Development of IMS IOP Test Purposes.

Task 4) Development of IMS IOP Test descriptions.

## 3.13	Base documents and their availability

The STF work will be based upon the following documents:

TISPAN NGN Rel-1 IMS (3GPP early Rel-7)

3GPP IMS specifications

Any relevant OMA Enabler specification series, such as for PoC, Presence.

## 3.14	Work Items from the ETSI Work Programme (EWP) for which the STF is required:

The STF will produce the following deliverables, for TB approval:

- DTS/TISPAN-06027-1

Title: Telecommunications and Internet converged Services and Protocols for Advanced Networking (TISPAN);

IMS NNI Interworking Test Specifications;

Part 1: Test Purposes for IMS NNI Interworking

Scope: To produce a basic set of interoperability test purposes for IMS interworking applicable at the IMS NNI, i.e. at the interface between two IMS networks. The tests will be driven by IMS end-to-end applications such as PoC or Presence

- DTS/TISPAN-06027-2

Title: Telecommunications and Internet converged Services and Protocols for Advanced Networking (TISPAN);

IMS NNI Interworking Test Specifications;

Part 2: Test Descriptions for IMS NNI Interworking

Scope: To produce a basic set of interoperability test descriptions

for IMS interworking applicable at the IMS NNI, i.e. at the interface between two IMS networks. The tests will be driven by IMS end-to-end applications such as PoC or Presence

## 3.15	Planned output schedule:

The STF will produce the deliverables according to the following time scale:

Work Item(s):

- DTS/TISPAN-06027-1

- DTS/TISPAN-06027-2

- Start of the work 	19/02/2007

- ToC and scope 	30/03/2007	TISPAN#13bis

- First stable draft for TB review	27/04/2007

- WG6 approval	18/05/2007	TISPAN#13ter

- TISPAN approval	01/06/2007	TISPAN#14

- Publication	28/07/2007

## Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 1.0 | 01 Aug 2006 | Martin Brand | Proposal | Preliminary draft proposal. |
| 1.1 | 31 Aug 2006 | Reiner Münch | Proposal | Minor updates by Reiner Münch. Preliminary proposal submitted to ETSI Secretariat |
| 1.2 | 22 Sept 2006 | Brand | Approved by Board#59, | Full ToR submitted to ETSI Secretariat |
| 1.3 | 14 Aug 2006 | Brand | Approved by TISPAN#12 | Start February |
| 1.4 | 30 Jan 07 | Berrini | Prep. Meet. | Schedule review |