|  | ToR STF 338 (DECT / NG DECT) |
| --- | --- |
|  | Status: approved by Board#62 |
|  | Version: 0.7 - Date: 17 December 2007 |
|  | Author: Dr. Günter Kleindl |
|  | Last updated by: Alberto Berrini |
|  | page 1 of 7 |

Terms of Reference for Specialist Task Force STF 338 (RG) 
(TB DECT / WG NG DECT) on 
”Base standards update for New Generation DECT”

# Reasons for proposing the Specialist Task Force (STF)

## Overview of the proposal

### Purpose of the work

The purpose of the work is to produce new versions of the standards EN 300 175-1 to 9 and EN 300 176-2, that contain the new functions for ‘New Generation DECT phase 2’ as well as the wideband speech transmission tests. Completion is planned until March 2008.

### Relation with the ETSI Strategic Objectives

DECT is one of the very successful ETSI standards. DECT is the world wide leading digital cordless technology and has been approved by ITU as IMT-2000 air-interface. DECT is selling in large and growing volumes. The following figure from the DECT Forum shows the expected market value development.

### Market impact, benefits to be gained

The DECT manufacturers including the chip manufacturers have come to the conclusion, that the market requires a new generation of DECT products. The DECT Forum has approached TC DECT to develop the specification for next generation DECT products, based on the market requirements as provided by DECT Forum. They also stressed the urgency of the work and therefore we agreed to develop the specification in phases. For the integration of NG-DECT products into home-gateways a higher level of interoperable features is required by the operators. The new generation DECT will not only further increase the quantity of products, but also the value of the DECT products.

### Stakeholders interest

ETSI members who support the NG-DECT work:  BMWA, DSP Group, France Telecom, Infineon, Institut für integrierte Schaltungen FHG-IIS, Philips, Sagem, Siemens, SiTel, SunCorp, Thomson.

The members of the DECT Forum requested ETSI to produce the specification as fast as possible.

### Relation with other activities within ETSI and/or related organizations

There is a complementary activity within the DECT Forum, who has established a marketing group for NG DECT to provide market requirements to TC DECT. DECT Forum is also promoting the NG DECT technology in close cooperation with the ETSI secretariat.

There are related liaisons with TC TISPAN, TC STQ, SAGE, ITU-T SG12, ITU-T SG16 and ISO/IEC JTC1/SC29. The parts regarding the speech transmission parameters are intended to be developed in cooperation with ETSI TC STQ

### Priority within the TB

Highest priority.

### Motivation why the work cannot be performed within the TB (mandatory)

The DECT Forum has expressed an urgent need for the completion of the Specifications and with the support of a full-time expert the compilation of the documents can be done much faster. There are many technical contributions from the members of the working group, but the various experts are not so familiar with the ETSI drafting rules and one editor, who can transform the input into the correct style will help to produce a high quality output much more rapidly.

### Confirmation of interest and active support from the Members

There are more than 50 persons involved in the discussions on the mailing list for ‘New Generation DECT’. The NG DECT Working Group meets 6-times per year with an average participation of 15 experts. In addition the DECT Forum provides input regarding the requirements and market information.

## Organization of the work

### Identification of tasks, phases, priorities, technical risk

The task is to produce updates of the base standard EN 300 175 parts 1 to 8 and the speech tests EN 300 176-2 to include the new protocol elements for ‘New Generation DECT phase 2’ as well as the transmission parameters and tests for wideband speech.

The risk is very low as the new features are based on the well proven DECT concept and because companies are already developing systems to validate the functions.

### Outcome of the STF

Expected output:

EN 300 175 - 1 to 8 update

EN 300 176-2 update

# Consequences if not agreed:

The DECT Forum has asked ETSI to produce the specifications for ‘New Generation DECT’ as fast as possible in order to be able to quickly develop a standardized solution and to ensure that the DECT technology continues to hold the top market position in the cordless domain. There is strong competition from other technologies, e.g. WLAN, and any delay of the introduction of ‘New Generation DECT’ products will hurt the DECT industry. The support of an STF is essential for the timely production of the standards and the seamless continuation of the DECT success story.

# Detailed description:

## Subject title: Base update for NG DECT

## Reference Technical Body:

TB: TC DECT

WG: NG DECT

## Other interested TBs (if any):

DECT Forum:	provides requirements and needs the ETSI NG DECT specification in return

TC TISPAN:	to align network and terminal requirements

TC STQ:	concerning wideband speech transmission issues

TC SAGE:	regarding security algorithms

## Steering Committee

The chairman of TC DECT together with the WG NG DECT will act as Steering Committee.

The DECT_NewGeneration email-list will be used for technical discussions and information distribution.

Meetings will be the plenary and the WG NG DECT meetings. Additional ad-hoc meetings will be scheduled as required.

Telephone conferences will be arranged, if needed.

## Support from ETSI Members

The following ETSI members have confirmed their support for the NG DECT activities:

Bundesnetzagentur: Bernd Wolf

DSPG: Steven Dickinson

France Telecom R&D: Stéphane Proust

Fraunhofer IIS: Manfred Lutzky

Infineon: Ingolf Karls, Ulf Magnusson

Thomson Telecom: Guy-Louis

Philips: Jochen Kilian

Sagem: Hoel Guilcher

Siemens: Dieter Kehren, Günter Kleindl

SiTel: Oliver Maiwald

SunCorp: Mark Barrett

## Target date for the start of work:

October 2007

## Duration and target date for the conclusion of the work (TB approval):

Duration: 8 months

Conclusion of work: June 2008

## Resources required

Total resources required from the ETSI budget: 74 000 EUR. (total of 3.8.1, 3.8.2, 3.8.3)

2007: 37 000 EUR

2008: 37 000 EUR (funding to be confirmed by Board#64 under 2008 budget)

### Experts manpower

Total manpower resources required: 120 working days (72 000 EUR)

Additional non-remunerated resources required: 0 working days

### Travel cost:

Total travel cost 2 000 EUR, to attend Technical Body and WG meetings (2 meetings at European location outside ETSI).

## Experts qualification required, mix of skills

The following experts are required to perform the work.  The actual number of experts and mix of skills may depend on the actual applications received and will be decided when setting up the STF:

Number of experts required: 1

Relevant expertise required: protocol specification, especially knowledge of DECT layer 2 and 3

Experience with drafting ETSI specifications is required

Period over which the experts are required and duration of the secondment: full time for 6 months

## Scope of Terms of Reference:

The scope of the work is the production of an update of the standards EN 300 175-1 to 9 and EN 300 176-2 to include all the protocol extensions for the phase 2 of New Generation DECT and to add the speech transmission parameters.

The requirements for ‘New Generation DECT’ have been defined by the DECT Forum. TC DECT is working together with DECT Forum to select those features, which have to be supported in the specifications for the different phases of NG DECT. TC DECT has produced the Technical Report TR 102 570 to provide an overview of the new activities and to collect information concerning the agreed standardization choices. This report will be further updated to reflect the latest decisions in TC DECT.

## Organization of the work in tasks and/or phases:

EN 300 175-1 to 8 update: 4.5 month

EN 300 176-2 update: 1.5 months

## Validation

NA

## Related activity in other bodies and co-ordination of schedules:

A joint meeting with experts from TC STQ is planned in December 2007, during the meeting of the NG DECT working group.

## Base documents and their availability

The STF work will be based upon the following documents:

| Work Item | Title | Current Status |
| --- | --- | --- |
| REN/DECT-000241-1 to 8 | Digital Enhanced Cordless Telecommunications (DECT); Common Interface (CI); Part 1 to 8 | OAP |
| DTS/DECT-NG0243 | Digital Enhanced Cordless Telecommunications (DECT); New Generation DECT phase 1, wideband speech | published |
| EN 300 176-2 | Digital Enhanced Cordless Telecommunications (DECT); Test specification; Part 2: Speech | published |

## Work Items from the ETSI Work Programme (EWP) for which the STF is required:

The STF will produce the following deliverables, for TB approval:

| WI Reference | Title | Deliverable | Scope |
| --- | --- | --- | --- |
| REN/DECT-000248-1 | DECT; Common Interface (CI); Part 1: Overview. | EN 300 175-1 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000248-2 | DECT; Common Interface (CI); Part 2: Physical Layer (PHL). | EN 300 175-2 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000248-3 | DECT; Common Interface (CI); Part 3: Medium Access Control (MAC) Layer. | EN 300 175-3 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000248-4 | DECT; Common Interface (CI); Part 4: Data Link Control (DLC) Layer. | EN 300 175-4 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000248-5 | DECT; Common Interface (CI); Part 5: Network (NWK) Layer. | EN 300 175-5 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000248-6 | DECT; Common Interface (CI); Part 6: Identities and addressing. | EN 300 175-6 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000248-7 | DECT; Common Interface (CI); Part 7: Security Features. | EN 300 175-7 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000248-8 | DECT; Common Interface (CI); Part 8: Speech coding and transmission. | EN 300 175-8 | Maintenance of and inclusion of new features to the Base Standard |
| REN/DECT-000249-2 | DECT; Test specification; Part 2: Speech | EN 300 176-2 | Maintenance of and inclusion of new features to the test specification |

## Planned output schedule:

The STF will produce the deliverables according to the following time scale:

Work Item(s):

REN/DECT-000248-1 to 8 (EN 300 175 1 to 8)

REN/DECT-000249-2 (EN 300 176-2)

Start of the work STF 338	1 October 2007

First draft for WG review	17 December 2007	DECT NewGen#12 18-19 Dec 2007

Second draft for WG review	20 February 2008	DECT NewGen#13 26-27 Feb 2008

Draft for WG approval	21 April 2008 	DECT NewGen#14 22-23 April 2008

WG approval	30 May 2008	By correspondence

Draft for TB approval	30 May 2008 	By correspondence

TB approval	30 June 2008

Publication	15 July 2008

In addition, the STF will produce the following reports:

Date delivery
	Milestone	by STF leader:	To be approved by:

Progress Report#1	17 December 2007	DECT NewGen#12 18-19 Dec 2007

Progress Report#2	25 February 2008	DECT NewGen#13 26-27 Feb 2008

Progress Report#3	21 April 2008	DECT NewGen#14 22-23 Apr 2008

Final Report 	30 May 2008	Final deliverables approved by DECT NewGen by correspondence

The STF milestones will be as follows:

Milestone A: Progress Report#1 to be approved by DECT NewGen#12 (18-19 Dec 2007)

Milestone B: Progress Report#2 and 2nd draft deliverables for WG review to be approved by DECT NewGen#13 (26-27 February 2008).

Milestone C: Progress Report#3 and draft deliverables for WG review by DECT NewGen#14 (22-23 April 2008).

Milestone D: Final Report and final drafts of REN/DECT-000248 (EN 300 175) parts 1 to 8 and REN/DECT-000249-2 (EN 300 176-2) approved by DECT NewGen by correspondence.  The target for the conclusion of the approval by correspondence is 30 May 2008.

The STF Leader will upload the draft reports and deliverables on the DECT docbox before the meeting and inform the ETSI Secretariat (STFLINK) that the documents are available.

# Performance indicators

Effectiveness: (e.g. number of participants in the project, number of meetings/participants held in relation to this work, number of presentations made on the activity, feedback received)

Stakeholder engagement: stakeholder representation in the project and the number of liaison activities performed (especially at the international level).

Dissemination of results: assessment of the effectiveness of activities related to the dissemination of project deliverables and efforts made to raise industry awareness of the activity (including e.g. hits made on the project web pages and downloads of drafts for comment).

Impact: satisfaction of the stakeholders with the progress and outputs of the project, in the occasion of Steering Group meetings, plenary meetings, workshop.

Timeliness: project progress in relation to the work plan schedule, acceptance of the deliverables by the TB (approval of Progress Reports, interim and final deliverables at the planned dates)

# Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.0 | 16 May 07 | Kleindl | To be approved by TB DECT by correspondence | Initial DECT STF request |
| 0.1 | 21 May 07 | Berrini | For submission to OCG#32/Board#62 | Editorials |
| 0.2 | 24 May 07 | Martin Arndt | Submitted to OCG#32/Board#62 | Added Work Items details |
| 0.3 | 12 Jun 07 | Berrini | Approved by Board#62 | Removed details on approval |
| 0.4 | 2007-07-02 | Arndt |  | WI references from WPM added following TB approval of WIs. |
| 0.5 | 17 Sep 07 | Berrini |  | Time scale revised for late start + limited availability experts. Target finish end March 08. |
| 0.7 | 17 Dec 07 | Berrini |  | Updated schedule DECT meetings 2008, deliverables and milestones |