|  | ToR STF 386 Ph. 3 (ERM / TG17 WP3) |
| --- | --- |
|  | Version: 3.5- Date: 6 November 2012 |
|  | Author: ERM TG17 WP3, |
|  | Last updated by: Alberto Berrini, 4 December 2012 |
|  | page 1 of 10 |

Terms of Reference for Specialist Task Force STF 386 Phase 3
PMSE – Cognitive Radio ERM / TG17 WP3 
“Methods, parameters and test procedures for cognitive interference mitigation techniques for use by PMSE devices (Programme Making and Special Events)”

Document status

| Current status of ToR | Approved by TC ERM and Board#85 |
| --- | --- |
| Work Items approved | DTR/ERM-TG17WG3-013 (Phase 3). |

# Confirmation of request for funding of Phase 3

The STF has successfully completed Phase 1 and 2 of the work, even if there has been some delay with respect to the original plan, in the order of 3-4 months.

The deliverable of Phase 1 (TR 102 799) has been published.

The deliverable of Phase 2 (TS 102 800) has been published.

The purpose of Phase 3 is to validate TS 102 800.  The STF will specify input test scenarios for the technology demonstrator implementing TS 102 800 on protocols for spectrum access and sound quality control systems for Programme Making and Special Events (PMSE) applications using cognitive interference mitigation techniques.

The C-PMSE project will provide essential input based on the carried out field measurement at their test site and practical assistance to STF386. Therefore STF386 is also dependant on the timing and schedule the C-PMSE project.

CPMSE project is currently in Phase 2.  It will start to set up a test bed in Berlin from January.  A “Radio Link Simulator” is in alpha stadium and will reach beta stadium end of 2012.  Will be operational at end of CPMSE Phase 2 (end May 2013)..  Operation of test bed and Radio Link Simulator (Phase 3) is planned to run until end November.

Note: downscaled versions of the test bed are reproduced in the Universities of Hannover and Nuremberg.

Synchronization with CPMSE will be decided during the first face-to-face meeting of STF386 Phase 3 that will be held in January 2013.

The STF will take advantage of the synergy with the research project C-PMSE to validate and upgrade the TS developed in the previous phases.  This is a unique opportunity to progress standardization in parallel with research.

On the other hand, the timing for Phase 3 is dependent on the actual progress of the RF tests in the C-PMSE research project, which has suffered of some delay and will extend in 1st half 2013.

As close bi-directional exchange between STF386 and the C-PMSE project is required and initial results from C-PMSE project sufficient to start collaboration cannot be expected before January 2013.

Phase 3 of the STF work should then be started in January 2013. This would allow a certain time of parallel work, in which information between the two teams could be directly exchanged.

# Reasons for proposing the Specialist Task Force (STF)

## Definition of PMSE including SAP/SAB, ENG/OB and SNG

Taken from draft ECC Report 2, developed by FM51.

The term Programme Making and Special Events applications (PMSE) describes radio applications used for SAP/SAB, ENG/OB and applications used in meetings, conferences, cultural and education activities, trade fairs, local entertainment, sport, religious and other public or private events for perceived real-time presentation of audio-visual information.

The definitions of SAP/SAB and ENG/OB are set out as follows:

SAP:	Services Ancillary to Programme making (SAP) support the activities carried out in the making of “programmes”, such as film making, advertisements, corporate videos, concerts, theatre and similar activities not initially meant for broadcasting to general public.

SAB:	Services Ancillary to Broadcasting (SAB) support the activities of broadcasting industry carried out in the production of their programme material.

The definitions of SAP and SAB are not necessarily mutually exclusive. Therefore they are often used together as “SAP/SAB” to refer generally to the whole variety of services to transmit sound and video material over the radio links.

ENG:	Electronic News Gathering (ENG) is the collection of video and/or sound material by means of small, often hand-held wireless cameras and/or microphones with radio links to the news room and/or to the portable tape or other recorders.

OB:	Outside broadcasting (OB) is the temporary provision of programme making facilities at the location of on-going news, sport or other events, lasting from a few hours to several weeks. Mobile and/or portable radio links are required for wireless cameras or microphones at the OB location. Additionally, radio links may be required for temporary point to point connections between the OB vehicle, additional locations around it, and the studio.

The definitions of ENG and OB are not mutually exclusive and certain operations could equally well reside in either or both categories. Therefore, it has been a long practice within the CEPT to consider all types of such operations under the combined term “ENG/OB”. It is also understood that ENG/OB refers to terrestrial radio communication services, as opposed to SNG/OB term, which refers to similar applications but over the satellite radio communication channels.

The SAP/SAB applications include both ENG/OB and SNG/OB applications, but also the communication links that may be used in the production of programmes, such as talk-back or personal monitoring of sound-track, telecommand, telecontrol and similar applications.

Quality requirements of PMSE applications can vary depending on the task in hand. The bandwidth of the signal to be transmitted i.e. audio or video has a direct impact on the spectral bandwidth required.

The perceived quality of the signals is going to be dependent on their potential final use. The uses can vary from SNG links into a news programme through to a high quality HD TV production.

The reliability of service again can vary according to the task in hand. Typically within the events for large numbers of people and for broadcast applications there is frequently a need for a high degree of protection for the signals. This required protection inherently puts constraints on the amount of spectrum required to guarantee this quality of service.

Please see ECC Report 002, ERC Reports 38 and 42 for further details and definitions

PMSE is under increasing strain and demand following the advent of the Digital Dividend and the Digital Switch-Over. The increasing demand for PMSE services and the demand for extra bandwidth are putting even more strain on the over-stretched PMSE1 spectrum4. Some easement has been obtained by provision of access to L Band, but this is of limited capacity and has many operational constraints. Without access to new spectrum the only way to ensure sufficient capacity to cater for demand is to utilise cognitive spectrum access methods to allow usage of hitherto un-available spectrum and to facilitate spectrum sharing. The proposed STF would investigate this concept, define a suitable method and apply it on a technology demonstrator, to be developed by the industrial members of ERM TG17 in the frame of a separate research project.

For the purposes of this STF, the term ‘PMSE’ will encompass the requirements of PWMS1, SAB1 and SAP1 applications, as given in the above mentioned definition, developed by FM51

The PMSE market urgently needs access to new spectrum resources to satisfy existing and future demand. New, or revised, ETSI standards would fulfil this purpose and give a competitive boost to the market. Without adequate spectrum resource the multimedia industry, which the Digital Dividend is feeding, will falter through lack of available  resources.

TC ERM is, through its TG17 WP3 (Radio Microphones, Cordless Audio and Audio Links) task group, developing standards for the audio applications that come under the PMSE definition.

ERM TG17/WP3 has developed ETSI TR 102 546 (ETSI System Reference Document) that includes the technical characteristics for Professional Wireless Microphone Systems (PWMS).

Currently(12/2011) TG17WP3 is developing ETSI TR 103 058, that includes the technical characteristics for a broader scope of PMSE applications such as Professional Wireless Microphones, In Ear Monitoring systems, tour guide systems, professional wireless conference systems, intercom systems

The proposed STF work will lead afterwards in a following step to revision making of Harmonized European Standard EN 300 422, EN 301 357 and EN 300 454 to incorporate additional technical parameters such as for a Detect-And-Avoid (DAA) mechanism or inclusion of requirements for a site installed database to further increase the efficient use of spectrum of these wireless, mainly audio, devices.

The development of exact parameters, operation principles and test definition and purpose is seen as a prerequisite for :

definition of a specialized method for spectrum access and the guarantee of a high sound production quality on selected frequencies, using cognitive radio techniques.

recommendation on inclusion of technical requirements in the Harmonized European Standard EN 300 422 and other related standards EN 301 357, EN 300 454 or a new ETSI standard or specification.

investigation of suitable cognitive interference mitigation techniques and recommendation of technical requirements including, but not limited to:

  - a site installed database that may also use GNSS positioning information;

  - an organisational radio channel or beacon  (intra- PMSE use) for PMSE in the UHF frequency range;

  - intelligent detection and cataloguing of victim systems

the application of the test methods to an UHF spectrum access demonstrator, using cognitive interference mitigation techniques;

Please note that although the technology demonstrator will concentrate on one particular application, the technology will ultimately be transferable to other PMSE applications.

[note: add some words there]

## Overview of the proposal

### Purpose of the work

The purpose of the work is to achieve co-existence of high audio quality PMSE devices that use a 100% transmitter duty cycle emission profile with victim radio services such as broadcasting services and other and future Land Mobile Services and applications in the UHF frequency range. This includes especially the UHF-TV band that is currently under investigation under the “Digital Dividend” discussions in EC, ECC and ETSI and future potential applications: WSD’s.

All procedures, techniques and solutions developed by this STF should be ultimately transferrable to other SAB/SAP applications and their assigned frequency bands.

It should also be stressed, that whilst the demonstrator might be designed for a specific frequency range (e.g. UHF-TV band), the techniques should be applicable to a wide range of frequencies. The work does not solely focus on one specific frequency band.

For the complete standardisation of the mechanisms, suitable technical parameters and test procedures are needed. These include flexible mechanisms based on detection thresholds, recognition of victim service patterns, corporate awareness of uncoordinated PMSE usage within the same area by using a common database, beacons or common organizational channel. Attention also should be paid to methods for making this information available to other PMSE users.

There are currently several sub-groups of ECC/CEPT dealing with regulatory and co-existence aspects of PMSE that will influence the technical requirements, content and standardization requirements within ETSI (i.e. ECC/TG4, SE24, SE43, FM50, FM51, SE7, FM/SRDMG). It will be the responsibility of ERM TG17 WG3 to mirror these regulatory requirements into technical specifications and test procedures.

### Relation with the ETSI Strategic Objectives

Co-existence with other radio services and applications is one of the strategic topics in all RF conformance standards developed in ETSI.  It is also related to article 3.2 of the R&TTE and EMC Directive and is therefore important for ETSI in the strategic area European Standards Organization.  The new draft of R&TTE Directive includes Transmitter requirements and the Receivers are within the EMC Directive.

The results of this STF will ease the development of a revised EN 300 422, EN 301 357 and EN 300 454 or even stimulate the creation of a new Harmonized European Standard under the EC standardization Mandate M/289.

### Market impact, benefits to be gained

PMSE is the first step in a chain of production and directly affects the viability of many dependant entertainment industries, such as TV broadcasting, stage shows, theatre productions, sporting events, political events, social events, religious events, commercial events etc. Any restriction or degradation of PMSE services will not only damage the PMSE industry, but also those dependant industries, In many cases the future media sales, such as music DVDs, are affected by any restriction or degradation of PMSE services.

Much of the existing [audio] equipment will become unusable following the reorganisation of the 470-862 MHz band and the reallocation of parts to mobile and other services. Following the EC decision 2010/267/EU the band 790-862MHz was allocated to Electronic Communications Systems (ECS) in Europe. The expectation is that the market for PMSE devices which will work without interference to the program being made will grow larger and faster if devices demonstrate a higher level of compatibility in a wider spectrum which is also available for other radio services and applications in Europe.

Other PMSE Equipment is equally affected by the ongoing changes in spectrum use and spectrum availability for these applications.

### Relation with other activities within ETSI and/or related organizations

For the completion of the standardisation process of cognitive interference mitigation mechanisms, the following contributions are required:

definition of a specialized method for spectrum access and the guarantee of a high sound production quality on selected frequencies, using cognitive radio techniques

suitable technical parameters for a cognitive interference mitigation mechanism

a spectrum access test bed for interference mitigation performance validation

the validation of suitable test procedures in a certified test laboratory environment

development of syntax, semantics and functionality of the selected spectrum access and interference mitigation system

In order to complete its task, the STF will establish technical collaboration with existing organisations (see the list below) conducting technical studies and research into cognitive interference mitigation and spectrum access methods as well as suitable support systems. The STF will consolidate the results for contributing to test specifications complementing the base Harmonized European Standards EN 300 422, EN 301 357 and EN 300 454 for PMSE devices.

Liaisons will be established with:

ECC/TG4, SE24, SE43, FM50, FM51, SE7, FM/SRDMG, for the provision of cognitive interference mitigation regulatory requirements

CEPT / ECC WGFM PT 50

EU and National Projects on the subject

CEPT/ECC WGSE's established project team PT SE43 that will define technical and operational requirements for the operation of cognitive radio systems in the white spaces of the UHF broadcasting band (470-790 MHz) to ensure the protection of incumbent radio services and systems and investigate the consequential amount of spectrum potentially available as “white space”.

IEEE 802.22, 802.16 working groups.

JTC Broadcast, TC BRAN, TC RRS

GRSC WG1

The STF liaisons are planned to be coordinated in a timely manner via the proposed steering committee, i.e. the STF experts will not liaise directly but look for approval by the steering committee members.

### Priority within the TB

High

### Motivation why the work cannot be performed within the TB

Experience with the development of other interference mitigation techniques has shown that involvement of experts on radio frequency conformance testing with knowledge of the upper layer protocols used for PMSE communications devices is needed. The generation of this kind of specification requires significant concentrated effort, and it cannot be expected that this effort can be provided only on a voluntary basis. Hence the involvement of testing, spectrum and regulatory experts is needed in order to assure timely completion and high quality of the first release of the test specifications. These testing experts are not available at the TC ERM level and need to be recruited on a funded basis.

### Stakeholders’ interest and active support from the Members

Active support including voluntary contributions are indicated in clause 3.5.

ERM TG17 WG3 will progress their work on the Harmonized Standards EN 300 422, EN 301 357, EN 300 454 based on the results of the proposed STF work. This will greatly improve usage of the Harmonized European Standard.

## Organization of the work

### Identification of tasks, phases, priorities, technical risk

The documents already produced by the STF during Phases 1 and 2 are:

- TR 102 799 - ETSI Technical Report on “Operation methods and principles for spectrum access systems for PMSE technologies and the guarantee of a high sound production quality on selected frequencies utilising cognitive interference mitigation techniques”. This Report will analyse the various possible techniques and recommend a specific method.

- TS 102 800 - ETSI Technical Specification on the recommended spectrum access technique, defined in (a)

The purpose of Phase 3 is to produce the ETSI Work Item DTR/ERM-TG17WG3-013:

- TR 102 801 - ETSI Technical Report of the different RF compliance tests for the selected spectrum access mechanism, as defined in (b)

The work is done in three phases.

Phase 1: Approval of the ETSI TR 102 799, as in step (a), published in June 2010.

Phase 2: Approval of the ETSI TS 102 800, in step (b), published in January 2011.

Phase 3: Approval of the TR 102 801 on validation of the RF tests, with measurements from a technology demonstrator, by December 2012

Phase 1	The amount of work is estimated to be approximately 25% of the overall funding

Phase 2	The amount of work is estimated to be approximately 25% of the overall funding

Phase 3:	The amount of the work for the respective radio parameter measurements is estimated to be approximately 50% of the funding. This work is divided into two main activities:

i) preparation for validation and testing and

ii) specification of input test scenarios and validation of a technology demonstrator.

The amount of effort necessary is anticipated to be equal for each task (i.e. 25% of the total resource each). See 3.10 for more details on validation.

## Risk involved:

The risk involved is low based on the existing experience with similar functional mechanisms and the fact that Electronic Communications Committee (ECC) will set out a firm basis.

# Consequences if not agreed:

PMSE is under increasing strain and demand following the advent of the Digital Dividend and the Digital Switch-Over. The increasing demand for PMSE services and the demand for extra bandwidth are putting even more strain on the over-stretched PMSE spectrum. Without access to new spectrum the only way to ensure sufficient capacity to cater for demand is to utilise cognitive spectrum access methods to allow usage of hitherto un-available spectrum and to facilitate spectrum sharing.

TG17 WG3 itself does not have the resources to investigate this issue. If the STF proposal is not agreed, it would not be possible to explore cognitive spectrum access techniques and it would not be possible to satisfy the growing market demand for PMSE services.

The definition of the operation principles and test specifications as described in the present document is key to the testing and certification activities that should ensure the co-existence of PMSE devices having cognitive interference mitigation functions with other radio services and applications. A poor initial specification can be detrimental to the future successful market development of PMSE in Europe. Delaying the availability of good test specifications may adversely affect the arrival of products in the market place and their level of conformance.

# Detailed description:

## Subject title:

Specialist Task Force STF PMSE – principles, parameters and test procedures for cognitive radio functions used by PMSE devices (Programme Making and Special Events) using cognitive interference mitigation techniques”

## Reference Technical Body:

TC ERM will be responsible for the approval for publication of all the deliverables of this STF.

## Other interested TBs (if any):

See 1.1.4

## Steering Committee

TC ERM TG17 WP3 will monitor the progress through a steering committee that will consist of the ERM Chairman, the ERM TG17 Chairman, a representative from a regulatory authority and a representative of the PMSE industry and users.

## Support from ETSI Members

The ETSI members supporting this work in the STF are Sennheiser, Shure, AKG, APWPT, ASP, Bosch, Myrcomm Consulting, BMWi, Estonian Technical Surveillance Authority, and OFCOM (CH), BMVIT (Austria), beyerdynamic

Member companies are prepared to voluntarily contribute a total of 140 working days:

20 working days towards drafting of STF deliverables

120 working days for performing review of the deliverables (drafts for review or approval in the TB).

This represents an estimated equivalent total voluntary contribution of 84 000 Euro.

## Target date for the start of work for Phase 3:

The work on Phase 3 is planned to start in January 2013.

## Duration and target date for the conclusion of Phase 3:

The duration of the Phase 3 is planned to be up to mid 2014:

Phase 3: ETSI Technical Report of the different RF compliance tests for the selected spectrum access mechanism.

## Resources required

The STF has spent a total amount of 39,800 € to perform Phases 1 and 2.

The actual cost has been much lower than the resources agreed by the Board, thanks to a very high voluntary contribution of the experts.

The remaining resources for Phase 3 are 65 working days (55 remunerated + 10 voluntary = 33 000 €) and 3 000 € for travel.

All funding requests will be supported by the evidence of the outcome of the previous phases.

### Experts manpower

65 working days (55 remunerated + 10 voluntary = 33 000 €

### Travel cost:

Travel costs may be incurred if attendance is required at Steering Group, TC-ERM or CEPT meetings.

Maximum 3 000 EUR, during Phase 3.

### Other cost: None.

## Experts qualification required, mix of skills

The following experts are required to perform the work.  The actual number of experts and mix of skills may depend on the actual applications received and will be decided when setting up the STF.

Number of experts required: 3-4, available part time for a total of 150 working days (apportionment according to the distribution of skills)

Each expert should have experience in one or more of the following areas:

PMSE spectrum issues

PMSE regulatory issues

PMSE standardisation issues

RF conformance testing and

Development of RF test beds.

## Scope of Terms of Reference:

During Phases 1 and 2, the STF has done the following work:

Investigate methods, principles and techniques for spectrum access systems for PMSE technologies and for the guarantee of a high sound production quality on selected frequencies utilising cognitive interference mitigation techniques.

Deliver an ETSI Technical Report on “Operation methods and principles for spectrum access systems for PMSE technologies and for the guarantee of a high sound production quality on selected frequencies utilising cognitive interference mitigation techniques”, based on the findings under (1). This Report will analyse the various possible techniques and recommend a specific method.

Deliver an ETSI Technical Specification on the recommended spectrum access technique, defined in (2).

During Phase 3, the STF will:

Specify input test scenarios for a demonstrator for the TS developed under (3) and test its compliance.

Deliver an ETSI Technical Report of the defined RF compliance tests, carried out under (0), for the selected spectrum access mechanism defined in (3)  STF386 will propose the type of compliance required, which will be different from the current EN 300 422 specifications.

Please note that although the technology demonstrator will concentrate on one particular PMSE application and frequency band, the theory will be applicable to all PMSE applications.

## Related activity in other bodies and co-ordination of schedules:

The STF will interact with the responsible TG, i.e. ERM TG17 WP 3 task group and its STF steering group.

## Base documents and their availability

The STF work will be based upon the following base standards and other reference documents:

| Document | Title | Current Status |
| --- | --- | --- |
| ETSI TR 102 546 | The technical characteristics for Professional Wireless Microphone Systems (PWMS). | approved |
| ETSI TR 103 058 | Electromagnetic compatibility and Radio spectrum Matters (ERM); Technical characteristics for Programme Making and Special Events (PMSE) applications; System Reference Document | draft |
| ECC Report 002 | SAP/SAB (incl. ENG/OB); Spectrum Use and Future Requirements; Lisbon, February 2002 | Approved under revision |
| ERC Report 038 | “Handbook on radio equipment and systems video links for ENG/OB use” (01/04/2001). | approved |
| ERC Report 042 | “Handbook on radio equipment and systems radio microphones and simple wide band audio links” (01/04/2001) | approved |
| IEEE 802.22.1 | Task Group protection wireless audio | Published |
| EN 300 422 | Electromagnetic compatibility and Radio spectrum Matters (ERM); Wireless microphones in the 25 MHz to 3 GHz frequency range; Part 2: Harmonized EN covering essential requirements of article 3.2 of the R&TTE Directive | Published |
| EN 301 357 | Electromagnetic compatibility and Radio spectrum Matters (ERM); Cordless audio devices in the range 25 MHz to 2 000 MHz; Part 2: Harmonized EN covering essential requirements of article 3.2 of the R&TTE Directive. Cordless audio devices | Published |
| EN 300 454 | Electromagnetic compatibility and Radio spectrum Matters (ERM); Wide band audio links; Part 2: Harmonized EN under article 3.2 of the R&TTE Directive | published |
| ECC TG4 | CEPT Report 32 "Report from CEPT to EC in response to the Mandate on Recommendation on the best approach to ensure the continuation of existing Program Making and Special Events (PMSE) services operating in the UHF (470-862 MHz), including the assessment of the advantage of an EU-level approach" | Draft Public consultation available |
| ECC WGSE PTSE24 | ECC Report 121 "Compatibility studies between PWMS and other services/systems in the bands 1452-1492 MHz, 1492-1530 MHz, 1533-1559 MHz also considering the services/systems in the adjacent bands" | Approved Published |
| ECC WGSE PTSE24 | ECC Report 147: Additional Compatibility Studies Relating To PWMS In The Band 1518-1559 MHz Excluding The Band 1543.45-1543.95 MHz And 1544-1545 MHz; Tromsoe, May 2010 | Approved Published |
| ECC WGFM PTFM45 | ECC Report 161: Additional technical considerations relating to the L-BAND and the MA02REVCO07 agreement | Approved Published |
| TR 102 799 - | Operation methods and principles for spectrum access systems for PMSE technologies and the guarantee of a high sound production quality on selected frequencies utilising cognitive interference mitigation techniques | Published STF 386 Phase 1 |
| TS 102 800 | Protocols for spectrum access and sound quality control systems using cognitive interference mitigation techniques | Published STF 386 Phase 2 |
| Recommendation ITU-R BT.1871 | User requirements for wireless microphones | Available published |
| Report ITU-R.BT.2069 | Tuning ranges and operational characteristics of terrestrial electronic news gathering (ENG), television outside broadcast (TVOB) and electronic field production (EFP) systems | Available published |
| Recommendation ITU-R M.1824 | System characteristics of television outside broadcast electronic news gathering and electronic field production in the mobile service for use in sharing studies | Available published |
| Recommendation ITU-R F.1777 | System characteristics of television outside broadcast, electronic news gathering and electronic field production in the fixed service for use in sharing studies | Available published |

## Work Items from the ETSI Work Programme (EWP) for which the STF is required:

The STF will produce the following deliverables, for TB approval:

| WI number | Work item title |
| --- | --- |
| DTR/ERM-TG17WG3-013 Phase 3 | TR 102 801 “Test reports from technology demonstrator implementing sections of TS 102 800 on protocols for spectrum access and sound quality control systems for PMSE using cognitive interference mitigation techniques.” Scope: to specify input test scenarios for a technology demonstrator implementing TS 102 800 on protocols for spectrum access and sound quality control systems for Programme Making and Special Events (PMSE) applications using cognitive interference mitigation techniques. |

## Planned output schedule:

DTR/ERM-TG17WG3-013 (aligned with C-PMSE)

| Start of technology demonstrator build | January 2013 |
| --- | --- |
| Start of tests | April 2013 |
| End of C-PMSE Phase 2 (set up platform) (STF386 can use for one month to collect data for the TR) | May 2013 |
| Start of the work on TR | June 2013 |
| End of C-PMSE Phase 3 (execution of tests, if approved) | November 2013 |
| Early draft TR | December 2013 |
| Final Draft for TG17-WP 3 approval | July 2014 |
| TB approval | September 2014 |
| Publication | October 2014 |

(see also §4.7 for details on each of the work items)

The STF will also provide the following reports (provisional schedule):

| Mil | Description | Target date milestone achieved |
| --- | --- | --- |
| C | Progress Report#1 for information to ERM#49 (18-22 Mar). | 22 Mar 2013 |
| D | Progress Report#2 with the STF work plan defined after conclusion of CPMSE Phase 2 and preliminary ToC of the TR, to be contributed to ERM#50 (24-28 June). | 28 Jun 2013 |
| E | Progress Report#3 and preliminary early draft with consolidated ToC and some content, to be contributed to ERM#51 (18-22 Nov). | 22 Nov 2013 |
| F | Progress Report#3 and early draft TR uploaded on ERM Portal | 31 Dec 2013 |
| 2014 | Progress Reports to each ERM meeting and current draft TR uploaded on ERM Portal | tbd |
| Final ETSI | Final Report and TR approved by TG17 and TC ERM plenary and accepted by ETSI Secretariat for publication. The Final Report and the draft TR must be uploaded by the STF Leader on the ERM contributions area at least two weeks before the ERM plenary. | tbd |

# Abbreviations

PMSE	Programme Making & Special Events

SAB	Services Ancillary to Broadcasting

SAP	Services Ancillary to Programme making

PWMS	Professional Wireless Microphone Systems

DAA	Detect And Avoid

GNSS	Global Navigation Satellite System

# Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 1.0 | 22 April 2009 | ERM TG17 WP 3 | Proposal | Adopted by ERM TG17 WP 3 |
| 1.1 | 6 May 2009 | ERM Chairman | Proposed revisions | Mainly an editorial improvement. Clarification about the status of the work item on EN 300 422 and also about liaison are requested. |
| 1.2 | 8 May 2009 | Thomas Weber | Proposed Revision | incorporation of comments as agreed with ERM chairman |
| 1.3 | 8 May 2009 | ERM Chairman | Proposal for consideration by ERM for approval | Only editorial changes were made with respect to version 1.2. |
| 1.4 | 3 Jun 09 | Berrini |  | Work Item codes, editorials |
| 1.5 | 12 Jun 09 | ERM Chair | For Board#73 approval | Added names of additional supporting members. |
| 1.6 | 18 Jun 09 | Berrini | Approved B73 | Clarified that STF will not build the demonstrator |
| 1.7 | 18 Aug 09 | Berrini | Prep. Meet. | Updated base documents, liaisons |
| 1.8 | 25 Aug 09 | Berrini | Prep. Meet. | Editorials |
| 2.0 | 12 Oct 10 | Berrini | Phase 2 | Proposal for funding under 1st allocation 2011 (OCG#42, Board#80) |
| 3.0 | 06 Oct 11 | Berrini | Phase 3 | Proposal for funding under 1st allocation 2012 (OCG#45, Board#85) |
| 3.1 | 17 Feb 12 | Frank Ernst | Proposed revision | Editorials, clarifications, additional material introduced |
| 3.2 | 25 May 12 |  | OCG46/B88 | Streamlining text |
| 3.3 | 8 June 12 | Bilz ERM Chair |  | Updated to respond to the comments on the OCG reflector from Jean-Pierre Henninot and to remove ECC-TG4 since it has closed. |
| 3.4 | 6 Nov 12 | Berrini | Prep. Meet. |  |
| 3.5 | 4 Dec 12 | Berrini | Contracts | Updated milestone table (dates) |

# Footnotes

Programme Making includes the making of a programme for broadcast, the making of a film, presentation, advertisement or audio or video recordings, and the staging or performance of an entertainment, sporting or other public event.

A Special Eventis an occurrence of limited duration, typically between one day and a few weeks, which take place on specifically defined locations. Examples include large cultural, sport, entertainment, religious and other festivals, conferences and trade fairs. In the entertainment industry, theatrical productions may run for considerably longer.

ERC Report 038, “Handbook on radio equipment and systems video links for ENG/OB use” (01/04/2001).

ERC Report 042, “Handbook on radio equipment and systems radio microphones and simple wide band audio links” (01/04/2001)

See ETSI TR 102 546, “Electromagnetic compatibility and Radio spectrum Matters (ERM); Technical characteristics for Professional  Wireless Microphone Systems (PWMS); System Reference Document”.