|  | ToR STF 449 (TB ITS / WG1-WG3) |
| --- | --- |
|  | Version: 0.7 - Date: October 2010 |
|  | Author: TC ITS (A. Festag) |
|  | Last updated by: Alberto Berrini 10 July-2012 |
|  | page 1 of 10 |

Terms of Reference for Specialist Task Force STF 449 on

"Maintenance of Test Specifications for CAM, DENM, BTP, GeoNetworking and IPv6 over GeoNetworking"

Document status

| Current status of these ToR | Approved at ITS#9 27 – 28 October and Board#85 with slight budget reduction (voluntary = 20% of total) |
| --- | --- |
| Work Items approved | see §3.14 |

# Reasons for proposing the Specialist Task Force (STF)

STF405 has produced test specifications (PICS, TSS&TP, ATS) for the base specifications:

- CAM TS 102 637-2 V1.1.1

- DENM TS 102 637-3 V1.1.1

- BTP TS 102 636-5-1 V0.0.6

- GeoNetworking TS 102 636-4-1 V0.0.8

- GeoNetworking TS 102 636-4-2 V0.0.5

- IP over GeoNetworking TS 102 636-6-1 V0.0.8

During ITS#7, discussions on the base specification release plan showed that for 2011 new revisions of base specifications will be delivered containing new important features. Furthermore multiple activities are foreseen for 2011/2012 such as

- Field Operational Tests of the various ITS EC projects are considered to produce an important amount of CRs to the base specifications.

- EC funded STF405 on “Platform for Conformance Testing of Co-operative Awareness Messages (CAM), Decentralized environmental Notification Messages (DENM) and GeoNetworking” is considered to produce CRs to the base specifications.

- International harmonization in particular with regard to other existing messages systems, e.g. with SAE J2735.

- Development of road safety application specifications may require the evolution of CAM & DENM base standards.

The scope of STF405 was to produce test specifications for and to validate base specifications developed in 2010. This allowed having stable base specifications as input to the 2011 activities. To cover for the new activities described above this maintenance STF is proposed.

## Overview of the proposal

### Purpose of the work

The purpose of the work is to assure interoperability of devices produced in compliance with the ITS base specifications on CAM, DENM, BTP, GeoNetworking and IPv6 over GeoNetworking. This particular work is to maintain the test specifications with regard to new features and CRs being introduced in the base specifications.

### Relation with the ETSI Strategic Objectives

This STF will address the interoperability issues related to an new technology where conformance testing has not yet been performed and potential interoperability issues may arise

### Market impact, benefits to be gained

The availability of good test specifications may positively affect the arrival of products in the market place and their level of protocol conformance and interoperability.

### Interest of ETSI Members and other stakeholders

The work is supported by ITS member companies, in particular:

- DAIMLER

- HITACHI EUROPE

- INRIA

- NEC EUROPE

- RENAULT

- VOLKSWAGEN

### Relation with other activities within ETSI and/or related organizations

The STF will only be interacting with the responsible TB, i.e. ITS, ITS WG1 and ITS WG3.

### Priority within the TB

High

### Motivation why an STF is needed

Experience with the development of other standards has shown that involvement of experts on conformance and interoperability testing of protocols requires highly specialised knowledge in testing methodology. The generation of this kind of specifications requires significant concentrated effort that can be done in this case by experts provided on a funded basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the Test Specifications. The experts will use dedicated software tools available at ETSI.

### Active support from ETSI Members

Members are prepared to support and review of the STF deliverables.

## Organization of the work

### Identification of tasks, phases, priorities, technical risk

There shall be the tasks of

- Update of PICS and TP documents

- Update of TTCN test suites (ATS)

- Management of STF and Liaison to TC ITS

The tasks shall be performed throughout the year 2012, whereby the team should work at least 1 week per month in order to assure a timely update of test specifications and to provide feedback on new features of base specifications.

### Outcome of the STF

To produce revisions of CAM, DENM, BTP, GeoNetworking and IPv6 over GeoNetworking test specification.

# Consequences if not agreed:

The production of test specifications as described in the present document is key to the testing and potential certification activities that should assure the interoperability of ITS equipment. Such devices are required to have high levels of interoperability if the safety on road is to be kept at the highest level. The non-availability of such standards may cause problems of interoperability.

# Detailed description:

## Subject title:

Maintenance of test specifications for CAM, DENM, BTP, GeoNetworking and IPv6 over Geonetworking.

## Reference Technical Body:

TC ITS and in particular WG1 and WG3 will be responsible for the approval of all the deliverables of this STF.

## Other interested TBs (if any):

N/A

## Steering Committee

TC ITS will monitor the progress through the WG1 and WG3 chairmen, and no steering committee is planned.

## Target date for the start of work:

It is planned to start the STF in 1st quarter of 2012.

## Duration and target date for the conclusion of the work (TB approval):

The duration of the work is planned to be up to 12 months. The target is that the STF completes the work by the end of fourth quarter of 2012.

## Resources required

Two or three experts would be required. In addition support from CTI is required.

### Experts manpower

Expert manpower resources required: 110 working days for drafting deliverables of which 22 working days will be voluntary contribution.

In addition CTI resource is required: 25 working days for support on drafting deliverables, funded from the ETSI STF budget of which 5 working days will be voluntary contribution.

The total manpower budget is for 108 working days (88 from experts and 20 from CTI), remunerated at 600 €/day = 64 800 €.

### Travel cost

Travel to 4 TC ITS meetings for 1 person will require additional travel cost of 3 200 EUR.

If all of the ITS meetings will take place at ETSI then no travel cost are required.

### Other cost:

No additional direct cost is requested to be funded by ETSI.

### Estimated cost of Members’ contribution

Voluntary resource from members performing review of the deliverables (drafts for review or approval in the TB), on the basis on a number days, is estimated as at least 60 man days. This represents an estimated equivalent of 36 000 Euro.

## Experts qualification required, mix of skills

- In-depth knowledge of the test specification series CAM, DENM, BTP, GeoNetworking and IPv6 over GeoNetworking,

- Expertise in protocol and conformance test specification, software to produce test suites,

- Expertise in communication systems and network protocols, in particular ad hoc routing and Internet protocols (IPv6),

- Knowledge of radio co-operative systems and ITS station reference model,

- Knowledge of road safety applications supported by road co-operative systems,

- Expertise in the 5.9 GHz physical layer and Medium Access Control layer,

- Knowledge of CAM and DENM use and specifications,

- Expertise in test strategy, test systems, conformance testing specifications,

- Expertise in TTCN-3 language development and validation,

- Standardisation.

## Scope of Terms of Reference:

The scope of the work is to maintain the test specification series CAM, DENM, BTP, GeoNetworking and IPv6 over GeoNetworking with regard to new features and CRs in the base specifications.

## Organization of the work in tasks and/or phases:

The work will be done in a single phase.

## Validation

This STF will work closely with the EC sponsored STF424 on “Platform for Conformance Testing of Co-operative Awareness Messages (CAM), Decentralized environmental Notification Messages (DENM) and GeoNetworking”. Task 12 of STF424 will generate Change Requests (CRs) for any errors found in the related input documents such as PICS, Test Purposes or TTCN-3 code. Furthermore any error found in the related base specifications will be recorded as well. A list of the CRs will be made available and included in the project reporting. This STF will implement the CRs.

## Related activity in other bodies and co-ordination of schedules:

The STF will be interacting with the responsible TB, i.e., TC ITS WG1 and WG3 working group.

## Base documents and their availability

The STF work will be based upon the following base specifications:

| Work Item | Title | Current Status |
| --- | --- | --- |
| DTS/ITS-0030002 | Vehicular Communications; Part 1: Requirements for GeoNetworking and Data Transport Protocol | Under revision |
| DTS/ITS-0030004 | Vehicular Communications; Part 3: Network architecture | Under revision |
| DTS/ITS-0030001 | Intelligent Transportation System (ITS); Vehicular communications; Part 4: Geographical addressing and forwarding for point-to-point and point-to-multipoint communications; Subpart 1: Media independent functionalities | Under revision |
| DTS/ITS-0030007 | Vehicular Communications; Part 4: Geographical addressing and forwarding for point-to-point and point-to-multipoint communications; Subpart 2: Media dependent functionalities for 5 GHz media (5,9 GHz) | Draft available |
| DTS/ITS-0030006 | Vehicular Communications; Part 5: Transport Protocols; Subpart 1: Basic Transport Protocol for GeoNetworking | Published |
| DTS/ITS-0030005 | Vehicular Communications; Part 6: Internet Integration; Subpart 1: Integration of IPv6 and GeoNetworking | Under revision |
| DEG/ITS-0020022 | Framework for testing in ITS | Published |
| ETSI TS 102 637-1 | Vehicular Communications; BSA functional requirements | Published |
| ETSI TS 102 637-2 | Vehicular Communications; BSA; Co-operative Awareness Message specification | Under revision |
| ETSI TS 102 637-3 | Vehicular Communications; BSA; Specification of Decentralised environmental Notification Message | Revision stable |

The STF work will be based upon the following test specifications:

| Work Item | TS Number | Title | Current Status |
| --- | --- | --- | --- |
| DTS/ITS-0030014 | TS 102 871-1 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma | Published |
| DTS/ITS-0030015 | TS 102 871-2 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 2: Test Suite Structure and Test Purposes (TSS&TP) | Published |
| DTS/ITS-0030013 | TS 102 871-3 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) | Published |
| DTS/ITS-0030011 | TS 102 870-1 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking Basic Transport Protocol (BTP); Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma | Published |
| DTS/ITS-0030012 | TS 102 870-2 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking Basic Transport Protocol (BTP); Part 2: Test Suite Structure and Test Purposes (TSS&TP) | Published |
| DTS/ITS-0030010 | TS 102 870-3 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking Basic Transport Protocol (BTP); Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT); | Published |
| DTS/ITS-0030017 | TS 102 859-1 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Transmission of IP packets over Geonetworking; Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma | Published |
| DTS/ITS-0030009 | TS 102 859-2 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Transmission of IP packets over Geonetworking; Part 2: Test Suite Structure and Test Purposes (TSS&TP) | Published |
| DTS/ITS-0030016 | TS 102 859-3 | Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Transmission of IP packets over Geonetworking; Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT); | Published |
| DTS/ITS-0010007-1 | TS 102 868-1 | Intelligent Transport System (ITS); Testing; Conformance test specification for Co-operative Awareness Messages (CAM); - Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma | Published |
| DTS/ITS-0010007-2 | TS 102 868-2 | Intelligent Transport System (ITS); Testing; Conformance test specification for Co-operative Awareness Messages (CAM); - Part 2: Test Suite Structure and Test Purposes (TSS&TP). | Published |
| DTS/ITS-0010007-3 | TS 102 868-3 | Intelligent Transport System (ITS); Testing; Conformance test specification for Co-operative Awareness Messages (CAM); - Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) | Published |
| DTS/ITS-0010008-1 | TS 102 869-1 | Intelligent Transport System (ITS); Testing; Conformance test specification for Decentralized environmental Notification Messages (DENM); - Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma. | Published |
| DTS/ITS-0010008-2 | TS 102 869-2 | Intelligent Transport System (ITS); Testing; Conformance test specification for Decentralized environmental Notification Messages (DENM); - Part 2: Test Suite Structure and Test Purposes (TSS&TP); | Published |
| DTS/ITS-0010008-3 | TS 102 869-3 | Intelligent Transport System (ITS); Testing; Conformance test specification for Decentralized environmental Notification Messages (DENM); - Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT). | Published |

## Work Items from the ETSI Work Programme (EWP) for which the STF is required:

The STF will produce the following deliverables, for TB approval:

| Work Item | TS Number | Title |
| --- | --- | --- |
| RTS/ITS-0030022 | TS 102 871-1 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma |
| RTS/ITS-0030023 | TS 102 871-2 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 2: Test Suite Structure and Test Purposes (TSS&TP) |
| RTS/ITS-0030024 | TS 102 871-3 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) |
| RTS/ITS-0030028 | TS 102 870-3 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking Basic Transport Protocol (BTP); Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT); |
| RTS/ITS-0030029 | TS 102 859-1 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Transmission of IP packets over Geonetworking (GN6); Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma |
| RTS/ITS-0030030 | TS 102 859-2 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Transmission of IP packets over Geonetworking (GN6). Part 2: Test Suite Structure and Test Purposes (TSS&TP) |
| RTS/ITS-0030026 | TS 102 859-3 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Transmission of IP packets over Geonetworking (GN6); Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT); |
| RTS/ITS-001XXXX | TS 102 868-1 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification for Co-operative Awareness Messages (CAM); - ); Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma |
| RTS/ITS-0010026 | TS 102 868-2 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification for Co-operative Awareness Messages (CAM); - Part 2: Test Suite Structure and Test Purposes (TSS&TP). |
| RTS/ITS-0010027 | TS 102 868-3 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification for Co-operative Awareness Messages (CAM); - Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) |
| RTS/ITS-001XXXX | TS 102 869-1 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification for Decentralized environmental Notification Messages (DENM); - Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) proforma. |
| RTS/ITS-0010028 | TS 102 869-2 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification for Decentralized environmental Notification Messages (DENM); - Part 2: Test Suite Structure and Test Purposes (TSS&TP); |
| RTS/ITS-0010029 | TS 102 869-3 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification for Decentralized environmental Notification Messages (DENM); - Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT). |

## Planned output schedule:

The STF will produce the deliverables according to the following time scale (all Work Items):

- Start of the work 	20 August 2012

- First stable draft for WG review

- Stable draft for WGreview

- Draft for WG1 and 3 approval

- Draft for TB approval

- TB approval	August 2013 (depending on base stds availability)

- Publication

# Performance indicators

- Contribution from the ETSI Members

  - Voluntary work of experts provided free of charge in form of CRs being provided and CR resolutions being reviewed

- Interest from stakeholders other than ETSI Members

  - Number of Change Requests

  - Liaison activities performed by the STF (e.g. workshops/Plugtests/conferences/events)

- Quality of deliverables

  - Approval of deliverables from the Reference TB according to schedule

  - Respect of time scale, with reference to start/end dates in the approved ToR

  - Application of the ETSI drafting rules

# Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 |  | TC ITS | draft |  |
| 0.2 | 12.10.2010 | G. Segarra | Draft | Added supporting members |
| 0.3 | 12.10.2010 | A. Festag | Draft | Added supporting members; minor corrections |
| 0.4 | 12.10.2010 | G.Segarra | Draft | Added rationale for this STF, correction of minor errors. |
| 0.5 | 29.11.2011 | TC ITS | Draft | Revision for re-submission |
| 0.6 | 10-Oct-2011 | Berrini |  | Revised voluntary contribution (20%) + WI codes |
| 0.7 | 10-Jul-2012 | Berrini | Prep. Meet. | Deliverable list, time scale. |