|  | ToR STF 464 (TC DECT / WG ULE) |
| --- | --- |
|  | Version: 0.4 |
|  | Author: Dr. Günter Kleindl – Date: 25 Apr 2013 |
|  | Last updated by: Alberto Berrini – Date: 24 July 2013 |
|  | page 1 of 7 |

Terms of Reference - Specialist Task Force

STF 464 (TC DECT / WG ULE)

ULE Test Specification

Summary information

| Approval status | Approved by TC DECT#57 (18-20 June) Approved by Board#93 (6-7 June 2013) |
| --- | --- |
| Funding | 40 400 €, voluntary contribution 20% of total manpower |
| Time scale | 12 August 2013 to Jan 2014 |
| Work Items | DTS/DECT-ULE269-1 |
| Board priority category B(12)88_030 | Standards enablers/facilitators (e.g. conformance test/interoperability/methodology) Recommendations: use of TTCN and CTI supervision, require average 20% voluntary contribution from Companies sending experts. |
| Note from Secretariat | Required to resolve interoperability problems with different implementations of ULE standards. Strong support from TC DECT Members (Operators and Manufacturers). Specific DECT testing methodology will be used. Managed directly by TC DECT (CTI not involved). Test cases coverage and resources required have been assessed by TC DECT. |

Part I – Reason for proposing the STF

# Rationale

The DECT manufacturers are starting to implement the ‘ULE’ features as defined in the Technical Specification ‘DECT ULE phase 1’. Unfortunately, with different interpretations of the specification, these implementations may differ slightly and could present some challenges with full interoperability are therefore not interoperable. With the creation of a test specification and the subsequent implementation of a tester, the interoperability could be guaranteed. This would then lead to higher user satisfaction and more success on the market.

# Objective

The objective is the production of a test specification for the Technical Specification TS 102 939-1 DECT ULE, machine to machine communications, phase 1, during the second half of 2013.

# Relation with ETSI strategy and priorities

ETSI Long Term Strategy item to which the STF may contribute:

Create high quality standards for global use and with low time-to-market.

Priority category for this request [BOARD(12)88_030r1]

Standards enablers/facilitators (conformance testing, interoperability, methodology)

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| AVM | Mathias Frey Sven Trevisany | Since Standards allow for slightly different interpretations, a test specification is needed to ensure interoperability of the implemented products. This STF would considerably shorten creation time of the test specification and consequently, time to market. |
| DSPG | Jochen Kilian | Ensure interoperability of the standard to allow wide market penetration with a standardized solution. |
| FEEI | Günter Kleindl | To improve the interoperability of products. |
| Gigaset Communications | Dieter Kehren, Andreas Müller | Our motivation for supporting this STF request is to ensure interoperability between implementations from different manufacturers by creating a dedicated test specification in a shorter time frame |
| RTX TELECOM | Jens T. Petersen | To enable a faster introduction of new applications and products in new markets and to ensure interoperability of these. |

## Market impact

With over 820 million devices installed throughout the world, ETSI’s DECT specification is the leading standard worldwide for digital cordless telecommunications for both cordless voice and broadband home communication. The system has been adopted in over 110 countries and every year more than 100 million new devices are sold. DECT products now account for more than 80% of the world market. In the near future many devices will support the software update function and it is important to have interoperability for this feature.

## Tasks that cannot be done within the TB and for which the STF support is necessary

For the production of test specifications very specific knowledge is necessary which is generally not available inside the TB.

## Related voluntary activities in the TB

The TB will assist in the selection of the test cases, review the tests and provide feedback to the STF.

## Outcome from previous funded activities in the same domain

The following three STFs have worked on DECT ULE:

ETSI Resources:

|  | Work days | Cost in EUR |
| --- | --- | --- |
| STF 419 | 60 | 36 000 |
| STF 441 | 167 | 102 000 |
| STF 444 | 15 | 9 000 |
| Total | 242 | 147 000 |

## Consequences if not agreed

A timely production of the test specification will not be possible and a market opportunity will be lost.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TC DECT, Chairman: Dr. Günter Kleindl

DECT ULE Working Group, Chairman: Jens T. Petersen

## Other interested ETSI Technical Bodies

TC ERM, TC M2M, oneM2M

## Other interested Organizations outside ETSI

DECT Forum, ULE Alliance

# Working method/approach

## Organization of the work

The work will be steered by the TC DECT Chairman, the ULE WG chairman and the ULE WG There will be at least three TC DECT / WG NG meetings from June to December 2013.

## Base documents

| Document | Title | Current Status |
| --- | --- | --- |
| ETSI TS 102 939-1 | Digital Enhanced Cordless Telecommunications (DECT); Ultra Low Energy (ULE);Machine to Machine Communications; Part 1: Home Automation Network (phase 1) | Published |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | DTS/DECT-ULE269-1 | Digital Enhanced Cordless Telecommunications (DECT); Ultra Low Energy (ULE); Machine to Machine Communications; Part 1: Test Case Library for Home Automation Network (phase 1) test specifications for ULE phase 1 |

## Deliverables schedule:

DTS/ DECT-NG270	Working title

Start of work	12-Augl-2013

Early draft	10-Sep-2013 	DECT#58

Stable draft	30-Oct-2013

TB approval	20-Dec-2013	DECT#59

Publication	31-Jan-2014

## Work plan, time scale and resources

| N | Task / Milestone / Deliverable | From | To | Funded experts (days) | Volunt. experts (days) |
| --- | --- | --- | --- | --- | --- |
| M0 | Start of work | 31.07.2013 |  |  |
| T0 | Project management | 31.07.2013 | 20.12.2014 | 2 |  |
| T1 | Develop draft test cases | 31.07.2013 | 10.09.2013 | 20 | 6 |
| M1 | Draft for WG review (TB#58) | 10.09.2013 |  |  |
| T2 | Task 2: Complete test cases | 11.09.2013 | 30.10.2013 | 20 | 5 |
| M2 | Stable draft for TB review | 30.10.2013 |  |  |
| T3 | Task 3: Finalise all test cases | 11.11.2013 | 17.12.2013 | 20 | 5 |
| M3 | Final draft for TB approval | 17.12.2013 |  |  |
| M4 | TB approval (TB#59) | 20.12.2013 | 1 |  |
| M5 | STF Final Report | 24.01.2014 | 1 |  |
| M6 | Publication | 31.01.2014 |  |  |
| Total | 64 | 16 |

## Task and milestone description

Task 1 – Develop draft test cases

Propose structure of the test specification. Create high level description of test cases. Start writing the detailed test cases.

Milestone 1 – Draft for WG review

First draft of the test specification with high level description of all test cases and detailed implementation of some test cases is available.

Task 2 – Complete test cases

Update the draft test specification according to the comments received from the TB and produce final specification for TB approval.

Milestone 2 - Stable draft for TB review

Stable draft with all test cases is available for TB review.

Task 3 – Finalise all test cases

Integrate the comments from the TB, finalise all test cases and produce final version for TB approval.

Milestone 3 - Final draft for TB approval

Final draft with all test cases is available for TB approval.

# Required expertise

Up to two experts with the following skills:

Knowledge of DECT protocol, especially the ULE functions

Experience in writing test specifications

Part III:	Financial conditions

# Estimated cost

## Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 64 | 600 | 38 400 |
| Contracted experts (voluntary) | 16 |  |  |
| CTI staff from ETSI budget | 0 |  |  |
| CTI staff (voluntary) | 0 |  |  |
| Total manpower cost | 80 | 600 | 38 400 |

## Travel Costs

| Description | Cost estimate |
| --- | --- |
| TC DECT Plenary, Sophia Antipolis, 10.-12.09.2013 | 1 000 |
| TC DECT Plenary, Paris, 17.-19.12.2013 | 1 000 |
| Total cost | 2 000 |

## Other Costs

none

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from ETSI Members to STF work

Number of delegates attending meetings attending DECT and WG DECT-ULE meetings

Number of documents/contributions from TC delegates, in addition to STF work

Contribution from STF experts to ETSI work

Contributions presented to TB/WG meetings (number, type, comments received)

Liaison with other stakeholders

Stakeholder participation in the project (category, business area)

Cooperation with other standardization bodies

Potential interest of new members to join ETSI

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Quality review by TB

Quality review by ETSI Secretariat

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.0 | 29-Apr-2013 | Dr. Günter Kleindl | First draft | Sent out for comments |
| 0.1 | 13-May-2013 | Dr. Günter Kleindl | Draft for approval | AbC |
| 0.2 | 14-May-2013 | Dr. Günter Kleindl | AbC | Update due to received comments |
| 0.3 | 14-May-2013 | Dr. Günter Kleindl |  |  |
| 0.4 | 24-Jul-2013 | Berrini | Prep. Meet. | Start date |