|  | ToR STF AE (TC INT) |
| --- | --- |
|  | Version: 0.3 - Date: 12 May 2015, 2015 |
|  | Author: TC INT |
|  | Last updated by: Giulio Maggiore – Date 12 May 2015 |
|  | page 1 of 10 |

Terms of Reference for Specialist Task Force STF AE (TC INT) 
“Validation of the Conformance Test Specifications for the Diameter Protocol over the Cx and Dx reference points”

Document status

| Current status ToR | Approved by Board#103) |
| --- | --- |
| Funding required | Full budget allocated (39 000 €) Contracted experts: 75 working days, including voluntary contribution (20% of total). Manpower cost: 60 days @ 600 €/day = 36 000 € + 15 days free of charge Travel cost up to 3 000 €. |
| Work items | RTS/INT-00128-1 (revised version of DTS/INT-00103-1) Diameter Conformance testing for Cx and Dx interfaces Part 1: Protocol Implementation Conformance Statement (PICS) RTS/INT-00128-2 (revised version of DTS/INT-00103-2) Diameter Conformance testing for Cx and Dx interfaces Part 2: Test Suite Structure (TSS) and Test Purposes (TP) RTS/INT-00128-3 (revised version of DTS/INT-00103-3) Diameter Conformance testing for Cx and Dx interfaces Part 3: Abstract Test Suite (ATS) and partial Protocol Implementation eXtra Information for Testing (PIXIT) proforma specification |

Part I – Reason for proposing the STF

# Rationale

The Diameter protocol was initially developed to provide an Authentication, Authorization, and Accounting (AAA) framework that could overcome the limitations of RADIUS. RADIUS had issues with reliability, scalability, security and flexibility. The Diameter protocol defines a policy protocol used by clients to perform Policy, AAA and Resource Control. Diameter is one of the major protocols within the context of LTE network and is essential to guarantee reliable user authentication, policy management and charging procedures.

Interrogating Call Session Control Functions (I-CSCF) and Serving Call Session Control Functions (S-CSCF) within the IMS core network are in charge of handling the signalling of all call session related message exchanges of User Equipment (UE) connecting through the IMS. The IMS core is also responsible for authenticating the user in conjunction with the Home Subscriber Server (HSS). It downloads user profiles and uploads user-to-CSCF associations which are only cached locally for processing reasons. The HSS is a network database that holds both static and dynamic data elements related to subscribers. The HSS provides subscriber profile information to the CSCF on demand. The Cx interface that enables transfer of subscriber profile data for authenticating/authorizing user access to the IMS network is located between the Call Session Control Functions (CSCF) and the Home Subscriber Server (HSS).

In case an IMS core is located within a multi-HSS environment there is the need to find the correct HSS for any connecting user. This is done via the Service Locator Function (SLF). The Dx interface enables the CSCF to determine the correct HSS and is located between the Call Session Control Functions (CSCF) and the Service Locator Function (SLF).

The protocol used on the two above interfaces is the Diameter protocol as defined in RFC3588 and profiled for the Cx and Dx interfaces in ETSI TS 129 228 and ETSI TS 129 229.

In the following figure the location of the named entities and interfaces are highlighted.

Figure 1: IMS logical architecture

Given that there are already a test specifications related to the Diameter protocol profile for the Cx and Dx reference points under implementation, it seems reasonable to validate those test specifications.

Following the methodologies developed and used by ETSI, the validation is based on the Abstract Test Suite of the Cx and Dx Test Specifications, which have been approved at the INT#28 meeting (Sophia Antipolis, March 24-26, 2015).

Experience with the validation of other testing standards has shown that involvement of experts on conformance testing of protocols requires highly specialised knowledge in testing methodology, TTCN-3 language and dedicated tools. There is an advantage if testing experts are disjoint from experts developing the protocol specifications. In addition, the validation of this kind of specifications requires significant effort and it cannot be expected that this effort can be provided on a voluntary basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the test adaptors. These testing experts are not available on TC INT level and need to be recruited on a funded basis. The experts will use TTCN-3 platforms available at ETSI.

Past ETSI experience has shown that an STF, supported by the ETSI CTI, is the most effective and cost-efficient way to develop and validate test specifications.

# Objective

Recently major efforts have been made by LTE component providers to inter-connect complete networks, i.e. connecting the single components that comprise an LTE network of different operators to allow seamless roaming. This is mainly done via the Cx and the Dx interfaces. Experiences from those trials have shown that there are implementations of the Diameter protocol that have massive interconnection issues due to different interpretation of the protocol standards.

Given that the test specifications related to the Diameter protocol profile for the Rx, the Gx, the S6a and the S9 reference points have been validated by STF450 and STF482 against equipment of a significant number of vendors, it seems reasonable to extend the INT set of validated test specifications to also cover Diameter on the Cx and Dx reference point. Members of INT have already expressed the wish to provide access to equipment to validate against.

Experience with the validation of other testing standards has shown that involvement of experts on conformance testing of protocols requires highly specialised knowledge in testing methodology, TTCN-3 language and dedicated tools. There is an advantage if testing experts are disjoint from experts developing the protocol specifications. In addition, the validation of this kind of test specifications requires significant effort and it cannot be expected that this effort can be provided on a voluntary basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the Test Specifications. These testing experts are not available on TC INT level and need to be recruited on a funded basis. The experts will use dedicated software tools available at ETSI.

# Relation with ETSI strategy and priorities

This STF is directly related to ETSI strategic objective "Major Strategic Topics - NGN" and “Service level interconnection of IP-Based Services” and corresponds to the “Standards enablers/facilitators (conformance testing, interoperability, methodology)” category.

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Telecom Italia | Giulio Maggiore | Tests used to get detailed information from vendors about Interoperability Testing before coming to the market |
| Telekom Austria | Martin Brand | Tests needed for internal network testing |
| Deutsche Telekom | Gerhard Ott | Tests needed for internal network testing |
| AT&T | Dewayne Sennet | Tests used to promote conformance testing for Public Safety |
| Telekom Slovenjia | Matjaz.Bericic | Test used to promote interoperability among vendors |
| Cisco | Jesus Trujllo Gomez | Test will be used for quality enhancement of IMS&EPC products |
| ZTE | David Huo | Test will be used for quality enhancement of IMS&EPC products |
| Iskratel | Primož Kočar | Test will be used for quality enhancement of IMS&EPC products |
| Italtel | Diego Saiu | Test will be used for quality enhancement of IMS&EPC products |
| Arcatech | Terence A, Simpson | Provide test system for functional and performance test. |
| Codenomicon | Ari Takanen | Provide test system to test protocols |
| Confomiq | Stephan Schulz | Generation of tests for testing protocol |
| Testing Tech | Theofanis Vassiliou-Gioles | Provide the Test System for the test cases implementation and execution |
| Fokus | Axel Rennoch | Research Institute, advanced automated/standardized test solutions with TTCN-3 |
| Elvior | Andres Kull | Tool Provider, Provide the Test System for the test cases |
| Tektronix Communications | Kanthi, Prakash | Tool Provider, Provide the Test System for the test cases |
| Keynote Sigos | Shicheng Hu | Try to establish the synergy between the network conformance and the network e2e tests. Provide the Test System for the global roaming and the e2e QoS / QoE tests |
| BNetzA | Wolfgang Balzer | Provide and evolve tools based on end user devices (e.g. smartphones with respective apps)to create stimuli (scenarios where DIAMETER communication is invoked) for testing, and to interpret system responses from an end to end QoS perspective |
| Sintesio | Bostjan Pintar | The aim of the SINTESIO Foundation is to promote open standards, interoperability in multi-vendor/multi-operator environments, to develop open test suites and tools for conformance and interoperability, and to support standardization efforts and to facilitate vendors collaboration in the area of NGN telecommunication technologies and standardization. |

## Market impact

Public Safety Projects have become recently a major context where operators required full compliance of products against the base specification. National Organizations and Government are going towards a fully compliant VoLTE network with priorities management. Validation of Conformance Test Specifications allows not only to test early implementation but also to provide feedback to 3GPP in time to validate the standard before the mass market application.

The availability of reliable and validated test specifications will allow implementers of LTE components and protocol stacks (for HSS, SLF and CSCFs) to test the conformance of their products against the protocol specifications. Conformance testing during the whole development phase of all LTE products will significantly reduce the time-to-market of the LTE architecture, as protocol conformant products will be of an enhanced quality level and will hence be less likely to cause interoperability problems with the products of other vendors.

Protocol conformant products will therefore provide the network operators with the means to deliver fully LTE compliant services to their end customers in a continuously high quality, with reliable service functionality, without communication failures and generally with the optimum quality of service for the transported media.

The validated tests for the Cx and Dx interface will allow consequently allow faster connection of the LTE networks of different operators due to well tested and interoperable LTE entities that form the border of the adjacent networks and are responsible for the key functionalities policy, charging and authentication.

## Tasks that cannot be done within the TB and for which the STF support is necessary

LTE networks are currently being deployed in the telecoms industry. They must operate alongside and interwork correctly with the existing IMS networks already installed.

Consequently there is the need to allow seamless roaming functionalities between the networks of different operators.

Field trials showed massive interoperability problems related to Diameter implementations of different vendors. Therefore detailed Abstract Test Specifications are urgently required to complete the overall testing framework.

To complete the testing work, and to capitalise on the investment done during the field trials, the corresponding Abstract Test Suite is urgently needed.

The ETSI members do not have sufficient resources to create an Abstract Test Suite on time, and with the high quality that has been experienced with using STF resources for this purpose in the past.

It is essential that this work is done in a timely manner in order to synchronise with global testing activities, especially in the context of LTE.

## Related voluntary activities in the TB

The ETSI Members supporting the creation of the STF are committed to supporting this STF in terms of participation in the STF Steering Group, providing input and review to the STF, providing test bed structures and test tools.

## Outcome from previous funded activities in the same domain

STF480 Conformance Test Specifications for the Diameter Protocol over the Cx and the Dx reference points.  Resource: 80 remunerated and 20 voluntary effort days, 51 000€

## Consequences if not agreed

LTE networks are currently being deployed in telecoms networks during the progression towards fully LTE compliant network architectures. Thorough conformance testing will increase the level of confidence that equipment from various suppliers will interwork. This in turn will reduce implementation and rollout times. Not providing timely validated and reliable test specifications, would ultimately delay the deployment of LTE.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TC INT, Giulio Maggiore

## Other interested ETSI Technical Bodies

3GPP CT1

3GPP CT3

3GPP SA3

ETSI TC MTS

## Other interested Organizations outside ETSI

GSMA IREG

# Working method/approach

## Organization of the work

The work can be separated in 4 main tasks:

Task T0: Project Management, Reporting	  5 working days in total

Task T1: Codec and TA development	20 working days in total

Task T2: ATS Validation	50 working days in total

Task T3: TS update	  5 working days in total

## Base documents

| Document | Title | Current Status |
| --- | --- | --- |
| DTS/INT-00103-1 | Diameter Conformance testing for Cx and Dx interfaces; Part 1: PICS | Published |
| DTS/INT-00103-2 | Diameter Conformance testing for Cx and Dx interfaces; Part 2: TSS&TP | Approved for publication (June 2015) |
| DTS/INT-00103-3 | Diameter Conformance testing for Cx and Dx interfaces; Part 3: ATS&PIXIT | Approved for publication (June 2015) |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | RTS/INT-00128-1 | Diameter Conformance testing for Cx and Dx interfaces; Part 1: PICS |
| D2 | RTS/INT-00128-2 | Diameter Conformance testing for Cx and Dx interfaces; Part 2: TSS&TP |
| D3 | RTS/INT-00128-3 | Diameter Conformance testing for Cx and Dx interfaces; Part 3: ATS&PIXIT |

## Deliverables schedule:

Start of work	14-Sep-2015

ToC and scope	25-Sep-2015

Early validation results	Dec-2015	INT#31

Further validation results	Feb/Mar-2016	INT#32

Final validation results	May/Jun-2016	INT#33

Stable draft of all docs	May/Jun-2016	INT#33

TB approval	May/Jun-2016	INT#33

Publication	Jul-2016

## Work plan, time scale and resources

| N | Task / Milestone / Deliverable | Target date | Testing experts (days) | CTI contrib. (days) |
| --- | --- | --- | --- | --- |
| M0 | Start of work | Sep 2015 |  |
| T0 | Project management, reporting CTI supervision | Sep 2015 – Jun 2016 |  | 5 |
| T1 | Codec and TA development | Sep – Dec 2015 | 20 |  |
| M1 | First Progress Report (INT#31) | Dec 2015 |  |
| T2 | ATS Validation | Nov 2015 – May 2016 | 50 |  |
| M2 | Second Progress Report (INT#32) | March 2016 |  |
| T3 | TS Updates | Jan – May 2016 | 5 |  |
| M3 | Approval of all revised TS document, Final Progress Report (INT#33) | Jun 2016 |  |
| Total | 75 | 5 |

INT meetings

INT#31	Dec 2015	tbd	first report

INT#32	Mar 2016	tbd	second report

INT#33	May/Jun 2016	tbd	final drafts for approval

## Task and milestone description

Task T0: Project Management (CTI supervision)

Drafting non-published documents:	  2 working days in total

Attending Technical Body and WG meetings: 	  3 working days in total

Task T1: Codec and TA development		20 working days in total

ETSI TS 129 229 clause 5.4 states that the transport protocol Diameter messages over the Cx and the Dx interfaces shall make use of SCTP as defined in IETF RFC 4960. Therefore the Codec and TA shall support SCTP as transport protocol.

Note: The codec and TA software shall be delivered as source code including all source code modules needed for the compilation into an executable version of the software on the chosen test platform.

Task T2: ATS Validation		50 working days in total

Task T3: TS Update	  5 working days in total

Milestone 1 – First Report on Validation Activities

Approval of Progress Report by INT#31 (Dec 2015) plenary

Milestone 2 – Second Report on Validation Activities

Approval of Progress Report by INT#32 (Mar 2016) plenary

Milestone 3 –Approval of all revised documents, STF Final Report

Approval of final drafts of PICS, TSS&TP and ATS&PIXIT documents

Approval of Final Report by INT#33 (May/Jun 2016) plenary

The draft documents must be uploaded by the STF Leader on the TB contributions area of the ETSI Portal two weeks before INT#33.

# Required expertise

The following experts are required to perform the work. The actual number of experts and mix of skills may depend on the actual applications received and will be decided when setting up the STF.

Number of experts required: 2-3

Relevant expertise required:

Expert knowledge of DIAMETER protocols and LTE architecture

Expert knowledge in procedures on the Cx and Dx interfaces

Expert knowledge in validating DIAMETER test specification in TC INT

Expert knowledge in implementing Abstract Test Suites in TTCN-3

Awareness of outputs from earlier STFs on Diameter testing

Part III:	Financial conditions

# Estimated cost

## Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 60 | 600 | 36 000 |
| Contracted experts (voluntary) | 15 | 0 |  |
| Total manpower cost | 80 | - | 36 000 |

## Travel Costs

| Description | Cost estimate |
| --- | --- |
| INT#31, INT#32, INT#33 | 3 000 |
| Total cost | 3 000 |

## Other Costs

None

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Key performance indicators suitable for this kind of STF projects are the following:

Contribution from ETSI Members to STF work

Voluntary work of experts (free of charge or with partial remuneration)

Steering Group meetings (number of participants/duration)

Delegates attending meetings/events related to STF (number of participants/duration)

Direct contribution of delegates (e.g. number of documents/comments/e-mail)

Support to the STF work (e.g., provision of test–beds, organization of workshops, events)

Contributions/presentations to other ETSI TBs

Contributions received from other ETSI TBs

Contribution from STF experts to ETSI work

Contributions presented to TB/WG meetings (number, type, comments received)

Presentations in workshops, conferences, stakeholder meetings

Liaison with other stakeholders

Stakeholder participation in the project (category, business area)

Cooperation with other standardization bodies

Potential interest of new members to join ETSI

Liaison to identify requirements and raise awareness on ETSI deliverables

Comments received on drafts (e.g. on WEB site, mailing lists, etc.)

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Quality review by TB

Quality review by ETSI Secretariat

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

| Ver. | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 2015-03-26 | Giulio Maggiore | Draft | First draft |
| 0.2 | 2015-04-21 | Giulio Maggiore | Draft | Second draft, Mandated support of SCTP for task 1 (codec and TA) |
| 0.3 | 2015-05-12 | Berrini | OCG/Board consultation | Editorials |