|  | ToR STF AK (TC INT) |
| --- | --- |
|  | Version: 0.5 - Date: 27 January 2015 |
|  | Author: TC INT |
|  | Last updated by: Alberto Berrini |
|  | page 1 of 10 |

Part I – Reason for proposing the STF

# Rationale

Call Session Control Functions (CSCF) within the IMS core network are in charge of handling the signalling of all call session related message exchanges of User Equipment (UE) connecting through the IMS. Application Servers (AS) host and execute services, and can be located in the home network or in an external third-party network. Both the IMS core made up by its CSCFs and the Application Servers (AS) are relying on data related to the charging procedures. Offline charging information is provided by the Charging Trigger Function (CTF) nested in IMS core functions and in AS. Online charging information is provided by the CTF to the Online Charging Function (OCF) implemented in the Online Charging System (OCS) for AS, IMS Gateway Functions (IMS-GW) and Media Gateway Control Functions (MGCF).

The Rf Reference Point that enables transfer of offline charging information is located between the CTF of Call Session Control Functions (CSCF) or Application Servers (AS) and the Charging Data Function (CDF) which is usually co-located with the Charging Gateway Function (CGF) in the Charging Collection Function (CCF). The Ro Reference Point that enables transfer of online charging information is located between the CTF of Application Server (AS), IMS Gateway Function (IMS-GW) or Media Gateway Control Function (MGCF) and the Online Charging Function (OCF).

The Rf/Ro protocols used on the two above IMS ETSI TS 132 260 Rf/Ro Reference Points, are specified in ETSI TS 132 229, and rely on the Diameter protocol as defined in RFC3588.

The architecture for IMS offline charging is described in figure 1.

Figure 1: IMS offline charging architecture

The architecture for IMS online charging is described in figure 2.

Figure2: IMS online charging Architecture

Given that there are already test specifications related to the Diameter protocol profile for the Rf and Ro reference points under implementation, it seems reasonable to validate those test specifications.

Following the methodologies developed and used by ETSI, the validation is based on the three part Test Specification for the Rf and Ro interfaces, where part 1 (PICS) has already been approved at the INT#30 meeting (Vienna, September 7-10, 2015). Approval of parts 2 (TSS&TP) and part 3 (ATS&PIXIT) are planned for INT#31 (December 2015) and INT#32 (March 2016) respectively.

Experience with the validation of other testing standards has shown that involvement of experts on conformance testing of protocols requires highly specialised knowledge in testing methodology, TTCN-3 language and dedicated tools. There is an advantage if testing experts are disjoint from experts developing the protocol specifications. In addition, the validation of this kind of specifications requires significant effort and it cannot be expected that this effort can be provided on a voluntary basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the test adaptors. These testing experts are not available on TC INT level and need to be recruited on a funded basis. The experts will use TTCN-3 platforms available at ETSI.

Past ETSI experience has shown that an STF, supported by the ETSI CTI, is the most effective and cost-efficient way to develop and validate test specifications.

# Objective

Recently major efforts have been made by VoLTE component providers to inter-connect complete networks, i.e. connecting the single components that comprise an VOLTE network of different operators to allow seamless roaming for end customers and complete and reliable functionality for network providers. Billing is the most important topic for network operators as the revenue generated through traffic on their networks is the main income factor for them.

Given that all the test specifications related to the Diameter protocol profiles developed so far (for Rx, Gx, S6a, S9, Cx and Dx reference points) have been validated by STF450, STF482 and STF500 against equipment of a significant number of vendors, it seems reasonable to extend the INT set of validated test specifications to also cover Diameter on the IMS Rf and Ro reference points. Members of INT have already expressed the wish to provide access to equipment to validate against.

Experience with the validation of other testing standards has shown that involvement of experts on conformance testing of protocols requires highly specialised knowledge in testing methodology, TTCN-3 language and dedicated tools. There is an advantage if testing experts are disjoint from experts developing the protocol specifications. In addition, the validation of this kind of test specifications requires significant effort and it cannot be expected that this effort can be provided on a voluntary basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the Test Specifications. These testing experts are not available on TC INT level and need to be recruited on a funded basis. The experts will use dedicated software tools available at ETSI.

# Relation with ETSI strategy and priorities

This STF is directly related to ETSI strategic objective "Major Strategic Topics - NGN" and “Service level interconnection of IP-Based Services” and corresponds to the “Standards enablers/facilitators (conformance testing, interoperability, methodology)” category.

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Telecom Italia | Giulio Maggiore | Tests used to get detailed information from vendors about Interoperability Testing before coming to the market |
| Telekom Austria | Martin Brand | Tests needed for internal network testing |
| Deutsche Telekom | Gerhard Ott | Tests needed for internal network testing |
| AT&T | Dewayne Sennet | Tests used to promote conformance testing for Public Safety |
| Telekom Slovenjia | Matjaz.Bericic | Test used to promote interoperability among vendors |
| Cisco | Jesus Trujllo Gomez | Test will be used for quality enhancement of IMS&EPC products |
| ZTE | David Huo | Test will be used for quality enhancement of IMS&EPC products |
| Iskratel | Primož Kočar | Test will be used for quality enhancement of IMS&EPC products |
| Italtel | Diego Saiu | Test will be used for quality enhancement of IMS&EPC products |
| Arcatech | Terence A, Simpson | Provide test system for functional and performance test. |
| Codenomicon | Ari Takanen | Provide test system to test protocols |
| Confomiq | Stephan Schulz | Generation of tests for testing protocol |
| Testing Tech | Theofanis Vassiliou-Gioles | Provide the Test System for the test cases implementation and execution |
| Fokus | Axel Rennoch | Research Institute, advanced automated/standardized test solutions with TTCN-3 |
| Elvior | Andres Kull | Tool Provider, Provide the Test System for the test cases |
| Tektronix Communications | Gruyer, Martial | Tool Provider, Provide the Test System for the test cases |
| Keynote Sigos | Shicheng Hu | Try to establish the synergy between the network conformance and the network e2e tests. Provide the Test System for the global roaming and the e2e QoS / QoE tests |
| BNetzA | Wolfgang Balzer | Provide and evolve tools based on end user devices (e.g. smartphones with respective apps)to create stimuli (scenarios where DIAMETER communication is invoked) for testing, and to interpret system responses from an end to end QoS perspective |
| Sintesio | Bostjan Pintar | The aim of the SINTESIO Foundation is to promote open standards, interoperability in multi-vendor/multi-operator environments, to develop open test suites and tools for conformance and interoperability, and to support standardization efforts and to facilitate vendors collaboration in the area of NGN telecommunication technologies and standardization. |

## Market impact

Public Safety Projects have become recently a major context where operators required full compliance of products against the base specification. National Organizations and Government are going towards a fully compliant VoLTE network with priorities management. Billing is one of the key elements in that context. Validation of Conformance Test Specifications allows not only to test early implementation but also to provide feedback to 3GPP in time to validate the standard before the mass market application.

The availability of reliable and validated test specifications will allow implementers of both VoLTE components (AS, x-CSCFs, IBCF, etc.) and online and offline charging functions (CDF and CGF combined in a CCF and OCS) to test the conformance of their products against the protocol specifications. Conformance testing during the whole development phase of all VoLTE products will significantly reduce the time-to-market of the VoLTE architecture, as protocol conformant products will be of an enhanced quality level and will hence be less likely to cause interoperability problems with the products of other vendors.

Protocol conformant products will therefore provide the network operators with reliable billing solutions that help to ensure their monetary benefit and to provide fair and transparent charging information to their end customers with reliable accounting detail and generally with an optimum quality.

The validated tests for the Rf and Ro interface will consequently allow faster connection of the VoLTE networks and billing components of different vendors and/or operators due to well tested and interoperable entities that are responsible for one of the key functionalities, accounting, charging and billing.

## Tasks that cannot be done within the TB and for which the STF support is necessary

- VoLTE networks are currently being deployed in the telecoms industry. They must operate alongside and interwork correctly with the existing IMS networks already installed.

- Consequently there is the need to allow seamless roaming functionalities between the networks of different operators.

- Field trials showed massive interoperability problems related to Diameter implementations of different vendors. Therefore detailed Abstract Test Specifications are urgently required to complete the overall testing framework.

- To complete the testing work, and to capitalise on the investment done during the field trials, the corresponding Abstract Test Suite is urgently needed.

- The ETSI members do not have sufficient resources to create an Abstract Test Suite on time, and with the high quality that has been experienced with using STF resources for this purpose in the past.

- It is essential that this work is done in a timely manner in order to synchronise with global testing activities, especially in the context of VoLTE.

## Related voluntary activities in the TB

The ETSI Members supporting the creation of the STF are committed to supporting this STF in terms of participation in the STF Steering Group, providing input and review to the STF, providing test bed structures and test tools.

## Outcome from previous funded activities in the same domain

STF490 Conformance Test Specifications for the Diameter Protocol over the Rf and the Ro reference points. Resource: 160 remunerated and 40 voluntary effort days, 99 000€

## Consequences if not agreed

VoLTE networks are currently being deployed in telecoms networks during the progression towards fully VoLTE compliant network architectures. Thorough conformance testing will increase the level of confidence that equipment from various suppliers will interwork. This in turn will reduce implementation and rollout times. Not providing timely validated and reliable test specifications, would ultimately delay the deployment of VoLTE.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TC INT, Giulio Maggiore

## Other interested ETSI Technical Bodies

- 3GPP CT1

- 3GPP CT3

- 3GPP SA5

- ETSI TC MTS

## Other interested Organizations outside ETSI

- GSMA IREG

# Working method/approach

## Organization of the work

The work can be separated in 4 main tasks:

- Task T0: Project Management, Reporting

- Task T1: Codec and TA development

- Task T2: ATS Validation

- Task T3: TS update

## Base documents

| Document | Title | Current Status |
| --- | --- | --- |
| DTS/INT-00121-1 | Diameter Conformance testing for Rf and Ro interfaces; Part 1: PICS | Approved for publication in September 2015 |
| DTS/INT-00121-2 | Diameter Conformance testing for Rf and Ro interfaces; Part 2: TSS&TP | Approval in December 2015 |
| DTS/INT-00121-3 | Diameter Conformance testing for Rf and Ro interfaces; Part 3: ATS&PIXIT | Approval in March 2016 |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | RTS/INT-00131-1 | Diameter Conformance testing for Rf and Ro interfaces; Part 1: PICS RTS/INT-00131-1 (TS 103 374-1) |
| D2 | RTS/INT-00131-2 | Diameter Conformance testing for Rf and Ro interfaces; Part 2: TSS&TP RTS/INT-00131-2 (TS 103 374-2) |
| D3 | RTS/INT-00131-3 | Diameter Conformance testing for Rf and Ro interfaces; Part 3: ATS&PIXIT RTS/INT-00131-3 (TS 103 374-3) |

## Deliverables schedule:

- Start of work	01-Mar-2016 *

- Codec and TA available	15-Apr-2016 *

- Early validation results	Jun-2016	INT#33

- Further validation results	Sep-2016	INT#34

- Final validation results	Dec-2016	INT#35

- Stable draft of all docs	Dec-2016	INT#35

- TB approval	Dec-2016	INT#35

- Publication	Jan-2017

* The Codec and TA development can begin before the approval of TS103 374-3, as the relevant information will be available through TS103 374-2 which will be available as of December 2015.

## Work plan, time scale and resources

| N | Task / Milestone / Deliverable | Target date |
| --- | --- | --- |
| M0 | Start of work | Mar 2016 |
| T0 | Project management, reporting, meeting attendance, CTI supervision | Mar 2016 – Dec 2016 |
| T1 | Codec and TA development | Mar – Apr 2016 |
| M1 | First Progress Report (INT#33) | Jun 2016 |
| T2 | ATS Validation | Apr – Dec 2016 |
| M2 | Second Progress Report (INT#34) | Sep 2016 |
| T3 | TS Updates | Sep – Dec 2016 |
| M3 | Approval of all revised TS document, Final Progress Report (INT#35) | Dec 2016 |
| Total |

INT meetings

INT#33	Jun 14-16, 2016	Vienna	first report

INT#34	Sep 6-8, 2016	Rome	second report

INT#35	Dec 13-15, 2016	ETSI	final drafts for approval

## Task and milestone description

Task T0: Project Management

- Drafting non-published documents:

- Attending Technical Body and WG meetings:

- Implementation Under Test Organisation 
(Communication with providers, establishment of VPN connections, etc.)

- CTI supervision

Task T1: Codec and TA development

The Codec and TA shall support both TCP and SCTP as transport protocol.

Note: The codec and TA software shall be delivered as source code including all source code modules needed for the compilation into an executable version of the software on the chosen test platform.

Task T2: ATS Validation

Task T3: TS Update

Milestone 1 – First Report on Validation Activities

Approval of Progress Report by INT#33 (Jun 2016) plenary

Milestone 2 – Second Report on Validation Activities

Approval of Progress Report by INT#34 (Sep 2016) plenary

Milestone 3 –Approval of all revised documents, STF Final Report

Approval of final drafts of PICS, TSS&TP and ATS&PIXIT documents

Approval of Final Report by INT#35 (Dec 2016) plenary

The draft documents must be uploaded by the STF Leader on the TB contributions area of the ETSI Portal two weeks before INT#35.

## Detailed effort estimate

T1	Codec and TA	Feb to Apr 2016

The Rf and Ro interfaces are defined in ETSI TS 132 260 and ETSI TS132 299. A significant number of data types are defined and have been implemented in the TTCN-3 code developed by STF490 in TS 103 374-3 V1.1.1. The bulk of the work will lie in the development of codec structures for each new TTCN-3 type.  The test architecture does not differ too much from the architecture for previous Diameter validation exercises, which has been developed within STF450, STF482 and STF500. It is assumed that this test architecture can be partly re-used. However, triggering via SIP interfaces is needed, which will add the development and integration of SIP related software modules.

T2	ATS Validation	Apr to Dec 2016

Validation against real existing and simulated Implementations Under Test (IUT)

Validation session will be performed by teams of 2 experts either on site at the premises of the provider of the IUT or at ETSI via a VPN connection.

Planned 8 validation sessions.

- Validation of 120 test cases for the Rf and Ro interfaces against 3 IUTs.

- Set up of connection with IUT provider done for remote testing

- 120 TTCN-3 scripts * 3 SUTs = 360 tests:

T3	TS Updates	Sep to Dec 2016

Transfer of the findings of the validation process into the test specification, i.e. into the three-part document covering PICS, TSS&TP and ATS&PIXIT.

PICS: Addition of PICS items where necessary.

TSS&TP: Correction of test purposes, addition/removal of test purposes where necessary.

ATS&PIXIT: Complete new version of the validated TTCN-3 code (bulk of the work).

All new version of the documents will be ready for TB approval at INT#33

Expected output:

PICS TS 103 374-1 V2.1.1

TSS&TP: TS 103 374-2 V2.1.1

ATS&PIXIT: TS 103 374-3 V2.1.1

# Required expertise

- Expert knowledge of DIAMETER protocols and VoLTE architecture

- Expert knowledge in procedures on the Rf and Ro interfaces

- Expert knowledge in validating DIAMETER test specification in TC INT

- Expert knowledge in implementing Abstract Test Suites in TTCN-3

- Awareness of output from previous work on Diameter testing in TC INT

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Key performance indicators suitable for this kind of STF projects are the following:

Contribution from ETSI Members to STF work

- Voluntary work of experts (free of charge or with partial remuneration)

- Steering Group meetings (number of participants/duration)

- Delegates attending meetings/events related to STF (number of participants/duration)

- Direct contribution of delegates (e.g. number of documents/comments/e-mail)

- Support to the STF work (e.g., provision of test–beds, organization of workshops, events)

- Contributions/presentations to other ETSI TBs

- Contributions received from other ETSI TBs

Contribution from STF experts to ETSI work

- Contributions presented to TB/WG meetings (number, type, comments received)

- Presentations in workshops, conferences, stakeholder meetings

Liaison with other stakeholders

- Stakeholder participation in the project (category, business area)

- Cooperation with other standardization bodies

- Potential interest of new members to join ETSI

- Liaison to identify requirements and raise awareness on ETSI deliverables

- Comments received on drafts (e.g. on WEB site, mailing lists, etc.)

Quality of deliverables

- Approval of deliverables according to schedule

- Respect of time scale, with reference to start/end dates in the approved ToR

- Quality review by TB

- Quality review by ETSI Secretariat

Time recording

The STF experts shall report in the time sheet provided by ETSI, the days spent for the performance of the services.

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

| Ver. | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 2015-10-13 | Giulio Maggiore | Draft | First draft |
| 0.2 | 2015-10-13 | Alberto Berrini | OCG/Board consultation | Added §6.7 (detailed effort estimate) |
| 0.3 | 2015-10-22 | Giulio Maggiore | Final Draft | Comments received by various members |
| 0.4 | 20-Nov-2015 | Alberto Berrini |  | Statement on time sheets in KPI’s |
| 0.5 | 27-Jan-2016 | Alberto Berrini | CfE | Abstract from ToR approved by Board#105 |