|  | ToR STF AO (TC ITS / WGs 1, 3, 5) |
| --- | --- |
|  | Version: 0.1 |
|  | Author: Sebastian Müller – Date:4 March 2016 |
|  | Last updated by: Alberto Berrini – Date:4 April 2016 |
|  | page 1 of 9 |

Terms of Reference - Specialist Task Force

STF AO (TC ITS / WGs 1, 3, 5)

“Validation of the Conformance Test Specifications for the ITS Protocols”

Summary information

| Approval status | Approved by TC ITS (doc ref: ITS(16)000031) Approved in principle by ETSI Board, if no comments from OCG consultation 25 April – 8 May) |
| --- | --- |
| Funding | Maximum budget: 100 000 € from ETSI FWP |
| Time scale | June 2016 to March 2017 |
| Work Items | See §6.2 (deliverables to be produced) |
| Board priority | Standards enablers/facilitators (e.g. conformance test/interoperability/methodology) Recommendations: use of TTCN and CTI supervision |

Part I – Reason for proposing the STF

# Rationale

ETSI will organize the latest in a series of interoperability events for ITS. This event will be hosted by CNIT from 7 to 18 November 2016 in Livorno, Italy (see http://www.etsi.org/news-events/events/1054-plugtests-2016-itscms5 ). More than 15 vendors are expected to attend the interoperability event which manifests the high interest of industry in ITS tests. As a prerequisite, a conformance test suite is needed in order to ensure the compliance of devices to the base standards. The existing test specifications must be updated according to the evolution to the ETSI ITS base standards. The ITS conformance test suite may also be used in upcoming certification programs.

# Objective

The objective of this present STF proposal is:

to update the current CA, DEN, SPAT&MAP, Security and GN test specifications according to the latest versions of ETSI ITS base specifications

to validate the test specifications against ITS implementations prior to the ITS Plugtests (pre-qualification phase)

to run the conformance test suite during the ITS Plugtests

# Relation with ETSI strategy and priorities

The STF will contribute to the following ETSI Strategy:

keep ETSI effective, efficient and recognised as such

create high quality standards for global use and with low time-to-market.

establish leadership in key areas impacting members' future activities

This request is in following the priority category:

Standards enablers/facilitators (conformance testing, interoperability, methodology)

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| BNETZA | Stefan Hiensch | The Federal Ministry of Economic Affairs and Energy (BMWi) supports the revision of the test specifications. |
| DENSO | Lutz Breyer | We have been following corresponding draft standards with our prototype implementations and final products need to pass the below mentioned tests. |
| FBConsulting | Friedbert Berens | FBConsulting supports the revision of the CA, DEN, GN and Security conformance test specifications. |
| HITACHI | Lan Lin | Testing STFs are a fundamental step to allow proper checking and validation of the standards we implement in our products. |
| KAPSCH | Hans Johannson | Testing is vital to the interoperability of different implementations of ITS G5 applications and supports an open market. |
| NEC | Andreas Festaf | Testing STFs are essential for successful interoperability testing and deployment. We will continue implementing latest ETSI standards in our products. |
| QFREE | Knut Evenson | Testing STFs are a fundamental step to allow proper validation of the standards we implement in our future products. The upcoming new version of the base standards makes it necessary to perform new tests. |
| RENAULT | Brigitte Lonc | Renault supports the revision of the CA, DEN, GN and Security conformance test specifications. |
| SPIRENT | Stephan Pietsch | Conformance testing is one of the essential tools in telecommunications for ensuring successful interoperability and credible commercial deployment. |
| TELECOM ITALIA | Marco Annoni | Conformance testing is one of the essential tools in telecommunications for ensuring successful interoperability and credible commercial deployment. |
| TNO | Jan de Jongh | ETSI standards successfully implemented in our products. Conformance test needed to ensure quality. |
| VOLKSWAGEN | Teodor Buburuzan | These test standards are important milestones to accompany deployment. |
| VOLVO | Katrin Sjoberg | Volvo supports the revision of the conformance test specifications for CN, DEN, GN and Security. |

## Market impact

With more than 200 million vehicles on the roads in Europe today and some 13 million jobs at stake across the continent, it is essential for Europe’s automotive industry to be at the forefront when it comes to introducing new technologies. However, the next generation of 'connected cars' will not work without common technical specifications, for example regarding radio frequencies and messaging formats. The TTCN-3 test specifications must be available in 2016 for product validation in order to support the product market entry.

## Tasks for which the STF support is necessary

Experience with the development of other standards has shown that involvement of experts on conformance and interoperability testing of protocols requires highly specialised knowledge in testing methodology. The generation of test specifications requires significant concentrated effort that can only be done by service contractors’ experts on a funded basis. Hence, the involvement of testing experts is needed in order to assure timely completion and high quality deliverables. The service contractors’ experts will use dedicated software tools available at ETSI. Test adapter development and test suite validation are expert tasks, which cannot be provided by a TB.

## Related voluntary activities in the TB

Delegates within the TC will review the deliverables

Companies will provide and install the devices that are being tested free of charge.

Companies will provide the hardware of the ITS test platform during the project, i.e. ITS G5 modem etc.

## Outcome from previous funded activities in the same domain

TC ITS has benefited of STF support in this domain:

TC ITS WG2: STF398 (2010) 72 000

TC ITS WG1/3: STF405 (2010-2012) EC/EFTA 354 000 €

TC ITS WG1/3: STF424 (2010-2012) EC/EFTA 246 900 €

TC ITS WG1/3: STF449 (2013) ETSI 68 000 €

TC ITS WG5: STF452 (2013/2014) ETSI 77 400 €

TC ITS WG1/3: STF462 (2013/2014) ETSI 63 200 €

TC ITS WG5: STF481 (2014/2015) ETSI 128 000 €

TC ITS WG1/3: STF484 (2014/2015) ETSI 51 200 €

TC ITS WG5: STF507 (2015/2016) ETSI 36 000 €

## Consequences if not agreed

ITS equipment is currently being deployed in experimental trials with the progression towards fully operational deployment. Thorough conformance testing will increase the level of confidence that equipment from various suppliers will interoperate. This in turn will reduce implementation and rollout times. Not providing timely validated and reliable test specifications, would ultimately delay the deployment of ITS.

Part II - Execution of the work

# Technical Bodies and other stakeholders

## Reference TB

TC ITS

## Other interested ETSI Technical Bodies

ITS WGs 1, 3, 5

## Other stakeholders

ERTICO - ITS Europe and ETSI have a MoU in place which defines amongst other activities the cooperation on ‘Testing support and certification initiative’.

SAE DSRC TC develops the basis of SPAT and MAP protocols on which the European Profile TS 103 301 is based.

The C2C CC has been an observer of the TC ITS test activities since 2010.

European Commission funded pre-deployment pilots such as AutoNet2030, iGAME, SCOOP@F and Cooperative ITS Corridor Rotterdam – Frankfurt/M. – Vienna, will benefit from the available tests.

# Base documents and deliverables

## Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| ETSI TS 102 894-2 RTS/ITS-00168 | Intelligent Transport Systems (ITS); Users and applications requirements; Part 2: Applications and facilities layer common data dictionary | Under revision | Apr 2016 |
| ETSI EN 302 637-2 | Intelligent Transport Systems (ITS); Vehicular Communications; Basic Set of Applications; Part 2: Specification of Cooperative Awareness Basic Service | Published | Available |
| ETSI EN 302 637-3 | Intelligent Transport Systems (ITS); Vehicular Communications; Basic Set of Applications; Part 3: Specifications of Decentralized Environmental Notification Basic Service | Published | Available |
| ETSI EN 302 636-4-1 RTS/ITS-00349 | Intelligent Transport Systems (ITS); Vehicular Communications; GeoNetworking; Part 4: Geographical addressing and forwarding for point-to-point and point-to-multipoint communications; Sub-part 1: Media-Independent Functionality | Under revision | Apr 2016 |
| ETSI TS 103 301 | Intelligent Transport Systems (ITS); Vehicular Communications; Basic Set of Applications; Facilities layer protocols and communication requirements for infrastructure services | Published | Available |
| ETSI TS 103 097 RTS/ITS-00533 | Intelligent Transport Systems (ITS); Security; Security header and certificate formats | Under revision | Apr 2016 |

## Deliverables to be produced

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | RTS/ITS-00169 TS 102 868-1 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification specifications for Cooperative Awareness Basic Service (CA); - Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) pro forma |
| D2 | RTS/ITS-00170 TS 102 868-2 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification specifications for Cooperative Awareness Basic Service (CA); - Part 2: Test Suite Structure and Test Purposes (TSS&TP); |
| D3 | RTS/ITS-00171 TS 102 868-3 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification specifications for Cooperative Awareness Basic Service (CA); - Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) |
| D4 | RTS/ITS-00172 TS 102 869-1 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification specifications for Decentralized Environmental Notification Basic Service (DEN); - Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) pro forma |
| D5 | RTS/ITS-00173 TS 102 869-2 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification specifications for Decentralized Environmental Notification Basic Service (DEN); - Part 2: Test Suite Structure and Test Purposes (TSS&TP); |
| D6 | RTS/ITS-00174 TS 102 869-3 | Revision of Intelligent Transport System (ITS); Testing; Conformance test specification specifications for Decentralized Environmental Notification Basic Service (DEN); - Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) |
| D7 | RTS/ITS-00352 TS 102 871-1 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) pro forma |
| D8 | RTS/ITS-00353 TS 102 871-2 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 2: Test Suite Structure and Test Purposes (TSS&TP) |
| D9 | RTS/ITS-00354 TS 102 871-3 | Revision of Intelligent Transport Systems (ITS); Testing; - Conformance test specifications for Geonetworking ITS-G5; Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) |
| D10 | RTR/ITS-0002 TR 103 099 | Intelligent Transport Systems (ITS); Architecture of conformance validation framework |
| D11 | RTS/ITS-00175 TS 103 191-1 | Intelligent Transport Systems (ITS); Testing; Conformance test specification for Signal Phase And Timing (SPAT) and Map (MAP); Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) pro forma |
| D12 | RTS/ITS-00176 TS 103 191-2 | Intelligent Transport Systems (ITS); Testing; Conformance test specification for Signal Phase And Timing (SPAT) and Map (MAP); Part 2: Test Suite Structure and Test Purposes (TSS&TP) |
| D13 | RTS/ITS-00177 TS 103 191-3 | Intelligent Transport Systems (ITS); Testing; Conformance test specification for Signal Phase And Timing (SPAT) and Map (MAP); Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) |
| D14 | RTS/ITS-00534 TS 103 096-1 | Intelligent Transport Systems (ITS); Testing; Conformance test specifications for ITS Security; Part 1: Test requirements and Protocol Implementation Conformance Statement (PICS) pro forma |
| D15 | RTS/ITS-00535 TS 103 096-2 | Intelligent Transport Systems (ITS); Testing; Conformance test specification for ITS Security; Part 2: Test Suite Structure and Test Purposes (TSS&TP) |
| D16 | RTS/ITS-00536 TS 103 096-3 | Intelligent Transport Systems (ITS); Testing; Conformance test specification for ITS Security; Part 3: Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) |

## Deliverables schedule:

Start of work	15-Jun-2016

ToC and scope	30-Jun-2016

Early draft	05-Sep-2016	ITS#24 (19-23 Sep)

Stable draft	31-Dec-2016	ITS#25 (16-20 Jan)

Final draft	31-Jan-2017	for WG approval (RC)

WG approval	02-Mar-2017	WG approval (RC)

TB approval	02-Apr-2017	TC ITS approval (RC)

Publication	02-May-2017

# Work plan, time scale and resources

## Task description

Task T0: Project Management

Attending Technical Body and WG meetings

Organisation of Devices Under Test (DUTs): communication with providers, establishment of VPN connections, etc.

Coordination, communication, reporting and leading of activities

Task T1: Tests, Codec and TA development

Update of tests and related codec and test adapter features according to base standard revisions:

Common Data Dictionary (ETSI TS 102 894-2)

GeoNetworking (ETSI EN 302 636-4-1)

Infrastructure (ETSI TS 103 301)

Security (ETSI TS 103 097)

The test update includes correction and development of new Test Purposes and the implementation in TTCN-3.

Furthermore tests will be updated according to issues found during the validation phase.

The Codec and TA software shall be delivered as source code including all source code modules needed for the compilation into an executable version of the software. The software shall be test platform independent. All software shall be accessible from https://forge.etsi.org

Task 2 – Pre-Qualification / ATS Validation

This task is the most important one, as it will support the pre-qualification process whereby each vendor who wants to attend the 2016-Plugtest shall run a selected set of conformance tests. 21 vendors attended the 2015-Plugtest in Helmond, NL. Based on this number it is expected that at least 15 and at most 25 vendors need to be pre-qualified. In summary:

Validation of ~ 80 TTCN-3 test cases against max 25 DUTs.

Set up of connection with DUT provider done for remote testing

80 TTCN-3 test cases * 25 SUTs = 2 000 tests

The validation report shall be provided in form of a simple spreadsheet and contributed to ITS#25. It shall be considered as supplementary information and it shall not be a deliverable. All information shall be provided in a statistical non-proprietary way.

This STF will provide level 2 validation, i.e.:

Extension and maintenance of the ITS Conformance Validation Framework

Provision and installation of SUT(s)

Execution of the tests

Reporting of errors in the ITS Conformance Validation Framework

Validation of test verdicts

Task T3: Plugtests support

At least 2 persons shall attend the 2016-Plugtest and provide support for conformance tests. Vendors who could not pre-qualify can do their pre-qualification in the first week of the 2016-Plugtest.

In addition to the pre-qualifying, the team will provide an on-demand support for debugging of erroneous device behaviour during the complete duration of the 2016-Plugtest.

Task T4: TS Updates

Production of the PICS, TSS&TP and ATS documents. Transfer of findings of the validation process into the test specification, i.e. into the three-part document covering PICS, TSS&TP and ATS&PIXIT.

PICS: Addition of PICS items where necessary.

TSS&TP: Transfer of tests from REQUALITY tool into WORD.

ATS&PIXIT: Update of the documentation

RTR/ITS-0002 (Architecture of conformance validation framework): Update of the documentation such as new Upper Tester commands etc.

Task T5: TC ITS approval and publication

T5.1 – Review of stable drafts

Before reaching the status of stable draft, the STF will submit the draft deliverables to editHelp for clean-up.  The STF will then present the stable drafts in parallel to the WG and TC ITS for comments and to the ETSI Secretariat for pre-processing.

T5.2 - Inclusion of comments from stable draft review

The STF will include the comments received from the stable draft review and produce the final drafts of the deliverables for WG and TC approval.

T5.3 - WG approval (RC)

The ETSI Secretariat will submit the final draft to the WGs concerned for approval by RC.

T5.4 – Preparation of Final Report

During the WG approval period, the STF Leader will prepare the Final Report, including the assessment of the Performance Indicators.

T5.5 – TC ITS approval (RC)

The ETSI Secretariat will submit the final drafts and the Final Report to TC ITS for approval by RC.

## Milestones

Milestone 1 – First Report on Revision Activities

Early draft including the result of Task 1 (Tests, Codec and Test Adapter updates) available for review.  Progress Report approved by ITS#24 (19-23 Sep 2016).  Documents must be uploaded on the TC docbox at least two weeks before the start of the TC plenary.

Milestone 2 - Second Report on Validation Activities

Stable drafts with the complete technical content of PICS, TSS&TP and ATS&PIXIT available for final review. Progress Report approved by ITS#25 (16-20 Jan 2017).  Documents must be uploaded on the TC docbox at least two weeks before the start of the TC plenary.

Milestone 3 – Deliverables and STF Final Report approved by TC ITS

All deliverables required by these ToR approved by TC ITS (RC) and accepted by the ETSI Secretariat for publication.  STF Final Report approved by TC ITS (RC).

M4 - Deliverables published, STF closed

Deliverables approved by TC ITS published.

STF closed.

## Task summary

| N | Task / Milestone / Deliverable | Target date | Estimated cost |
| --- | --- | --- | --- |
| M0 | Start of work | Jun 2016 |  |
| T0 | Project management, reporting, meeting attendance, CTI supervision | Jun 2016 – Feb 2017 | Done by ETSI CTI |
| T1 | Tests, Codec and Test Adapter updates | Jun– Aug 2016 | 34 000 |
| M1 | Early draft and Progress Report available ITS#24 Progress Report approval | 5 Sep 2016 23 Sep 2016 |  |
| T2 | ATS Validation | Sep – Oct 2016 | 42 000 |
| T3 | Plugtests (depending on validation completed) | Nov 2016 | 10 000 |
| T4 | TS Updates | Nov – Dec 2016 | 10 000 |
| M2 | Stable draft and Progress Report available ITS#25 Progress Report approval | 2 Jan 2017 20 Jan 2017 |  |
| T5.1 | Review of stable drafts (editHelp, WGs, TC ITS) | 02 Jan – 31 Jan |  |
| T5.2 | Inclusion of comments from stable draft review | 21 Jan – 31 Jan |  |
| T5.3 | WG approval (RC) | 01 Feb – 02 Mar |  |
| T5.4 | Preparation of Final Report | 01 Feb – 02 Mar |  |
| T5.5 | TC ITS approval deliverables and Final Report (RC) | 03 Mar – 02 Apr |  |
| M3 | Final Report approval | 02 Apr 2017 |  |
| T5.6 | Publication | 03 Apr – 02 May |  |
| M4 | Deliverables published, STF closed | 02 May 2017 |  |
| Total | 96 000 |

| Task Milest. | Description | J | J | A | S | O | N | D | J | F | M | A | M |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M0 | Start of work |  |  |  |  |  |  |  |  |  |  |  |  |
| T0 | Project management |  |  |  |  |  |  |  |  |  |  |  |  |
| T1 | Tests, Codec and Test Adapter updates |  |  |  |  |  |  |  |  |  |  |  |  |
| M1 | Progress Report ITS#24 (early draft) |  |  |  |  |  |  |  |  |  |  |  |  |
| T2 | ATS Validation |  |  |  |  |  |  |  |  |  |  |  |  |
| T3 | Plugtests Attendance |  |  |  |  |  |  |  |  |  |  |  |  |
| T4 | TS Updates |  |  |  |  |  |  |  |  |  |  |  |  |
| M2 | Progress Report ITS#25 (stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.1 | Review of stable drafts |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.2 | Inclusion of comments |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.3 | WG approval (RC) |  |  |  |  |  |  |  |  |  |  |  |  |
| M3 | Final Report |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.4 | TC ITS approval (RC) |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.5 | Publication |  |  |  |  |  |  |  |  |  |  |  |  |
| M4 | Deliverables published, STF closed |  |  |  |  |  |  |  |  |  |  |  |  |

## Working methods

The work will be partially performed remotely, at the contractor’s premises and partially in common sessions in the ETSI premises, to ensure coordination.  The participation to the Plugtests will require a mission travel to Livorno (I), which will be reimbursed by ETSI for real cost, under the travel budget.

The following preliminary assumption can be made for the location of the work:

Task T1: Tests, Codec and TA development: 90% remote, 10% ETSI

Task T2: Pre-Qualification / ATS Validation: 100% ETSI

Task T3: TS Updates: 100% remote

Task T4: Plugtests Attendance: 100% at Livorno (reimbursed at real cost on travel budget)

# Expertise required

Up to 4 contractors to ensure the following mix of skills:

expert knowledge of ETSI EN 302 637-2, ETSI EN 302 637-3, ETSI EN 302 636-4-1, ETSI EN 103 301, TS 102 941, ETSI EN 103 097;

expert knowledge of TTCN-3 (ES 201 873);

expert knowledge in conformance testing;

expert knowledge in codec and adaptation layer development in Java;

expert knowledge of ITS Security implementations

Part III:	Financial conditions

# Maximum budget

## Contractors cost

Maximum budget 96 000 € (see table in §7.3)

## Travel Costs

Maximum budget 4 000 €, including reimbursement of real cost for:

Travel for two persons to the ITS Plugtests 2016 (Task 4)

Presentation of reports and results to TC ITS and its WGs

## Other Costs

N/A

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from the ETSI Members

Number of WG/TC delegates involved in the review of the deliverables

Number of comments received

Number of Companies providing and installing devices to be tested, free of charge

Number of Companies providing the hardware of the ITS test platform during the project.

Interest from stakeholders other than ETSI Members

number of implementations using the test system in the pre-qualification and during the ITS Plugtests

Quality of deliverables

Approval of deliverables from the Reference TB according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.0 | 29-Mar-2016 | Sebastian Müller | First draft |  |
| 0.1 | 04-Apr-2016 | Alberto Berrini | Baord#107 |  |