|  | ToR STF AT (TC INT) |
| --- | --- |
|  | Version: 0.5 - Date: 13 June 2016 |
|  | Author: TC INT |
|  | Last updated by: Alberto Berrini – Date 9 June 2016 |
|  | page 1 of 4 |

Terms of Reference - STF AT (TC INT) Conformance Test Specifications for the S1AP and NAS protocols over the S1-MME reference point

Summary information

| Approval status | INT(16) 000008, approved by TC INT - RC INT(16)DEC0040 Approved by Board#108 |
| --- | --- |
| Funding | Maximum budget: ETSI FWP: 108 800 € |
| Time scale | Aug 2016 – Jun 2017 |
| Work Items | DTS/INT-00135-1 S1AP Conformance Testing for the S1-MME interface Part 1: Protocol Implementation Conformance Statement (PICS) DTS/INT-00135-2 S1AP Conformance Testing for the S1-MME interface Part 2: Test Suite Structure (TSS) and Test Purposes (TP) DTS/INT-00135-3 S1AP Conformance Testing for the S1-MME interface Part 3: Abstract Test Suite (ATS) and partial Protocol Implementation eXtra Information for Testing (PIXIT) proforma specification |
| Board priority category | Standards enablers/facilitators |

Part I – Reason for proposing the STF

# Rationale

The Mobility Management Entity (MME) is the key control-node for the VoLTE access-network. It connects via the S1-MME interface with an eNodeB using the S1AP protocol as defined in ETSI TS 136 413.

The MME is responsible for:

idle mode User Equipment (UE) paging and tagging

the bearer activation/deactivation processes

selection of the Serving Gateway (SGW) for a UE at the initial attach

authentication of the user (by interacting with the Home Subscriber Server (HSS) via the S6a interface)

The Non Access Stratum (NAS) signalling from the UE also terminates at the MME. The NAS protocols defined in ETSI TS 124 301 form the highest stratum of the control plane between a UE and the MME. NAS protocols support the mobility of the UE and the session management procedures to establish and maintain IP connectivity. NAS messages are transported between the eNodeB and the MME encapsulated in S1AP messages and are transparent for the eNodeB. There the MME is responsible for:

the generation and allocation of temporary identities to UEs

checking the authorization of the UE to camp on the service provider’s Public Land Mobile Network (PLMN)

enforcement of UE roaming restrictions

handling of the security key managements.

The network architecture is described in figure 1 below.

- Figure 1: Network architecture

The scope of this STF is to produce the conformance test specification for the MME protocol.  This is a standalone project not intended to complete the conformance test scenario for the VoLTE (IMS and EPC) architecture.  The conformance test for the NAS protocol and the validation of the test specification is not included in this project.  It will be handled with separate requests.

There is a significant difference between Phase 1 (S1AP) and Phase 2 (NAS). This is due to different complexity of the protocols. For example for NAS we only test direction towards MME, and instead for S1AP there are both directions towards MME and eNodeB. Another element of differences between Phase 1 and Phase 2 is also that Phase 1 includes the set-up of new data structure that will be completely reused in Phase 2. The Phase 1 will verify also the reuse of STF160 work on NAS done for testing the UE.

# Objective

Recently major efforts have been made by VoLTE component providers to inter-connect complete networks, i.e. connecting the single components that comprise a VoLTE network of different operators to allow seamless roaming for end customers and complete and reliable functionality for network providers. The S1-MME interface is a very important point for testing as it typically connects the radio components of one vendor to the MME of another vendor making flawless interworking of those components essential to the functioning of the network. Beside VoLTE the S1-MME interface is also of high importance for local small cell networks and new emerging technologies such as M2M communications.

Following the methodologies developed and used by ETSI this implies the production of multi-part conformance test specification documents covering the both the static conformance review (PICS proforma) and the dynamic conformance review (Test Purposes, Abstract Test Suite). The result would be a complete set of test suites for both the S1AP and the NAS protocols.

Note:	For the S1AP protocol tests will be written for testing both the MME and the eNodeB. For the NAS protocol only the MME will act as Implementation Under Test (IUT) as the NAS messages are transparent to the eNodeB. Testing the UE is out of the scope of TC INT.

ETSI members have expressed their interest in test specifications related to the S1AP and NAS protocol as defined in ETSI TS 136 413 and ETSI TS 124 301 and also declared their willingness to review the outputs of this STF and in a later stage in a potential follow-up project provide ETSI with the possibility to validate the outputs of this STF against their network components (i.e. eNodeB and MME). See also list of supporting organisations.

Experience with the development of other testing standards has shown that involvement of providers with expertise on conformance testing of protocols requires highly specialised knowledge in testing methodology, TTCN-3 language and dedicated tools. There is an advantage if testing expertise is disjoint from expertise in developing the protocol specifications. In addition, the development of this kind of specifications requires significant effort and it cannot be expected that this effort can be provided on a voluntary basis. Hence, the availability of testing expertise is needed in order to assure timely completion and high quality of the Test Specifications. This testing expertise is not available on TC INT level and need to be recruited on a funded basis. The providers must be in the position to use dedicated software tools that will be made available by ETSI.

# Relation with ETSI strategy and priorities

This STF is directly related to ETSI strategic objective “Major Strategic Topics – NGN” and “Service level interconnection of IP-Based Services” and corresponds to the “Standards enablers/facilitators (conformance testing, interoperability, methodology)” category.

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Telecom Italia | Giulio Maggiore | Tests used to get detailed information from vendors about Interoperability Testing before coming to the market |
| Telekom Austria | Martin Brand | Tests needed for internal network testing |
| Deutsche Telekom | Gerhard Ott | Tests needed for internal network testing |
| AT&T | Dewayne Sennet | Tests used to promote conformance testing for Public Safety |
| ZTE | David Huo | Test will be used for quality enhancement of IMS&EPC products |
| Iskratel | Primoz Svigeli | Test will be used for quality enhancement of IMS&EPC products |
| Italtel | Diego Saiu | Test will be used for quality enhancement of IMS&EPC products |
| Arcatech | Terence A, Simpson | Provide test system for functional and performance test. |
| Codenomicon | Ari Knuuti | Provide test system to test protocols |
| Spirent | Theofanis Vassiliou-Gioles | Provide the Test System for the test cases implementation and execution |
| Fraunhofer Fokus | Axel Rennoch/Marius Corici | Research Institute, advanced automated/standardized test solutions with TTCN-3 for Virtual environment |
| OU Elvior | Andres Kull | Tool Provider, Provide the Test System for the test cases |

## Market impact

The availability of reliable and validated test specifications will allow implementers of VoLTE components and protocol stacks (for eNodeB and MME) to test the conformance of their products against the protocol specifications. Conformance testing during the whole development phase of all VoLTE products will significantly reduce the time-to-market of the VoLTE architecture, as protocol conformant products will be of an enhanced quality level and will hence be less likely to cause interoperability problems with the products of other vendors.

Protocol conformant products will therefore provide the network operators with the means to deliver fully VoLTE compliant services to their end customers in a continuously high quality, with reliable service functionality, without communication failures and generally with the optimum quality of service for the transported media.

The tests for the S1-MME interface will consequently allow a faster rollout of the VoLTE networks due to well-tested and interoperable VoLTE entities that are responsible for key functionalities. Furthermore, the outputs of the present STF will be of high value for the small cell community as those local networks also use the S1AP and NAS protocols.

The emerging technologies of M2M communications will also heavily rely on a high level of conformance between the radio components (eNodeB) and the access components (MME) of the mobile network.

## Tasks that cannot be done within the TB and for which the STF support is necessary

VoLTE networks are currently being deployed in the telecoms industry. They must operate alongside and interwork correctly with the existing IMS networks already installed.

Consequently, there is the need to allow seamless roaming functionalities between the networks of different operators.

Field trials showed massive interoperability problems between different vendors. Therefore, detailed Abstract Test Specifications are urgently required to complete the overall testing framework.

To complete the testing work, and to capitalise on the investment done during the field trials, the corresponding Abstract Test Suite is urgently needed.

The ETSI members do not have sufficient resources to create an Abstract Test Suite on time, and with the high quality that has been experienced with using STF resources for this purpose in the past.

It is essential that this work is done in a timely manner in order to synchronise with global testing activities, especially in the context of VoLTE.

## Related voluntary activities in the TB

The ETSI Members supporting the creation of the STF are committed to supporting this STF in terms of participation in the STF Steering Group, providing input and review to the STF, providing test bed structures and test tools.

## Outcome from previous funded activities in the same domain

TC INT has not developed any test specifications for the S1-MME interface. This is a new activity.

## Consequences if not agreed

VoLTE networks are currently being deployed in telecoms networks during the progression towards fully VoLTE compliant network architectures. Thorough conformance testing will increase the level of confidence that equipment from various suppliers will interwork. This in turn will reduce implementation and rollout times. Not providing timely test specifications, would ultimately delay the deployment of VoLTE.

Part II – Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TC INT, Giulio Maggiore

## Other interested ETSI Technical Bodies

3GPP CT1

3GPP CT3

3GPP SA3

ETSI TC MTS

ETSI OneM2M

## Other stakeholders

GSMA IREG

Small Cell Forum

# Working method/approach

## Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| ETSI TS 136 413 | S1 Application Protocol (S1AP) | Published |  |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | DTS/INT-00135-01 | S1AP Conformance Testing for the S1-MME interface Part 1: Protocol Implementation Conformance Statement (PICS) |
| D2 | DTS/INT-00135-02 | S1AP Conformance Testing for the S1-MME interface Part 2: Test Suite Structure (TSS) and Test Purposes (TP) |
| D3 | DTS/INT-00135-03 | S1AP Conformance Testing for the S1-MME interface Part 3: Abstract Test Suite (ATS) and partial Protocol Implementation eXtra Information for Testing (PIXIT) proforma specification |

## Deliverables schedule:

DTS/INT-00135-1	Protocol Implementation Conformance Statement (PICS)

Start of work	01-Aug-2016

ToC and scope	01-Aug-2016

Early draft	30-Sep-2016

Stable draft	01-Dec-2016

TB approval	Mar-2017	INT#36

Publication	May-2017

DTS/INT-00135-2	Test Suite Structure (TSS) and Test Purposes (TP)

Start of work	01-Aug-2016

ToC and scope	01-Aug-2016

Early draft	31-Oct-2016

Stable draft	Mar-2017	INT#36

TB approval	Jun-2017	INT#37

Publication	Aug-2017

DTS/INT-00135-3	Abstract Test Suite (ATS) and partial Protocol Implementation eXtra Information for Testing (PIXIT) proforma specification)

Start of work	01-Aug-2016

ToC and scope	01-Aug-2016

Early draft	31-Dec-2016

Stable draft	31- May-2017

TB approval	Jun-2017	INT#37

Publication	Aug-2017

Note:	The tests for the S1AP protocol cover the requirements on both the eNodeB and the MME.

# Work plan, time scale and resources

## Organization of the work

The work of the STF starts with the analysis of the S1AP protocol requirements defined in ETSI TS 136 413 on the eNodeB and the MME. Following the work will follow the three step methodology defined in the ISO/IEC 9646 series on conformance test specifications.

- Static aspects of the requirements will be converted into PICS items, i.e. into questions demanding whether a requirement is supported or not. One set of PICS items will be created for eNodeB and one for the MME.

- Requirements on the dynamic behaviour will lead to test purposes, i.e. textual descriptions of the expected behaviour of the IUT (eNodeB or MME). Here also, two sets of test purposes for eNodeB and MME will be the resulting output of the STF.

- The bulk of the work will lie in the coding of the dynamic behaviour into test cases using the formal notation TTCN-3 and the production of the PIXIT proforma, which contains questions related to the practical aspects of testing.

A feedback loop will be installed to process findings of the later steps into the outputs of the earlier steps. Once the TTCN-3 code and the related PIXIT proforma have been completed, TC INT may request to proceed with the following phases of the project (conformance testing of the NS protocol, vliadtion).

TC INT will act as the steering committee for all STF activities and will inform all identified interested bodies via liaison statements at regular intervals.

An administration task will be maintained handling the progress reports of the STF and the representation at the TC INT meetings during the lifetime of the STF.

## Task description

Task 1 – Project Management

Objectives

Provision of progress reports for the TC INT meetings #34 through to #37. Presentation of reports and STF outputs during said meetings.  Scheduling of common sessions, administration of STF resources.

Processing of feedback comments received from the stakeholders.

The STF leader will perform all actions required by this task.

Input

None

Output

Three STF progress reports and one final report.

Interactions

Presence at all TC INT meetings during the STF’s lifetime.

Task 2 – PICS

Objectives

Creation of a PICS document for ETSI TS 136 413 containing two PICS proforma, one for eNodeB, one for MME static conformance review.

Input

ETSI TS 136 413

Output

DTS/INT-00135-1

Interactions

Presentation of an early draft at INT#34 (Sep 2016), a stable draft at INT#35 (Dec 2016) and a final draft for approval at INT#36 (Mar 2017)

Task 3 – TSS&TP

Objectives

Creation of a TSS&TP document for ETSI TS 136 413 containing two sets of test purposes covering all dynamic requirements for eNodeB and MME for the dynamic conformance review.

Input

ETSI TS 136 413

Output

DTS/INT-00135-2

Interactions

Presentation of an early draft at INT#35 (Dec 2016), a stable draft at INT#36 (Mar 2017) and a final draft for approval at INT#37 (Jun 2017)

Task 4 – ATS&PIXIT

Objectives

Implementation of all test purposes defined in DTS/INT-00135-2 into TTCN-3 code and production of two PIXIT proforma one for eNodeB and one for MME.

Input

ETSI TS 136 413

Output

DTS/INT-00135-3

Interactions

Presentation of an early draft at INT#36 (Mar 2017) and a final draft for approval at INT#37 (Jun 2017)

## Milestones

Milestone 1 – Early draft S1AP PICS, Progress report A

Approval of progress report A.

Presentation of an early draft of DTS/INT-00135-1 and progress report A at INT#34 (Sep 2016).

DTS/INT-00135-1 has to be made available at least two weeks before the start of INT#34.

Milestone 2 – Stable draft S1AP PICS, Early draft S1AP TSS&TP, Progress report B

Approval of progress report B.

Presentation of an early draft of DTS/INT-00135-2, a stable draft of DTS/INT-00135-1 and progress report B at INT#35 (Dec 2016).

DTS/INT-00135-1 and -2 have to be made available at least two weeks before the start of INT#35.

Milestone 3 – Approval S1AP PICS, Stable draft S1AP TSS&TP, Early draft S1AP ATS&PIXIT, Progress report C

Approval of DTS/INT-00135-1 and progress report C.  Presentation of an early draft of DTS/INT-00135-3, a stable draft of DTS/INT-00135-1 and progress report C at INT#36 (Mar 2017).  DTS/INT-00135-2 and -3 have to be made available at least two weeks before the start of INT#36.

Milestone 4 – Approval S1AP TSS&TP and S1AP ATS&PIXIT, Final phase I report D

Approval of DTS/INT-00135-2, DTS/INT-00135-3 and final phase I report D.  Presentation of final phase I report D at INT#37 (Jun 2017).  DTS/INT-00135-2 and -3 have to be made available at least two weeks before the start of INT#37.

## Task summary

| N | Task / Milestone / Deliverable | Target date |
| --- | --- | --- |
| M 0 | Start of work | Aug 2016 |
| T1 | Project Management | Aug 2016 – Jun 2017 |
| T2 | S1AP PICS | Aug 2016 – Mar 2017 |
| M1 | Progress Report A | Sep 2016 |
| T3 | S1AP TSS&TP | Aug 2016 – Jun 2017 |
| M 2 | Progress Report B | Dec 2016 |
| T4 | S1AP ATS&PIXIT | Aug 2016 – Jun 2017 |
| M3 | Progress Report C, approval S1AP PICS | Mar 2017 |
| M4 | Final report D, approval S1AP TSS&TP and ATS&PIXIT | Jun 2017 |

| Year | 2016 | 2017 |
| --- | --- | --- |
| Task Milest. | Description | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D |
| M0 | Start of work phase I | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1 | Project Management phase I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2 | S1AP PICS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M1 | Progress Report A |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3 | S1AP TSS&TP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M2 | Progress Report B |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| T4 | S1AP ATS&PIXIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| M3 | Progress Report C, approval S1AP PICS |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| M4 | Final phase I report D, approval S1AP TSS&TP and ATS&PIXIT |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |

## Working methods and travel cost

The work will be performed in a mix of remote sessions and common sessions at ETSI.

Task 1: Ongoing task, no common session needed, travel to INT meetings may be required

Task 2: 100% remote, task

Task 3: Two coordination sessions needed

Task 4: Three coordination sessions needed

Travel cost for working sessions (e.g. Tasks 3, 4) will be included in the contract compensation (manpower cost). Presentation of results to TC INT will be reimbursed as real cost from the travel budget if the meeting takes place outside of ETSI.

# Expertise required

Providers must ensure the following mix of competence:

knowledge of S1AP and NAS protocols and VoLTE architecture

Experience in analysing of protocols and writing of PICS proforma

Experience in analysing of protocols and writing of test purposes

knowledge in implementing Abstract Test Suites in TTCN-3

Awareness of outputs from earlier INT STFs on VoLTE (preferred)

The actual number of providers depends on the actual mix of skills in the applications received and will be decided when setting up the STF.

Part III:	Financial conditions

# Maximum budget

| Phase I | Maximum estimated cost (€) |
| --- | --- |
| Service contracts | 107 000 |
| Travels to two INT meetings | 1 800€ |
| Total cost | 108 800 |

No other cost has been identified.

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Key performance indicators suitable for this kind of STF projects are the following:

Contribution from ETSI Members to STF work

Steering Group meetings (number of participants/duration)

Delegates attending meetings/events related to STF (number of participants/duration)

Direct contribution of delegates (e.g. number of documents/comments/e-mail)

Support to the STF work (e.g., provision of test–beds, organization of workshops, events)

Contributions/presentations to other ETSI TBs

Contributions received from other ETSI TBs

Contribution from STF participants to ETSI work

Contributions presented to TB/WG meetings (number, type, comments received)

Presentations in workshops, conferences, stakeholder meetings

Liaison with other stakeholders

Stakeholder participation in the project (category, business area)

Cooperation with other standardization bodies

Potential interest of new members to join ETSI

Liaison to identify requirements and raise awareness on ETSI deliverables

Comments received on drafts (e.g. on WEB site, mailing lists, etc.)

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Quality review by TB

Quality review by ETSI Secretariat

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators. The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 06-April-2016 | Giulio Maggiore | Draft | Initial draft |
| 0.2 | 1 May 2016 | Alberto Berrini |  |  |
| 0.3 | 4 May 2016 | Giulio Maggiore |  | More information added to the rationale |
| 0.4 | 09-Jun-2016 |  | Board#108 | Approved with 5% maximum budget reduction |
| 0.5 | 13-Jun-2016 | Alberto Berrini | CfE | Reference to Phase 2 removed |