STF 705 – EUDIW-Stan - 101260771

Description of the Action (Part B)

(SMP STAND Standard)

Version 6.0

19 August 2025

PROJECT FACT SHEET

STF 705 / [2025-11]

| Reference Body |  | ESI |  |
| --- | --- | --- | --- |
| EC/EFTA Funding |  | Manpower: 1 560 000 € |  |
|  |  | Travels (estimated): 48 000 € |  |
|  |  | Other costs: 65 000 € |  |
|  |  | Total Budget (estimated): 1 673 000 € |  |
| Project Duration |  |  | 24 months |
| WP# | Task in BC | Task names | Amount |
| WP1: Project management and coordination | T0 | T1.1 Project set-up | 0 € |
|  | T1 | T1.2 Project management | 36 400 € |
|  | T2 | T1.3 Work package lead | 32 500 € |
| WP2: Wallets and privacy | T3 | T2.1 Batch 2025 wallet publication confirmation | 182 000 € |
|  | T4 | T2.2 Prepare stable drafts batch 2026/2027-B for wallet | 130 000 € |
|  | T5 | T2.3 Prepare ETSI TB approval batch 2026/2027-B for wallet | 130 000 € |
|  | T6 | T2.4 Prepare ENAP comment disposition batch 2026/2027-B wallet | 65 000 € |
| WP3: certificates and timestamps | T7 | T3.1 Batch 2025 certificates and timestamps publication confirmation | 123 500 € |
|  | T8 | T3.2 Prepare stable drafts batch 2026/2027-A for certificates and timestamps | 29 250 € |
|  | T9 | T3.3 Prepare ETSI TB approval batch 2026/2027-A for certificates and timestamps | 29 250 € |
|  | T10 | T3.4 Prepare ENAP comment disposition batch 2026/2027-A for certificates and timestamps | 6 500 € |
|  | T11 | T3.5 Prepare stable drafts batch 2026/2027-B for certificates and timestamps | 9 750 € |
|  | T12 | T3.6 Prepare ETSI TB approval batch 2026/2027-B for certificates and timestamps | 9 750 € |
|  | T13 | T3.7 Prepare ENAP comment disposition batch 2026/2027-B for certificates and timestamps | 6 500 € |
| WP4: ERDS | T14 | T4.1 Prepare stable draft batch 2026/2027-A for ERDS | 31 200 € |
|  | T15 | T4.2 Prepare ETSI TB approval batch 2026/2027-A for ERDS | 31 200 € |
|  | T16 | T4.3 Prepare ENAP comment disposition batch 2026/2027-A for ERDS | 15 600 € |
| WP5: Signatures | T17 | T5.1 Batch 2025 wallet publication confirmation | 78 000 € |
|  | T18 | T5.2 Prepare stable drafts batch 2026/2027-A for signatures | 52 000 € |
|  | T19 | T5.3 Prepare ETSI approval batch 2026/2027-A for signatures | 52 000 € |
|  | T20 | T5.4 Prepare ENAP comment disposition batch 2026/2027-A for signatures | 26 000 € |
|  | T21 | T5.5 Prepare stable drafts batch 2026/2027-B for signatures | 5 200 € |
|  | T22 | T5.6 Prepare ETSI TB approval batch 2026/2027-B for signatures | 5 200 € |
|  | T23 | T5.7 Prepare ENAP comment disposition batch 2026/2027-B for signatures | 2 600 € |
| WP6: Trust framework | T24 | T6.1 Batch 2025 wallet publication confirmation | 91 000 € |
|  | T25 | T6.2 Prepare stable drafts batch 2026/2027-A for trust framework | 23 400 € |
|  | T26 | T6.3 Prepare ETSI TB approval batch 2026/2027-A for trust framework | 23 400 € |
|  | T27 | T6.4 Prepare ENAP comment disposition batch 2026/2027-A for trust framework | 5 200 € |
|  | T28 | T6.5 Prepare stable draft batch 2026/2027-B for trust framework | 10 400 € |
|  | T29 | T6.6 Prepare ETSI TB approval batch 2026/2027-B for trust framework | 10 400 € |
|  | T30 | T6.7 Prepare ENAP comment disposition batch 2026/2027-B for trust framework | 5 200 € |
| WP7: New technology | T31 | T7.1 Prepare stable drafts batch 2026/2027-A for new technology | 26 000 € |
|  | T32 | T7.2 Prepare ETSI TB approval batch 2026/2027-A for new technology | 26 000 € |
| WP8: Consultation and Dissemination | T33 | T8.1 Certificate authority workshop - hosting | 6 500 € |
|  | T34 | T8.2 Certificate authority workshop - Presentations | 13 000 € |
|  | T35 | T8.3 ERDS workshop - hosting | 6 500 € |
|  | T36 | T8.4 ERDS workshop - Presentations | 13 000 € |
|  | T37 | T8.5 EUDI Wallet workshop - Hosting | 6 500 € |
|  | T38 | T8.6 EUDI Wallet workshop - Presentations | 19 500 € |
|  | T39 | T8.7 External liaison | 26 000 € |
|  | T40 | T8.8 Liaison with EU DG connect 2025 | 46 800 € |
|  | T41 | T8.9 Liaison with EU DG connect 2026/2027 | 46 800 € |
| WP9: Testing | T42 | T9.1 Testing framework study | 65 000 € |

# TECHNICAL DESCRIPTION (PART B)

| HISTORY OF CHANGES |  |  |
| --- | --- | --- |
| VERSION | PUBLICATION DATE | CHANGE |
| 1.0 | 01.03.2022 | Initial version (new MFF). |
| 2.0 | 01.06.2022 | Consolidation, formatting and layout changes. Tags added. |
| 3.0 | 28.05.2025 | Version submitted to Board for review |
| 4.0 | 06.06.2025 | Addressing Board comments |
| 5.0 | 12.06.2025 | Final version for EISMEA Submission |
| 6.0 | 19.08.2025 | Comments addressed following ESR: - Quality – Project Design and implementation - Update Part 2.5 Project management, quality assurance and monitoring and evaluation strategy: More detail on risk management strategies and resource allocation have been added - Quality – Project team and cooperation arrangements - Update Project teams, staff and experts table adding the two TC Vice-Chairs in case of unavailability of the TC Chair - Impact - Update Part 3.1: Details have been provided on how the maintenance of the Standards will be ensured. - Dissemination activities: - Work package 8 has been renamed “Consultation and Dissemination” to spread the outcomes - Scope of Task 8.7 has been extended and now includes a new Deliverable (D8.10) on the dissemination results. |

## COVER PAGE

| PROJECT |  |
| --- | --- |
| Project name: | EUDI Wallet Standardisation and Technical Specifications |
| Project acronym: | EUDIW-stan |
| Project Duration (in months) | 24 Months |
| Coordinator contact: | Jan Ellsberger, ETSI DG |

TABLE OF CONTENTS

TECHNICAL DESCRIPTION (PART B)	2

COVER PAGE	2

PROJECT SUMMARY	3

1. RELEVANCE	3

1.1 Background and general objectives	3

1.2 Needs analysis and specific objectives	4

1.3 Complementarity with other actions and innovation	9

2. QUALITY	9

2.1 Concept and methodology	9

2.2 Consortium set-up	9

2.3 Project teams, staff and experts	9

2.4 Consortium management and decision-making	11

2.5 Project management, quality assurance and monitoring and evaluation strategy	12

2.6 Cost effectiveness and financial management	12

2.7 Risk management	13

3. IMPACT	15

3.1 Impact and ambition	15

3.2 Communication, dissemination and visibility	17

3.3 Sustainability and continuation	17

4. WORKPLAN, WORK PACKAGES, ACTIVITIES, RESOURCES AND TIMING	18

4.1 Work plan	18

4.2 Work packages, activities, resources and timing	21

Work Package 1	21

Work Package 2	24

Work Package 3	33

Work Package 4	40

Work Package 5	42

Work Package 6	49

Work Package 7	55

Work Package 8	57

Work Package 9	61

Total Project costs	63

4.3 Subcontracting	65

Timetable	67

5. OTHER	73

5.1 Ethics	73

5.2 Security	73

6. DECLARATIONS	73

#@APP-FORM-SMPSTAND@#

#@PRJ-SUM-PS@#  [This document is tagged. Do not delete the tags; they are needed for the processing.]

## PROJECT SUMMARY

Project summary

The proposal is to update existing and define new technical specifications and standards (STS) for Implementing Acts under Regulation (EU) 2024/1183 of the European Parliament and of the Council of 11 April 2024 amending Regulation (EU) No 910/2014 with regards to establishing the European Digital Identity Framework including the EU Digital Identity Wallet. The requirements for the STS are derived from the outcomes of a gap analysis, conducted by DG Connect to identify shortcomings in the existing STS and to support the advancement of the EUDI Wallet ecosystem, as outlined in the Regulation. The EUDI Wallet Architecture and Reference Framework (hereinafter - ARF) sets out the functional and non-functional requirements, for the different actors and stakeholders to comply with, and for which common STS are essential to provide interoperability and conformity. Digital identity wallets that comply with the general EUDI Wallet requirements and specifications can be securely and efficiently deployed across the European Union for the daily use of both natural and legal persons in Member States and associated countries, including in cross-border contexts. The EUDI wallet would thereby become a key instrument for citizens and businesses, enabling identification, authentication and access to digital services in public and private sectors, supporting the use of electronic signatures, and facilitating the storage and sharing of additional identity related information in attribute attestations supporting a range of applications including government, banking, travel, telecommunications and health.

#§PRJ-SUM-PS§# #@REL-EVA-RE@# #@PRJ-OBJ-PO@#

## 1. RELEVANCE

### 1.1 Background and general objectives

The European Digital Identity Framework aims to create an ecosystem for digital identities and trust services to enable digital and cross-border transactions in the public and private sector throughout the EU. The Regulation (EU) No 910/2014 already provided an EU-wide notification system for national eID´s and European standards for trust services. The amended Regulation (EU) 2024/1183 of the European Parliament and of the Council of 11 April 2024 now foresees cross-border interoperability through common standards and technical specifications. Digital identities and trust services such as the qualified electronic signature will be provided via Digital Identity Wallet. The rules and requirements for the member states are described and defined by law through the regulation and respective implementing acts and through the Architecture and Reference Framework (ARF) which serves as a guideline for the member states regarding the technical implementation of the EUDI wallet. The implementing acts and the ARF will reference standards that member states should follow. Therefore the European Commission (hereinafter – EC) has conducted a gap analysis to examine existing technical specification and standards (STS) that need updating and identifying gaps where new STS have to be created. This project aims at supporting the update and production of new STS following the outcomes of the gap analysis. The gap analysis provided a comprehensive overview of the necessary deliverables. The objective of this project is to address the gaps and support the development of several STS that are necessary for the successful implementation of the EUDI Wallet ecosystem described and defined in the Regulation 910/2014 amended by Regulation 2024/2018 on European Digital Identity Framework.

### 1.2 Needs analysis and specific objectives

The need for STS is based on a gap analysis carried out by the European Commission against the aims of the EU Digital Identity Wallet Architecture and Reference Framework. The call includes a list of 42 deliverables to be created or revised by ETSI. The list is based on a list of 42 gaps that DG CONNECT and TC ESI agreed on based on “batch 1-3” requirements for covering activities to be completed before November 2025. However: - In some cases, there are changes proposing minor variations in the ETSI standards and technical specification (STS) referencing alternative STS to achieve the same technical objective, this applies to both existing and new standards. - In addition, further deliverables are proposed for as 2026 deliverables to meet what is understood to be the additional STS that are considered necessary to complete the 2026 objectives for a complete roadmap meeting the “Batch 4-6” objectives for the EUDI Wallet. This generally applies to existing standards. - New standards are identified by ETSI of potential benefit to the general use of the EU Digital Identity Wallet. The resulting changes to the existing standards is to be updated are as highlighted below: No; Title. 1; Removed from this table. Covered by item n.8 in table no. 2 with the new standards to be developed.. 2; ETSI TS 119 432 - Electronic Signatures and Infrastructures (ESI); Protocols for remote digital signature creation. 3; Moved TS 119 602 as new standard Ref New 23. 4; ETSI TS 119 612 - Electronic Signatures and Infrastructures (ESI); Trusted Lists. 5; ETSI EN 319 102-1 - Electronic Signatures and Trust Infrastructures (ESI); Procedures for Creation and Validation of AdES Digital Signatures; Part 1: Creation and Validation. 6; ETSI TS 119 102-2 - Electronic Signatures and Infrastructures (ESI); Procedures for Creation and Validation of AdES Digital Signatures; Part 2: Signature Validation Report. 7; ETSI TS 119 172-4 - Electronic Signatures and Infrastructures (ESI); Signature Policies; Part 4: Signature applicability rules (validation policy) for European qualified electronic signatures/seals using trusted lists. 8; ETSI TS 119 312 - Electronic Signatures and Trust Infrastructures (ESI); Cryptographic Suites There is no need to develop an EN. This update will maintain the status of TS to facilitate further updates.. 9; ETSI EN 319 401 - Electronic Signatures and Trust Infrastructures (ESI); General Policy Requirements for Trust Service Providers. 10; ETSI EN 319 403-1 - Electronic Signatures and Infrastructures (ESI); Trust Service Provider Conformity Assessment; Part 1: Requirements for conformity assessment bodies assessing Trust Service Providers. 11; ETSI TS 119 403-3 - Electronic Signatures and Infrastructures (ESI); Trust Service Provider Conformity Assessment; Part 3: Additional requirements for conformity assessment bodies assessing EU qualified trust service providers. 12a; ETSI EN 319 411-2 - Electronic Signatures and Trust Infrastructures (ESI); Policy and Security Requirements for Trust Service Providers issuing certificates; Part 2: Requirements for trust service providers issuing EU qualified certificates. 12b; ETSI EN 319 411-1 - Electronic Signatures and Trust Infrastructures (ESI); Policy and Security Requirements for Trust Service Providers issuing certificates; Part 1: General requirements This document needs to be updated due to the 12a ETSI EN 319 411-2. 12c; ETSI TR 119 411-4 - Electronic Signatures and Trust Infrastructures (ESI); Policy and Security Requirements for Trust Service Providers issuing certificates; Part 4: Checklist supporting audit of TSP against ETSI EN 319 411-1 or ETSI EN 319 411-2 This document needs to be updated due to the 12a ETSI EN 319 411-2. 13; ETSI EN 319 421 - Electronic Signatures and Trust Infrastructures (ESI); Policy and Security Requirements for Trust Service Providers issuing Time-Stamps. 14; ETSI EN 319 422 - Electronic Signatures and Infrastructures (ESI); Time-stamping protocol and time-stamp token profiles. 15; ETSI TS 119 431-1 - Electronic Signatures and Trust Infrastructures (ESI); Policy and security requirements for trust service providers; Part 1: TSP services operating a remote QSCD / SCDev. 16; ETSI TS 119 441 - Electronic Signatures and Infrastructures (ESI); Policy requirements for TSP providing signature validation services. 17; ETSI TS 119 461 - Electronic Signatures and Trust Infrastructures (ESI); Policy and security requirements for trust service components providing identity proofing of trust service subjects. 18a; ETSI TS 119 511 - Electronic Signatures and Infrastructures (ESI); Policy and security requirements for trust service providers providing long-term preservation of digital signatures or general data using digital signature technologies. 18b; ETSI TS 119 512 - Electronic Signatures and Infrastructures (ESI); Protocols for trust service providers providing long-term data preservation services This document needs also to be updated due to the 18a ETSI TS 119 511. 19a; ETSI EN 319 521 - Electronic Signatures and Infrastructures (ESI); Policy and security requirements for Electronic Registered Delivery Service Providers. 19b; ETSI EN 319 522-1 - Electronic Signatures and Infrastructures (ESI); Electronic Registered Delivery Services; Part 1: Framework and Architecture This document needs also to be updated due to the 19a ETSI EN 319 521. 19c; ETSI EN 319 522-2 - Electronic Signatures and Infrastructures (ESI); Electronic Registered Delivery Services; Part 2: Semantic contents This document needs also to be updated due to the 19a ETSI EN 319 521. 19d; ETSI EN 319 522-3 - Electronic Signatures and Infrastructures (ESI); Electronic Registered Delivery Services; Part 3: Formats This document needs also to be updated due to the 19a ETSI EN 319 521. 19e; ETSI EN 319 522-4-1 - Electronic Signatures and Infrastructures (ESI); Electronic Registered Delivery Services; Part 4: Bindings; Sub-part 1: Message delivery bindings This document needs also to be updated due to the 19a ETSI EN 319 521. 19f; ETSI EN 319 522-4-2 - Electronic Signatures and Infrastructures (ESI); Electronic Registered Delivery Services; Part 4: Bindings; Sub-part 2: Evidence and identification bindings This document needs also to be updated due to the 19a ETSI EN 319 521. 19g; ETSI EN 319 522-4-3 - Electronic Signatures and Infrastructures (ESI); Electronic Registered Delivery Services; Part 4: Bindings; Sub-part 3: Capability/requirements bindings This document needs also to be updated due to the 19a ETSI EN 319 521. 20; ETSI TS 119 615 - Electronic Signatures and Infrastructures (ESI); Trusted lists; Procedures for using and interpreting European Union Member States national trusted lists. 21; ETSI TS 119 182-1 (to be EN 319 182-1) “Electronic Signatures and Trust Infrastructures (ESI); JAdES digital signatures; Part 1: Building blocks and JAdES baseline signatures This document needs to be updated to take into account feedback from implementers and to issue as a EN.. The resulting changes to the new standards to be developed are as highlighted below: No.; Title; DG CONNECT Gaps covered. 1, 3; Reference to be allocated.; (4.2.1) Common formats and API for Relying Party Registry information (4.2.3) Common set of Relying Party information to be registered Cover both requirements 4.2.1 and 4.2.3 with one document. 2; ETSI EN 319 411-8; (4.2.2) Common Access CA Certificate Policy. 4; ETSI EN 319 478; (4.2.14) Specification of interfaces related to Authentic Sources. 5; Added to TS 119 475 and TS 119 472; (4.2.15) Specification of mechanism allowing embedded disclosure policies This requirement will be covered in 475 and 472. ETSI does not need to deliver an additional document. 6; ETSI TS 119 476-2; (4.2.16) Zero-Knowledge Proof (ZKP) Implementation in EUDI Wallet As this document introduces new technology which has yet to be tried and tested with the EUDI Wallet, it is proposed to only issue it as a TS only.. 7, 8, 9; ETSI EN 319 412-6; Interoperability Profile 6: Certification Authority for the PID Issuing Authority (certificate profiles) Interoperability Profile 7: Certification Authority for the (Q)EAA/PUB-EAA Issuing Authority (certificate profiles) Interoperability Profile 8: Certification Authority for the Wallet Issuing Authority (certificate profiles) Cover all the three requirements with one document. 10; Reference to be allocated.; (4.2.4) Specification of the Wallet Unit Attestation (WUA). 11; Reference to be allocated.; (4.2.6) Specification of EUDI Wallet Trust Mark. 12; Reference to be allocated.; (4.2.7) Specification of common interface for lodging complaints to DPAs. 13; Reference to be allocated.; (4.2.8) Specification of common interface for data deletion requests to Relying Parties. 14; Reference to be allocated.; (4.2.9) Specification of interfaces and formats for the catalogue of Attestation Rulebooks and attributes. 15; Reference to be allocated.; (4.2.10) Specification of Wallet-to-Wallet interactions. 16; Reference to be allocated.; (4.2.11) Specification of systems enabling the notification and subsequent publication of Provider information. 17; Reference to be allocated.; (4.2.12) Data Portability and Download (export). 18; TR 119 462; Wallet interfaces for trust services and signing – general concepts. 19; ETSI EN 319 471; Policy and Security requirements for Providers of Electronic Attestation of Attribute Services. 20; ETSI EN 319 472-1; General Requirements for profiles for Electronic Attestation of Attributes (EAAs). 21; ETSI EN 319 472-2; Profiles for Relying Party Interface to EUDI Wallet. 22; ETSI EN 319 475; Relying party authorisations for access to EUDI Wallet. 23; ETSI EN 319 602; Trusted lists data model Moved here from the table of the standards that initially were planned to be updated.. 24; ETSI EN 319 472-3; Profiles for issuance of EAA or PID To fulfil the requirements issuance of EAA or PID need to create a 3rd part of the 472 (see lines 20 and 21 above). 25; ETSI TS 119 605; Processing trusted lists and trusted list content To fully cover the requirement, we initially foresaw as part of 602 ETSI suggests the creation of an additional document 605 Note: As this STS introduces new technology which has yet to be tried and tested with the EUDI Wallet is proposed only to issue this as a TS.. 26; ETSI TS 119 479-2; Extended validation services This is needed to address the detailed requirements for the provision of trust services for the validation of electronic attestation of attributes; as identified in Regulation 2024/1183 article 3 (16)(h). Note: As this STS introduces new technology which has yet to be tried and tested with the EUDI Wallet is proposed only to issue this as a TS.. 27; ETSI TS 119 479-3; Support for EAA within AdES signatures Needed to bind EAA to signatures Note: As this STS introduces new technology which has yet to be tried and tested with the EUDI Wallet is proposed only to issue this as a TS.. 28; ETSI TS 119 411-9; Requirements on a Certificate Transparency (CT) Ecosystem to make the issuing of certificates transparent and verifiable Needed for transparency of the issuance of certificates. Note: As this STS introduces new technology which has yet to be tried and tested with the EUDI Wallet is proposed only to issue this as a TS.. 29; ETSI EN 319 152-1 -; CB AdES (CBOR-AdES) digital signatures; Part 1: Building blocks and CB-AdES baseline signature Needed to support AdES in CBOR based solutions.. Other topics are proposed supporting consultation, coordination and testing of the standards.

#§PRJ-OBJ-PO§# #@COM-PLE-CP@#

### 1.3 Complementarity with other actions and innovation

ETSI is one of the European Standardization Organisations (ESO) supporting the European Commission in many different activities. The technical working group ETSI ESI has created several STS for the eIDAS regulation 910/2014. Those standards are widely used and appreciated today. ETSI ESI holds a variety of liaisons and cross memberships with different stakeholder groups in the ecosystem, amongst them CEN, CA-Browser Forum, OpenID Foundation, Cloud Signature Consortium, ensuring synchronisation of each´s activities. A concrete example is the collaboration with the CEN TC 224 and CEN TC 468 regarding the creation of STS for electronic signatures and electronic archiving. In the context of the EUDI wallet ecosystem creation, the EC is supporting a number of large scale pilots test driving the specifications of EU Digital Identity Wallets in a wide range of use cases. A number of ETSI members are involved in these pilots and information has been exchanged to ensure that this project can make best use of the experience of these pilots. ETSI operates a service for testing interoperability between implementers of ETSI standards referred to ETSI Plugtest. A separately foundered Plugtest is being carried out for the testing the protocols for Electronic Attestation of Attributes being developed in work package 2 (wallets) D2.2, D2.3 and D2.4 (TS 119 472 parts 1 to 3.). Other interoperability and conformance testing that ETSI may provide are to be investigated under work package 9 (testing).

#§COM-PLE-CP§# #§REL-EVA-RE§# #@QUA-LIT-QL@# #@CON-MET-CM@#

## 2. QUALITY

### 2.1 Concept and methodology

As an established ESO, ETSI has a clearly defined procedure of creating STS. This guarantees a reliable and well experienced way of working. For this project four guiding principles are defined to achieve the project´s objectives: - The development of STS will be carried out in correspondence with the EC and the team of experts working on the EU Digital Identity Wallet Architecture and Reference Framework. - The ETSI deliverables are reviewed by members of the ETSI technical committee overseeing the project. - ETSI Plugtests, including separately funded EAA interoperability Plugtests, will be organized to test interoperability and ensure the functioning of the protocols between the EUDI Wallet and external parties including relying parties and trust service providers. - Before the final agreement the most significant deliverables have to be approved by the European National experts through the formal EN Approval Process.

#§CON-MET-CM§# #@CON-SOR-CS@#

### 2.2 Consortium set-up

Not Applicable for ETSI

### 2.3 Project teams, staff and experts

| Project teams and staff |  |  |
| --- | --- | --- |
| Name and function | Organisation | Role/tasks/professional profile and expertise |
| Léa Belloulou Director of Funded Activities | ETSI | Director of ETSI funded Projects planning and control - Management of Funded Activity team - Management of the project costs and funding - Responsible for the Reporting to ETSI Management, Board/General Assembly and EC/EFTA. - Management of audit processes on Funded projects - Management of contractual aspects - Monitoring of the administrative and financial tasks of the projects - Validation of milestones, payments |
| Sofiane Haris Project Manager | ETSI | Project Manager of ETSI funded Projects planning and control - Management of the project costs and funding - Monitoring of the administrative and financial tasks of the projects - Provide support to Milestones follow-up - Consolidate and provide administrative and financial data to EISMEA and EFTA |
| Antoine Burckard Technical Officer | ETSI | ETSI Technical officer for the Technical Committee TC ESI - Act as prime ETSI Secretariat contact for the standardization activity. - Supervise the operation of the standardization activity under the relevant Directives, monitor progress of work programme. - Advise the group on the application of the relevant directives, drafting rules, and common best practice. - Ensure that deliverables are fit for purpose, and in line with the relevant directives, drafting rules and quality recommendations, and accompany them through the drafting and publication phases. - Act as secretary where appropriate, provide official reports of the group's meetings, highlighting actions and decisions. - Ensure that decisions, actions, approval of new work items and deliverables are properly recorded and communicated within the Secretariat. - Monitor activities of other relevant groups, both inside and outside of ETSI and advise of relevant activities as required. - Take appropriate actions to develop and maintain personal expertise in the relevant technical areas, and associated regulatory and market affairs. |
| Nick Pope TC Chair | ETSI | ETSI Chair of the Technical Committee TC ESI With overall responsibility for ensuring that the work plan as identified in this proposal is carried out as agreed and ensures the quality of the deliverables. The chair will promote through open discussion by the committee members, the stakeholders including EU member nations, implementers and service providers. |
| Andrea Röck Iñigo Barriera Arno Fiedler Vice Chairs |  | ETSI Vice-Chairs of the Technical Committee TC ESI Providing back-up in case of unavailability of the chair |

Outside resources (subcontracting, seconded staff, etc)

According to the ETSI Technical working procedure on the selection of the service providers, ETSI will issue a call for expertise to get the necessary skills and resources as described below. A project manager will be appointed from one of the Service Providers and will be responsible for coordinating the execution of the tasks assigned to the individual Service Providers, according to the project requirements and following the technical direction given by ETSI TC ESI. The project Manager (referred to as the STF leader) will possess project management experience, report-writing skills, experience of consensus building, presentations skills, experience of working in an international environment, and in liaising with other international organisations. The project term (referred to as the Specialist Task Force – STF) will be chosen based on: - their experience in developing ETSI technical specification and standards, - their knowledge of the latest techniques for digital identities - specific knowledge of the relevant EU regulations and implementing acts, as well as the EU Digital Identity Architecture and Reference Framework (It is expected that a team of (up to 26) experts will be required for the STF, who will fulfil the role of editor for one or more deliverables as well as carrying out review of deliverables from other experts. Using the ETSI-defined call for expertise and contractor selection process outlined above, the selected experts will begin the project with the preparatory meeting at the end of the second month of the project (M2).

### 2.4 Consortium management and decision-making

Not applicable for ETSI

#§CON-SOR-CS§# #@PRJ-MGT-PM@#

### 2.5 Project management, quality assurance and monitoring and evaluation strategy

A combination of frequent online progress meetings, face-to-face meetings and internal progress reports will create a clear view of the progress. Over and above the management of individual work packages, a lean, yet rigorous management framework linking all project components will be implemented based a formal review process has proven to be the most effective way to ensure a high-quality orientation throughout the project: - the STF leader will monitor progress of all the deliverables against the milestones given in the work plan and provide a report to the TC ESI chair as well as the STF support team. - Drafts of the deliverables will be reviewed by at least one other member of the STF team and feedback provided on the correctness of the deliverable checked against the requirements of applicable regulations and the EUDIW ARF. - When considered ready for approval by the STF firstly by the TC ESI committee the deliverable will be reviewed by the TC ESI Technical Officer and TC ESI members concerned and made available to the EU Commission for review by their experts. - The deliverable will then go through formal approval by TC ESI where any objections and comments missed during earlier review can be raised and corrections made as considered necessary by the committee - If the deliverable is a European Norm (EN) the deliverable will be sent out for a 3 month review by all EU member states through their national standards organisation. During this stage comments and objections can be raised through any EU national standards body. - If the deliverable is an EN and objections or comments are raised a meeting will be held to address all comments. If major technical changes are made to the document then the deliverable will go through a second confirmatory ballot by EU national standards bodies. - The ETSI TC ESI chairs and vice-chairs, and members of the project teams as appropriate, will hold regular meetings, at least monthly, with EU DG Connect to ensure that the work plan and technical solutions are aligned with the objectives of the Commission. A project of this scale, involving over 20 experts, may present significant project management challenges in addition to technical risks. To proactively address these, ETSI has put in place a comprehensive risk management strategy that includes both structural and operational measures. Firstly, the rigorous selection of the STF Leader ensures strong leadership and coordination capabilities. In parallel, the ETSI Secretariat will allocate dedicated resources to support the STF team throughout the project lifecycle: - A Funded Activities Project Manager will be assigned from the outset to oversee project execution, facilitate planning, and ensure early identification and mitigation of risks related to coordination, timelines, and resource allocation. - An ETSI Technical Officer will closely monitor the technical progress and provide guidance to ensure alignment with the expected outcomes. - Dedicated tools will be made available to support collaboration, task tracking, and reporting, thereby enhancing transparency and team coordination. These measures are designed to anticipate and mitigate both strategic and operational risks, ensuring smooth implementation and successful delivery of the project objectives.

#§PRJ-MGT-PM§# #@FIN-MGT-FM@#

### 2.6 Cost effectiveness and financial management

ETSI Secretariat does not have technical experts as staff thus all the EC/EFTA funded projects are subcontracted. For reasons linked to French social Regulations and to avoid a risk of subordinate relationship that could trigger negative consequences for ETSI, on advice of its lawyers, ETSI has abandoned the principle of a daily rate to contract its experts and ETSI works now under the principle of service contracts. The contractor is bound by delivering the agreed service for the price determined. It is the responsibility of the service provider to make available the necessary experts to deliver the expected service. The company contracted may allocate different experts of different seniority and expertise level, having each a different daily rate. Each subcontractor is allocated to specific tasks with an expected level of contribution. The financial resources allocated to the subcontractor are calculated on this principle. At the start of the project, ETSI develops a baseline cost plan. It is calculated with the cost of the tasks and the scheduled progress of task at each milestone cut-off date. This baseline cost plan provides the costs at each milestone cut-off date. The milestone payment schedule for each subcontractor is then calculated considering the baseline cost plan and the expected level of contribution. The milestone payment schedule is contractual. The subcontractors’ payments are submitted to the validation of the project milestones. The TC and ETSI proceed to the validation of the milestone. As the number of person days and the maximum daily rates are requested in the part 0 Introduction, of the EISMEA Call for Proposals, and taking into account the needed expertise, the maximum daily rate is assumed to be 650 EUR and is based on the market price. The estimated effort for all work packages amount to approximatively 2400 days of work spread out over a period of 24 months. Travels are strongly reduced, as teleconferences will be the most common tool for organising technical meetings. Travels are accounted to allow for face-to-face participation in the ETSI Technical Committee and for coordination. ETSI Secretariat ensures that neither the project as a whole nor any part of it have benefited from any other EU Grant thus avoiding any trouble with double funding.

#§FIN-MGT-FM§# #@RSK-MGT-RM@#

### 2.7 Risk management

| Risk No | Description | Work package No | Proposed risk-mitigation measures |
| --- | --- | --- | --- |
| 1 | Not enough experts can be identified or apply to the project with the appropriate skills (see section 2.3 of this proposal). Likelihood Low Impact Medium | WP1 | Proactive identification of potential candidates by ETSI and TC ESI inviting not only ETSI members but other experts with detailed knowledge of the EU Digital Identity Wallet Architecture and Reference Framework (ARF) |
| 2 | Difficulties in the selection process Likelihood Low Impact Medium | WP1 | Clear evaluation criteria list A list of relevant skills, competences and knowledge will be created as a reference to determine the selection of the candidates (including those in section 2.3 of this proposal). The list will support the selection panel in the process and will offer transparency of the decision taken. |
| 3 | Lack of the agreement on the contract issue Likelihood Low Impact Low | WP1 | All STF candidates will have previously applied based on a prior understanding of the STF terms of reference. Case by case evaluation and ad-hoc measures. ETSI will consider any request coming from the contractors and will create specific solutions to meet their needs. |
| 4 | The expert does not accept the appointment Likelihood Low Impact Low | WP1 | All STF candidates will have previously applied based on a prior understanding of the STF terms of reference. |
| 5 | Unacceptable performance level of the experts Likelihood Medium Impact Medium | WP2/3 | Contingency plans - alternative solution All experts are expected to have demonstrate their commitment to standardisation in support of the EU Digital Identity Wallet through previous activities. TC chair, STF lead and ETSI secretariat will support the team to fulfil all the tasks. An expert can be dismissed and replaced if necessary. In addition, the STF will comprise several experts from different providers so remaining experts could take on the work left by the dismissed expert. If needed a new Call for expertise for the remaining task(s) will be opened (respecting ETSI’s selection process detailed in section 2.3 Outside Resources) |
| 6 | Lack of success in the transposition of the project results into the formal Standardisation process Likelihood Low Impact Medium | WP2/3 | Contingency plans (following CEN BOSS rules and ETSI Directives) TB chair and secretariat will support the team in the implementation of the rules. |
| 7 | The regulatory requirements set under eIDAS2 are withdrawn are substantially modified during the legislative procedure Likelihood Low Impact Low | All | The basis for legislation is already set through the EUDIW ARF and committed to by all EU Nations. The planning of the proposal is based on a common plan discussed between ETSI and the EU Commission. This is not under control of the proponents; however, the proposal is meant to produce standardisation deliverables with market involvement that the market players can adopt voluntarily and that will be maintained by the ESOs. |
| 8 | Failure to meet milestone deadlines (medium/high) Likelihood Medium Impact High | All | The project’s tried and tested management methodology and its transparency will naturally flag potential progress-threats very early before they become a problem. This will enable us to respond quickly, via effort re-allocation or re-prioritisation, to any changes or deviations that may affect the plan. |
| 9 | Illness of key members of the STF impact on project Likelihood High Impact High | All | By involvement in more than one STF member in the development of the Deliverables, it is aimed that in case of one individual being unavailable an alternative expert can take their place. The project will plan all meetings with respect to regulations and travel restrictions according to the current status of the pandemic in Europe. Online conferencing will always be available to ensure communication in the consortium. No risks will be taken with regard to meetings and travelling which could lead to COVID related health complications |
| 10 | JTB/TC approval not in line with national requirement Likelihood Low Impact High | All | ESOs are used to strive for consensus and to find compromises to reach approval. As a last resort, for European standards national voting can be used. |
| 11 | Non-alignment of STS with the requirements of the EUDI Wallet national implementations Likelihood Medium Impact Medium | WP8 T8.8 and T8.9 (DG Connect liaison) | Technical solutions are aligned with the EUDI Wallet Architecture and Reference Framework (ARF) and implementing acts based on the ARF. Regular planning and technical focus meetings are held with DG Connect and appointed experts |
| 12 | Non-interoperable implementations based on the STS Likelihood Medium Impact Medium | WP9 | Implementers are invited to participate in separately funded ETSI Plugtests events , including EAA Plugtests, to test interoperability with potential EUDI Wallet relying parties and trust services supporting the EUDI Wallet, |

#§RSK-MGT-RM§# #§QUA-LIT-QL§# #@IMP-ACT-IA@#

## 3. IMPACT

### 3.1 Impact and ambition

The overall aim of developing STS for the European Digital Identity Framework is to achieve interoperable and secure solutions in Europe to create a harmonized ecosystem for secure digital identities and trust services in Europe. In the short term, existing STS can be used as a basis for referencing them in implementing acts or the ARF. In the medium and long term, STS can react to changes more easily and quickly. Which means that changing circumstances do not require an update of the law but an update of the respective standards. The target groups of STS are: - Implementors of the EU Digital Identity Wallet - Relying party system providers that will depend on identities and attributes provided by the EUDI Wallet - Trust service providers supporting the provision of identity and attribute information to the EUDI Wallet - Bodies assessment conformance to standards for trust service and wallet supporting services - By providing a comprehensive and coherent set of STS the project aims to provide the basis for the development of interoperable systems for the above target groups in line with applicable regulatory requirements. ETSI TC ESI has over the last 25 years maintained and built upon existing standards in support of EU Regulations, initially supporting the Electronic Signature Directive 1999/93/EC, and then expanding this in support of the range of trust services as specified in the original eIDAS Regulation EU 910/2014. Following the completion of this proposed work plan, ETSI TC ESI will endeavour to continue ongoing support for its standards including new standardisation for the EUDI Wallet under Regulation EU 2024/1183 amending Regulation EU 910/2014 as covered by this proposal.

#§IMP-ACT-IA§# #@COM-DIS-VIS-CDV@#

### 3.2 Communication, dissemination and visibility

The deliverables, including drafts undergoing EN Approval, will be available for review and comment by all EU nations through their national standardisation bodies. The project will participate in external conferences, events and workshops, and participate in external standardisation fora including: - CA / Browser forum - Cloud Signature Consortium - OpenID Forum - Accredited Conformity Assessment Bodies’ Council (ACAB’c) - Forum of European Supervisory Authorities and Competent Authorities for trust service providers (FESA / ECATS) - Trust Services and eID Forum - CA Day jointly organised with ENISA In addition, the project is to host a joint event with CEN on the EU Digital Identity Framework

#§COM-DIS-VIS-CDV§# #@SUS-CON-SC@#

### 3.3 Sustainability and continuation

Following completion of the project ETSI will continue to maintain its standards as it has done over more than a decade in support of STS for Regulation (EU) 910/2104 ETSI members will continue to support and promote the use of STS developed under this project.

#§SUS-CON-SC§#

#@WRK-PLA-WP@#

## 4. WORKPLAN, WORK PACKAGES, ACTIVITIES, RESOURCES AND TIMING

### 4.1 Work plan

Work plan Provide a brief description of the overall structure of the work plan (list of work packages or graphical presentation (Pert chart or similar)).

The work plan is organised in work packages covering several deliverable related to a common technical objective: WP1) Project management and coordination – ensures the project meets it milestone and produces quality deliverables WP2) Wallets – wallet related standards in line with the architecture and reference framework of the EU Digital Identity Framework including privacy requirements WP3) Certificates – standards supporting public key certificates and timestamps for both the EU Digital Identity Wallet, and eIDAS trust services, WP4) ERDS – standards supporting electronic registered delivery services (ERDS) and the derived registered electronic mail services based on ERDS WP5) Signatures - standards supporting advanced and qualified electronic signatures and seals. WP6) Trust framework – standards supporting audit of trust services as well as trust lists supporting both trust services and wallets WP7) New technology – standards supporting innovative use of the EU Digital Identity Wallet WP8) Consultation and Dissemination – Events and liaison activities disseminating the work of the project and obtaining feedback from stake holders WP9) Testing - Investigation into requirements for conformance testing of wallets The milestones are based on key stages in the development, acceptance and approval of batches of deliverables with timescales within particular constraints: - Batch 2025: Deliverables that are required for before Nov 2025 in joint Gap Analysis and Action Plan - Batch 2026/27-A: Deliverables for 2026/27 that are not directly supporting the EUDI Wallet and so do not need to be delayed until implementation feedback is received (e.g. existing certificate standards, ERDS) - Batch 2026/27-B: Deliverables for 2026/27 that are directly supporting the EUDI Wallet and so need to be delayed until implementation feedback on Batch 2025 deliverables is received. Milestone number; Milestone name; General Description; Timing months. Project start; Contract agreed with ETSI; 1. MS1; STF Kick off; Experts contracted for given tasks; 3. MS2; Batch 2025 confirmation; - Batch 2025 documents publication confirmed - Progress report #1; 5. MS3; Stable drafts batch 2026/27-A; Batch 2026/27-A Stable drafts available; 8. MS4; ETSI TB Approval Batch 2026/27-A Stable drafts batch 2026/27-B; - Batch 2026/27-A - TS approved for publication - Batch 2026/27-A - Draft EN approved for ENAP - Batch 2026/27-B - Stable drafts available - Progress report #2 (to EISMEA); 13. MS5; ETSI TB Approval Batch 2026/27-B; - Batch 2026/27-B - TS approved for publication - Batch 2026/27-B - Draft EN approved for ENAP; 16. MS6; ENAP Comment disposition Batch 2026/27-A; Batch 2026/27-A ENs comment resolution agreed; 18. MS7; ENAP Complete Batch 2026/27-A; - Batch 2026/27-A ENs ballot complete - Progress report #3; 20. MS8; ENAP Comment disposition Batch 2026/27-B; Batch 2026/27-B ENs comment disposition agreed; 21. MS9; ENAP Complete Batch 2026/27-B Project completion; - Batch 2026/27-B ballot complete - Final report; 24.

### 4.2 Work packages, activities, resources and timing

WORK PACKAGES

#### Work Package 1

| Work Package 1: Project management and coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M1- M24 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Ensures the project meets it milestone and produces quality deliverables |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T1.1 | Project Setup |  |  |  |  | ETSI Secretariat will arrange a call for experts. ETSI TC ESI Chair will review the potentials candidates and select those to best meet the workplan, including the assignment of the project leader. ETSI Secretariat will make arrangements for project members (service contracts, etc…) The ETSI TC Chair will check that the objectives of all WPs are clearly recognised by the participants |  |  |  |  | ETSI, TC Chair |  | COO |  | In-kind |
| T1.2 | Project Management |  |  |  |  | The overall management of the project will be under the responsibility of the STF (Specialist Task Force) Leader. He will ensure effective coordination among the different Tasks, working in close collaboration with the different Task Leaders and supervising them if needed, but also with ETSI TC ESI representatives. The overall project management consists in: - Effort 56 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T1.3 | Work package lead |  |  |  |  | Coordination of the development of deliverables in each of the major work packages (Wallets, Certificates, ERDS, Signatures, Trust framework) Effort: 50 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS1 |  | STF Kick off |  | 1 |  |  | ETSI | All activities have started following the selection of experts. |  |  |  | 3 |  | STF member contracts let |  |
| MS2 |  | Batch 2025 confirmation |  | 1 |  |  | ETSI | Progress report #1 |  |  |  | 5 |  | Progress report 1 approved by TC ESI |  |
| MS4 |  | ETSI TB Approval Batch 2026/27-A |  | 1 |  |  | ETSI | Progress report to EISMEA |  |  |  | 13 |  | Annual report to EISMEA approved by TC ESI |  |
| MS7 |  | ENAP Complete Batch 2026/27-A |  | 1 |  |  | ETSI | Progress report #3 |  |  |  | 20 |  | Progress report 3 approved by TC ESI |  |
| MS9 |  | Project completion |  | 1 |  |  | ETSI | Final report |  |  |  | 24 |  | Final report approved by TC ESI, ETSI Secretariat and sent to EISMEA |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D1.1 |  | Progress report #1 |  | 1 |  |  | ETSI | [R — Document, report] |  | PU - Public |  | 5 |  | Initial report covering startup and recognition of batch 2025 deliverables |  |
| D1.2 |  | Progress report #2 to EISMEA |  | 1 |  |  | ETSI | [R — Document, report] |  | SEN — Sensitive |  | 13 |  | Second report covering ETSI TC ESI approval of batch 2026/27-A documents and availability of stable drafts batch 2026/27-B documents |  |
| D1.3 |  | Progress report #3 |  | 1 |  |  | ETSI | [R — Document, report] |  | PU - Public |  | 20 |  | Third report covering ETSI ENAPI approval of batch 2026/27-A documents |  |

#### Work Package 2

| Work Package 2: Wallets and privacy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3 – M24 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - standards in line with the architecture and reference framework of the EU Digital Identity Framework including privacy requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T2.1 | Batch 2025 wallet publication confirmation |  |  |  |  | Confirm publication of: Batch 2025 deliverable for wallet (D2.1 to D2.7) Effort: 280 Days |  |  |  |  | ETSI TC Chair |  | COO |  | Yes, subcontracting |
| T2.2 | Prepare stable drafts Batch 2026/27-B for wallet |  |  |  |  | Prepare stable draft of Batch 2026/27-B-document for TS and ENs (D2.8 to D2.23) Effort: 200 Days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T2.3 | Prepare ETSI TB Approval Batch 2026/27-B for wallet |  |  |  |  | Prepare for TC ESI approval to a) start EN Approval process for D2.8 to D2.14 and D2.17 to D2.23 b) TS Approval of D2.15 and D2.16 Effort 200 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T2.4 | Prepare ENAP comment disposition Batch 2026/27-B wallet |  |  |  |  | Prepare Disposition of comments of ENs for D2.8 to D2.14 and D2.17 to D2.23 Effort 100 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS2 |  | Batch 2025 confirmation |  | 2 |  |  | ETSI | Publication confirmed for D2.1 to D2.7 |  |  |  | 5 |  | ETSI Publication, Work item drafts recorded on ETSI portal, Meeting reports |  |
| MS4 |  | Stable drafts batch 2026/27-B |  | 2 |  |  | ETSI | Stable draft submitted for review to TC ESI (D2.8 to D2.23) |  |  |  | 13 |  | Batch 2026/27-B Stable drafts available |  |
| MS5 |  | ETSI TB Approval Batch 2026/27-B |  | 2 |  |  | ETSI | Draft ENs approved for ENAP for D2.8 to D2.14 and D2.17 to D2.23 TS approved for publication for D2.15 and D2.16 |  |  |  | 16 |  | Record of TB approval either in plenary meeting or via remote consensus |  |
| MS8 |  | ENAP Comment disposition Batch 2026/27-B |  | 2 |  |  | ETSI | Disposition of ENAP comments for D2.8 to D2.14 and D2.17 to D2.23 approved |  |  |  | 21 |  | Record of TB approval of disposition of comments in plenary meeting or via remote consensus |  |
| MS9 |  | Project completion |  | 2 |  |  | ETSI | ENAP complete for D2.8 to D2.14 and D2.17 to D2.23 |  |  |  | 24 |  | EN Ballot portal |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D2.1 |  | TS 119 478 |  | 2 |  |  | ETSI | [R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA ref New 4 (4.2.14) Specification of interfaces related to Authentic Sources |  |
| D2.2 |  | TS 119 471 |  | 2 |  |  | ETSI | [R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA ref New 19 Policy and Security requirements for Providers of Electronic Attestation of Attribute Services |  |
| D2.3 |  | TS 119 472-1 |  | 2 |  |  | ETSI | [R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA ref New 20 General Requirements for profiles for Electronic Attestation of Attributes (EAAs) Note: separately funded ETSI lugtest will be carried out relating EAA to this deliverable which may feed into a later EN version of this standard D2.10. |  |
| D2.4 |  | TS 119 472-2 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA ref New 21 Profiles for EAA - Profiles for EAA/PID Presentations to Relying Party Note: separately funded ETSI Plugtest will be carried out relating to this deliverable which may feed into a later EN version of this standard D2.11. |  |
| D2.5 |  | TS 119 472-3 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA ref New 24 Profiles for EAA - Profiles for Issuance of EAA or PID Note: separately funded ETSI Plugtest will be carried out relating to this deliverable which may feed into a later EN version of this standard D2.12. |  |
| D2.6 |  | TS 119 475 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA ref New 22 Relying party authorisations for access to EUDI Wallet |  |
| D2.7 |  | TR 119 462 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA ref New 22 Wallet interfaces for trust services and signing Wallet interfaces for trust services and signing |  |
| D2.8 |  | EN 319 478 |  | 2 |  |  | ETSI | [R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 4 EN version (4.2.14) Specification of interfaces related to Authentic Sources |  |
| D2.9 |  | EN 319 471 |  | 2 |  |  | ETSI | [R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 19 EN version Policy and Security requirements for Providers of Electronic Attestation of Attribute Services |  |
| D2.10 |  | EN 319 472-1 |  | 2 |  |  | ETSI | [R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 20 EN version General Requirements for profiles for Electronic Attestation of Attributes (EAAs) |  |
| D2.11 |  | EN 319 472-2 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 21 EN version Profiles for EAA - Profiles for EAA/PID Presentations to Relying Party |  |
| D2.12 |  | EN 319 472-3 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 24 EN version Profiles for EAA - Profiles for Issuance of EAA or PID |  |
| D2.13 |  | EN 319 475 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 22 EN version Relying party authorisations for access to EUDI Wallet |  |
| D2.14 |  | EN 319 486 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 1 EN Version Common formats and API for Relying Party Registry information + Common set of Relying Party information to be registered |  |
| D2.15 |  | TS 119 476-2 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 16 |  | Batch 2026/27-B, EISMEA ref New 6 TS version Zero-Knowledge Proof (ZKP) Implementation in EUDI Wallet |  |
| D2.16 |  | TS 119 476-3 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 16 |  | Batch 2026/27-B, EISMEA ref New 10 TS version Wallet Unit Attestation |  |
| D2.17 |  | EN 319 487 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 11 EN version EUDI Wallet Trust Mark |  |
| D2.18 |  | EN 319 482-1 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 12 EN version Additional wallet interfaces - Common interface for lodging complaints to DPAs |  |
| D2.19 |  | EN 319 482-2 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 13 EN version Additional wallet interfaces - common interface for data deletion requests to Relying Parties |  |
| D2.20 |  | EN 319 482-3 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 14 EN Version Additional wallet interfaces - interfaces and formats for the catalogue of Attestation Rulebooks and attributes" |  |
| D2.21 |  | EN 319 482-4 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 15 EN Version Additional wallet interfaces - Specification of Wallet-to-Wallet interactions |  |
| D2.22 |  | EN 319 482-5 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 16 EN Version "Additional wallet interfaces - Specification of systems enabling the notification and subsequent publication of Provider information" |  |
| D2.23 |  | EN 319 482-6 |  | 2 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA ref New 17 EN Version Additional wallet interfaces-- Data Portability and Download (export) |  |

#### Work Package 3

| Work Package 3: Certificates and timestamps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3 – M24 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provision of Standards for - public key certificates for the EU Digital Identity Wallet, - Public key certificate for EU Trust Services eIDAS trust services - Electronic Timestamps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T3.1 | Batch 2025 certificates and timestamps publication confirmation |  |  |  |  | Confirm publication of: Batch 2025 deliverables to certificates and timestamps: D3.1, D3.2, D3.3, D3.4, D3.10, D3.12, D3.14 Effort: 190 days (70 existing + 120 new) |  |  |  |  | ETSI, TC Chair |  | COO |  | Yes, subcontracting |
| T3.2 | Prepare stable drafts Batch 2026/27-A for certificates and timestamps |  |  |  |  | Stable draft of ENs D3.5, D3.6, D3.8, D3.9 Stable draft D3.15 Effort: 45 (35 existing 10 New) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T3.3 | Prepare ETSI TB Approval Batch 2026/27-A for certificates and timestamps |  |  |  |  | Draft for TC ESI approval to start EN Approval process D3.5, D3.6, D3.8, D3.9 Draft TS for TC ESI D3.15 approval Effort: 45 (35 existing New 10) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T3.4 | Prepare ENAP comment disposition Batch 2026/27-A for certificates and timestamps |  |  |  |  | Disposition of comments of ENs D3.5, D3.6, D3.8, D3.9 Effort: 10 (existing) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T3.5 | Prepare stable drafts Batch 2026/27-B for certificates and timestamps |  |  |  |  | Stable draft of ENs D3.11, D3.13 Stable draft D3.7 Effort: 15 (new) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T3.6 | Prepare ETSI TB Approval Batch 2026/27-B for certificates and timestamps |  |  |  |  | Draft for TC ESI approval to start EN Approval process D3.11, D3.13 Effort: 15 (new) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T3.7 | Prepare ENAP comment disposition Batch 2026/27-B for certificates and timestamps |  |  |  |  | Disposition of comments of ENs D3.11 and D3.13 TR for TC ESI D3.7 approval Effort: 10 (new) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS2 |  | Batch 2025 confirmation |  | 3 |  |  | ETSI | Publication confirmed for D3.1, D3.2, D3.3, D3.4, D3.10, D3.12, D3.14 |  |  |  | 5 |  | ETSI Publication, Work item drafts recorded on ETSI portal, Meeting reports |  |
| MS3 |  | Stable drafts batch 2026/27-A |  | 3 |  |  | ETSI | Stable draft submitted for review to TC ESI D3.5, D3.6, D3.8 and D3.9 and D3.15 |  |  |  | 8 |  | Batch 2026/27-A Stable drafts available |  |
| MS4 |  | ETSI TB Approval Batch 2026/27-A Stable drafts batch 2026/27-B |  | 3 |  |  | ETSI | Draft EN approved for ENAP for D3.5, D3.6, D3.8 and D3.9 Draft TS approved for D3.15 Stable draft submitted for review to TC ESI D3.7, D3.11 and D3.13 |  |  |  | 13 |  | Batch 2026/27-A - EN approved for ENAP Batch 2026/27-B Stable drafts available |  |
| MS5 |  | ETSI TB Approval Batch 2026/27-B |  | 3 |  |  | ETSI | Draft EN approved for ENAP for D3.11 and D3.13 Draft TR approved for D3.7 |  |  |  | 16 |  | Record of TB approval either in plenary meeting or portal |  |
| MS6 |  | ENAP Comment disposition Batch 2026/27-A |  | 3 |  |  | ETSI | Disposition of ENAP comments for D3.5, D3.6, D3.8 and D3.9 approved |  |  |  | 18 |  | Batch 2026/27-A ENs comment resolution agreed |  |
| MS7 |  | ENAP Complete Batch 2026/27-A |  | 3 |  |  | ETSI | ENAP Complete for D3.5, D3.6, D3.8 and D3.9 |  |  |  | 20 |  | Batch 2026/27-A ENs ballot complete |  |
| MS8 |  | ENAP Comment disposition Batch 2026/27-B |  | 3 |  |  | ETSI | Disposition of ENAP comments for D3.11 and D3.13 approved |  |  |  | 21 |  | Record of TB approval of disposition of comments in plenary meeting or portal |  |
| MS9 |  | Project completion |  | 3 |  |  | ETSI | ENAP complete for D3.11 and D3.13 |  |  |  | 24 |  | EN Ballot portal, |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D3.1 |  | EN 319 411-2 v2.6.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA Ref existing 12a Policy TSP issuing EU qualified certificates |  |
| D3.2 |  | EN 319 411-1 v1.5.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA Ref existing 12b Policy TSP issuing certificates general |  |
| D3.3 |  | TR 119 411-4 v1.3.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA Ref existing 12c Policy TSP issuing certificates checklist |  |
| D3.4 |  | EN 319 421 v1.3.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA Ref existing 13 Policy TSP issuing Time-stamps |  |
| D3.5 |  | EN 319 411-2 v2.7.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref existing 12a Policy TSP issuing EU qualified certificates |  |
| D3.6 |  | EN 319 411-1 v1.6.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref existing 12b Policy TSP issuing certificates general |  |
| D3.7 |  | TR 119 411-4 v1.4.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA Ref existing 12c Policy TSP issuing certificates checklist |  |
| D3.8 |  | EN 319 421 v1.4.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref existing 13 Policy TSP issuing Time-stamps |  |
| D3.9 |  | EN 319 422 v1.2.1 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref existing 14 Policy TSP issuing Time-stamps |  |
| D3.10 |  | TS 119 411-8 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA new 2 TS Version Common Access CA Certificate Policy |  |
| D3.11 |  | EN 319 411-8 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA Ref new 2 EN Version Common Access CA Certificate Policy |  |
| D3.12 |  | TS 119 412-6 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA Ref new 8 TS Version Certificate Profiles and for Public Sector Issuing Authority signing certificates |  |
| D3.13 |  | EN 319 412-6 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B, EISMEA Ref new 8 EN Version Certificate Profiles and for Public Sector Issuing Authority signing certificates |  |
| D3.14 |  | TR 119 411-9 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025, EISMEA Ref new 29 TR Version Certificate transparency |  |
| D3.15 |  | TS 119 411-9 |  | 3 |  |  | ETSI | /R |  | PU - Public |  | 13 |  | Batch 2026/27-A, EISMEA Ref new 29 TS Version Certificate transparency |  |

#### Work Package 4

| Work Package 4: ERDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3- M20 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Standards supporting electronic registered delivery services (ERDS) and the derived registered electronic mail services based on ERDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T4.1 | Prepare stable drafts Batch 2026/27-A for ERDS |  |  |  |  | Stable draft of ENs D4.1 to D4.7 Effort 48 Days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T4.2 | Prepare ETSI TB Approval Batch 2026/27-A for ERDS |  |  |  |  | Draft for TC ESI approval to start EN Approval process D4.1 to D4.7 Effort: 48 Days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T4.3 | Prepare ENAP comment disposition Batch 2026/27-A for ERDS |  |  |  |  | Disposition of comments of ENs D4.1 to D4.7 Effort 24 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS3 |  | Stable drafts batch 2026/27-A |  | 4 |  |  | ETSI | Stable draft submitted for review to TC ESI D4.1 to D4.7 |  |  |  | 8 |  | Batch 2026/27-A Stable drafts available |  |
| MS4 |  | ETSI TB Approval Batch 2026/27-A |  | 4 |  |  | ETSI | Draft EN approved for ENAP for D4.1 to D4.7 |  |  |  | 13 |  | Batch 2026/27-A - EN approved for ENAP |  |
| MS6 |  | ENAP Comment disposition Batch 2026/27-A |  | 4 |  |  | ETSI | Disposition of ENAP comments for D4.1 to D4.7 |  |  |  | 18 |  | Batch 2026/27-A ENs comment resolution agreed |  |
| MS7 |  | ENAP Complete Batch 2026/27-A |  | 4 |  |  | ETSI | ENAP ballot complete for D4.1 to D4.7 |  |  |  | 20 |  | Batch 2026/27-A ENs ballot complete |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D4.1 |  | EN 319 521 |  | 4 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 19a |  |
| D4.2 |  | EN 319 522-1 |  | 4 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 19b |  |
| D4.3 |  | EN 319 522-2 |  | 4 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 19c |  |
| D4.4 |  | EN 319 522-3 |  | 4 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 19d |  |
| D4.5 |  | EN 319 522-4-1 |  | 4 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 19e |  |
| D4.6 |  | EN 319 522-4-2 |  | 4 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 19f |  |
| D4.7 |  | EN 319 522-4-3 |  | 4 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 19g |  |

#### Work Package 5

| Work Package 5: Signatures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3- M24 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Standards supporting advanced and qualified electronic signatures and seals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T5.1 | Batch 2025 wallet publication confirmation |  |  |  |  | Confirm publication of: Batch 2025 deliverable for wallet (D5.1 to D5.4, D5.15) Effort: 120 Days |  |  |  |  | ETSI, TC Chair |  | COO |  | Yes, subcontracting |
| T5.2 | Prepare stable drafts Batch 2026/27-A for signatures |  |  |  |  | Stable draft of TS / ENs D5.5 to D5.14 Effort 80 Days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T5.3 | Prepare ETSI TB Approval Batch 2026/27-A for Signatures |  |  |  |  | Draft for TC ESI approval to a) start EN Approval process D5.5 to D5.13 b) Approve TS D5.14 Effort: 80 Days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T5.4 | Prepare ENAP comment disposition Batch 2026/27-A for Signatures |  |  |  |  | Disposition of comments of ENs D5.5 to D5.13 Effort 40 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T5.5 | Prepare stable drafts Batch 2026/27-B for signatures |  |  |  |  | Stable draft of ENs D5.16 Effort: 8 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T5.6 | Prepare ETSI TB Approval Batch 2026/27-B for Signatures |  |  |  |  | Draft for TC ESI approval to start EN Approval process D5.16 Effort 8 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T5.7 | Prepare ENAP comment disposition Batch 2026/27-B for Signatures |  |  |  |  | Disposition of comments of ENs D5.16 Effort 4 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS2 |  | Batch 2025 confirmation |  | 5 |  |  | ETSI | D5.1 to D5.4, and D5.15 publication confirmed + Progress report #1 |  |  |  | 5 |  | ETSI Publication, Work item drafts recorded on ETSI portal, Meeting reports |  |
| MS3 |  | Stable drafts batch 2026/27-A |  | 5 |  |  | ETSI | Stable draft submitted for review to TC ESI D5.5 to D5.14 |  |  |  | 8 |  | Batch 2026/27-A Stable drafts available |  |
| MS4 |  | ETSI TB Approval Batch 2026/27-A Stable drafts batch 2026/27-B |  | 5 |  |  | ETSI | Draft EN approved for ENAP for D5.5 to D5.13 Draft TS D5.14 approved Stable draft submitted for review to TC ESI D5.16 |  |  |  | 13 |  | Batch 2026/27-A - TS approved for publication, and EN approved for ENAP Batch 2026/27-B Stable drafts available |  |
| MS5 |  | ETSI TB Approval Batch 2026/27-B |  | 5 |  |  | ETSI | Draft EN approved for ENAP for D5.16 |  |  |  | 16 |  | Record of TB approval either in plenary meeting or via remote consensus |  |
| MS6 |  | ENAP Comment disposition Batch 2026/27-A |  | 5 |  |  | ETSI | Disposition of ENAP comments for D5.5 to D5.13 |  |  |  | 18 |  | Batch 2026/27-A ENs comment resolution agreed |  |
| MS7 |  | ENAP Complete Batch 2026/27-A |  | 5 |  |  | ETSI | ENAP Complete for D5.5 to D5.13 |  |  |  | 20 |  | Batch 2026/27-A ENs ballot complete |  |
| MS8 |  | ENAP Comment disposition Batch 2026/27-B |  | 5 |  |  | ETSI | Disposition of ENAP comments for D5.16 |  |  |  | 21 |  | Batch 2026/27-B ENs comment resolution agreed |  |
| MS9 |  | ENAP Complete Batch 2026/27-B |  | 5 |  |  | ETSI | ENAP complete for D5.16 |  |  |  | 24 |  | Batch 2026/27-B ENs ballot complete |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D5.1 |  | TS 119 432 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 2 Protocols for remote digital signature creation |  |
| D5.2 |  | TS 119 172-4 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 7 Signature applicability rules |  |
| D5.3 |  | TS 119 441 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 16 Policy TSP providing signature validation |  |
| D5.4 |  | TS 119 511 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 18a Long-term preservation with digital signatures Policy |  |
| D5.5 |  | EN 319 432 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref 2 EN version Protocols for remote digital signature creation |  |
| D5.6 |  | EN 319 172-4 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref 7 EN version Signature applicability rules |  |
| D5.7 |  | EN 319 441 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref 16 EN version Policy TSP providing signature validation |  |
| D5.8 |  | EN 319 511 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref 18a EN version Long-term preservation with digital signatures Policy |  |
| D5.9 |  | EN 319 102-1 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 5 EN version Creation and validation of AdES signatures |  |
| D5.10 |  | EN 319 102-2 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 6 EN version Signature validation report |  |
| D5.11 |  | EN 319 431-1 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 15 EN Version Policy TSP services operating a remote QSCD / SCDev |  |
| D5.12 |  | EN 319 182-1 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 21 EN Version JAdES digital signatures; Part 1: Building blocks and JAdES baseline signatures |  |
| D5.13 |  | EN 319 512 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A, EISMEA Ref 18b EN Version Protocols for trust service providers providing long-term data preservation services |  |
| D5.14 |  | TS 119 312 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 13 |  | Batch 2026/27-A, EISMEA Ref 8 TS Version Cryptographic Suites |  |
| D5.15 |  | TS 119 152-1 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 30 TS Version CB-AdES baseline signature |  |
| D5.16 |  | EN 319 152-1 |  | 5 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 226/27-B EISMEA Ref 30 EN Version CB-AdES baseline signature |  |

#### Work Package 6

| Work Package 6: Trust Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3- M24 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| standards supporting audit of trust services as well as trust lists supporting both trust services and wallets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T6.1 | Batch 2025 wallet publication confirmation |  |  |  |  | Confirm publication of: Batch 2025 deliverable for signatures (D6.1, D6.2, D6.3, D6.5, D6.6) Effort 140 (60 existing, 80 new) |  |  |  |  | ETSI, TC Chair |  | COO |  | Yes, subcontracting |
| T6.2 | Prepare stable drafts Batch 2026/27-A for trust framework |  |  |  |  | Stable draft of TS / ENs D6.4, D6.7, D6.8, D6.9, D6.13 Effort 36 (16 existing 20 New) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T6.3 | Prepare ETSI TB Approval Batch 2026/27-A for trust framework |  |  |  |  | Draft for TC ESI approval for - TS D6.4 - to start EN Approval D6.7, D6.8, D6.9, D6.13 Effort: 36 (16 existing 20 New) |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T6.4 | Prepare ENAP comment disposition Batch 2026/27-A for trust framework |  |  |  |  | Disposition of comments of D6.7, D6.8, D6.9, D6.13 Effort 8 existing |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T6.5 | Prepare stable drafts Batch 2026/27-B for trust framework |  |  |  |  | Stable draft of ENs D6.10, D6.11, D6.12 Effort: 16 existing |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T6.6 | Prepare ETSI TB Approval Batch 2026/27-B for trust framework |  |  |  |  | Draft for TC ESI approval to start EN Approval D6.10, D6.11, D6.12 Effort: 16 existing |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T6.7 | Prepare ENAP comment disposition Batch 2026/27-B for trust framework |  |  |  |  | Disposition of comments of D6.10, D6.11, D6.12 Effort 8 Existing |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS2 |  | Batch 2025 confirmation |  | 6 |  |  | ETSI | Confirm publication D6.1, D6.2, D6.3, D6.5, D6.6 |  |  |  | 5 |  | ETSI Publication, Work item drafts recorded on ETSI portal, Meeting reports |  |
| MS3 |  | Stable drafts batch 2026/27-A |  | 6 |  |  | ETSI | Stable draft submitted for review to TC ESI D6.4, D6.7, D6.8, D6.9, D6.13 |  |  |  | 8 |  | Batch 2026/27-A Stable drafts available |  |
| MS4 |  | ETSI TB Approval Batch 2026/27-A Stable drafts batch 2026/27-B |  | 6 |  |  | ETSI | Draft EN approved for ENAP for to start EN Approval D6.7, D6.8, D6.9, D6.13 Draft TS D6.4 approved Stable draft of D6.10, D6.11, D6.12 |  |  |  | 13 |  | Batch 2026/27-A - TS approved for publication, and EN approved for ENAP Batch 2026/27-B Stable drafts available |  |
| MS5 |  | ETSI TB Approval Batch 2026/27-B |  | 6 |  |  | ETSI | Approved for ENAP D6.10, D6.11, D6.12 |  |  |  | 16 |  | Record of TB approval either in plenary meeting or via remote consensus |  |
| MS6 |  | ENAP Comment disposition Batch 2026/27-A |  | 6 |  |  | ETSI | Disposition of ENAP comments for D6.7, D6.8, D6.9, D6.13 |  |  |  | 18 |  | Batch 2026/27-A ENs comment resolution agreed |  |
| MS7 |  | ENAP Complete Batch 2026/27-A |  | 6 |  |  | ETSI | ENAP Complete for D6.7, D6.8, D6.9, D6.13 |  |  |  | 20 |  | Batch 2026/27-A ENs ballot complete |  |
| MS8 |  | ENAP Comment disposition Batch 2026/27-B |  | 6 |  |  | ETSI | ENAP comment disposition D6.10, D6.11, D6.12 |  |  |  | 21 |  | Batch 2026/27-B ENs comment resolution agreed |  |
| MS9 |  | Project completion |  | 6 |  |  | ETSI | ENAP complete for D6.10, D6.11, D6.12 |  |  |  | 24 |  |  |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D6.1 |  | TS 119 612 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 4 Trusted Lists |  |
| D6.2 |  | TS 119 615 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 20 Procedures for using EU national trusted lists |  |
| D6.3 |  | TS 119 602 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref New 28 Trust lists general data model |  |
| D6.4 |  | TS 119 605 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 13 |  | Batch 2026/27-A EISMEA Ref New 26 TS version Processing trusted lists and trusted list content |  |
| D6.5 |  | TS 119 461 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 17 Identity proofing |  |
| D6.6 |  | EN 319 401 v3.2.1 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 5 |  | Batch 2025 EISMEA Ref 9 General Policy Requirements for Trust Service Providers |  |
| D6.7 |  | EN 319 403-1 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref 10 TSP Conformity assessment |  |
| D6.8 |  | EN 319 403-3 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref 11 TSP Conformity assessment - EU Qualified |  |
| D6.9 |  | EN 319 461 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref 11 EN Version Identity proofing |  |
| D6.10 |  | EN 319 401 v3.3.1 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B EISMEA Ref 9 General Policy Requirements for Trust Service Providers |  |
| D6.11 |  | EN 319 612 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B EISMEA Ref 4 EN Version Trusted Lists |  |
| D6.12 |  | EN 319 615 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 24 |  | Batch 2026/27-B EISMEA Ref 20 EN Version Procedures for using EU national trusted lists |  |
| D6.13 |  | EN 319 602 |  | 6 |  |  | ETSI | /R |  | PU - Public |  | 20 |  | Batch 2026/27-A EISMEA Ref New 28 Trust lists general data model |  |

#### Work Package 7

| Work Package 7: New technology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3- M13 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Standards supporting innovative use of the EU Digital Identity Wallet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T7.1 | Prepare stable drafts Batch 2026/27-A for New technology |  |  |  |  | Stable draft of D7.1, D7.2, Effort 40 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T7.2 | Prepare ETSI TB Approval Batch 2026/27-A for new technology |  |  |  |  | Draft for TC ESI approval D7.1, D7.2, Effort: 40 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS3 |  | Stable drafts batch 2026/27-A |  | 7 |  |  | ETSI | Stable draft submitted for review to TC ESI D7.1, D7.2 |  |  |  | 8 |  | Batch 2026/27-A Stable drafts available |  |
| MS4 |  | ETSI TB Approval Batch 2026/27-A |  | 7 |  |  | ETSI | D7.1, D7.2 approved for publication |  |  |  | 13 |  | Batch 2026/27-A - TS approved for publication |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D7.1 |  | TS 119 479-2 |  | 7 |  |  | ETSI | /R |  | PU - Public |  | 13 |  | Batch 2026/27-A EISMEA Ref New 27 EAA Extended Validation Services Framework and Application |  |
| D7.2 |  | TS 119 479-3 |  | 7 |  |  | ETSI | /R |  | PU - Public |  | 13 |  | Batch 2026/27-A EISMEA Ref New 28 EAA within ADES |  |

#### Work Package 8

| Work Package 8: Consultation and Dissemination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3- M24 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Workshops and liaison activities disseminating the work of the project and obtaining feedback from stake holders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T8.1 | Certificate Authority Workshop - hosting |  |  |  |  | Preparation of agenda and hosting arrangements. Involving 4 coordination meetings to review of agenda involving 5 STF experts presenting. Effort: 10 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.2 | Certificate Authority Workshop - presentations |  |  |  |  | 3 days preparation of slides and 1 day presentation by 5 STF experts Effort: 20 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.3 | ERDS Workshop - hosting |  |  |  |  | Preparation of agenda and hosting arrangements Involving 4 coordination meetings to review of agenda involving 5 STF experts presenting. Effort: 10 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.4 | ERDS Workshop - presentations |  |  |  |  | 3 days preparation of slides and 1 day presentation by 5 STF experts Effort 20 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.5 | EUDI Wallet Workshop - hosting |  |  |  |  | Preparation of agenda and hosting arrangements Involving 4 coordination meetings to review of agenda involving 5 STF experts presenting. Effort 10 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.6 | EUDI Wallet Workshop – presentation |  |  |  |  | 3 days preparation of slides and 1 day presentation by 5 STF experts, plus further 10 days to review external presentations from partner organisations (CEN, OpenID foundation, Cloud Signature Consortium). Effort 30 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.7 | Dissemination of results and External liaison |  |  |  |  | The STF members will actively promote the work of the STF in external conferences and media. This includes ETSI TC ESI existing news email list. Also, STF members will participate in fora involving stakeholders in regulating, implementing and using the EUDI Wallet. joint meetings will be held with external standards organisations concerned with supporting non-EU specific wallet related functions as referenced in EUDI Wallet standards including CA/Browser Forum, Cloud Signature Consortium and OpenID Forum Effort 40 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.8 | Liaison with EU DG Connect 2025 |  |  |  |  | Monthly touchpoint meetings and technical coordination 2025 Effort 72: days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| T8.9 | Liaison with EU DG Connect 2026 / 27 |  |  |  |  | Monthly touchpoint meetings and technical coordination 2026/27 Effort 72 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS6 |  | All eventss held |  | 8 |  |  | ETSI | Certificate authority, ERDS and EUDI Wallet Workshops successfully completed (Scheduling of events to be decided shortly after kick off) |  |  |  | 18 |  |  |  |
| MS9 |  |  |  | 8 |  |  | ETSI | DG Connect meeting minutes |  |  |  | 24 |  |  |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D8.1 |  | Certification Authority event Agenda |  | 8 |  |  | ETSI | /R |  | PU - Public |  | 18 |  | Certification Authority event Agenda |  |
| D8.2 |  | Certification Authority event Presentations |  | 8 |  |  | ETSI | /R |  | PU - Public |  | 18 |  | Certification Authority event Set of presentations |  |
| D8.3 |  | ERDS Agenda |  | 8 |  |  | ETSI | /R |  | PU - Public |  | 18 |  | ERDS Agenda |  |
| D8.4 |  | ERDS Presentations |  | 8 |  |  | ETSI | /R |  | PU - Public |  | 18 |  | ERDS Presentations |  |
| D8.5 |  | EUDI Event Agenda |  | 8 |  |  | ETSI | /R |  | PU - Public |  | 16 |  | EUDI Workshop Agenda |  |
| D8.6 |  | EUDI Event Presentations |  | 8 |  |  | ETSI | /R |  | PU - Public |  | 18 |  | EUDI Workshop Presentations |  |
| D8.7 |  | Liaison meeting reports |  | 8 |  |  | ETSI | /R |  | SEN - Sensitive |  | 18 |  | Reports of liaison meetings |  |
| D8.8 |  | DG Connect meeting minutes 2025 |  | 8 |  |  | ETSI | /R |  | SEN - Sensitive |  | 5 |  | DG Connect meeting minutes |  |
| D8.9 |  | DG Connect meeting minutes Batch 2026/27 |  | 8 |  |  | ETSI | /R |  | SEN - Sensitive |  | 24 |  | DG Connect meeting minutes |  |
| D8.10 |  | Dissemination report |  | 8 |  |  | ETSI | /R |  | SEN - Sensitive |  | 24 |  | Dissemination report |  |

#### Work Package 9

| Work Package 9: Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M3 – M16 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Investigation into requirements for conformance and Interoperability testing of wallets This document presents an analysis of the methods for testing and validating the technologies and protocols associated with the various interfaces and reference points within the complete EUDIW system. The proposed testing framework outlined herein is intended to guide the development of conformance and interoperability testing strategies, test systems, and the corresponding test specifications for EUDIW. The framework will be based on the well-established ETSI Testing Methodology, which follows ISO/IEC 9646 standards and has been successfully applied for many years in various ETSI and 3GPP testing initiatives. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No | Task Name |  |  |  |  | Description |  |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T9.1 | Testing framework study |  |  |  |  | Study on requirements for conformance and interoperability testing in of EUDI Wallet that could be met by ETSI Conformance and Interoperability Testing services 100 days |  |  |  |  | ETSI |  | COO |  | Yes, subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  |  | Due Date (month number) |  | Means of Verification |  |
| MS5 |  | Testing framework study |  | 9 |  |  | ETSI | Study report on the requirements for conformance and interoperability testing of EUDI Wallet |  |  |  | 16 |  | Submission of study report to TC ESI for approval |  |
| Deliverable No (continuous numbering linked to WP) |  | Deliverable Name |  | Work Package No |  |  | Lead Beneficiary | Type |  | Dissemination Level |  | Due Date (month number) |  | Description (including format and language) |  |
| D9.1 |  | Testing framework study |  | 9 |  |  | ETSI | [R |  | PU - Public |  | 15 |  | Study report on the requirements for conformance and interoperability testing of EUDI Wallet |  |

## Total Project costs

#### 4.3 Subcontracting

| Work Package No | Subcontract No (continuous numbering linked to WP) | Subcontract Name (subcontracted action tasks) | Description (including task number and BEN/AE to which it is linked) |  | Estimated Costs (EUR) | Justification (why is subcontracting necessary?) | Best-Value-for-Money (how do you intend to ensure it?) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1-9 | NA | NA | Task 1.1 to T9.1 |  | 1 608 000 | Expertise not available in ETSI Secretariat | Subcontractors are selected on a case-by-case basis in the context of an open call through a clearly defined process (typically one or more of the following, publication of the call through ETSI Collective letters (see section 2.3 above) to the membership, Technical Body mailing lists or explicit calls for tender). Travel costs are included in the subcontracting cost. |
| Other issues: If subcontracting for the project goes beyond 30% of the total eligible costs, give specific reasons. |  |  |  | Each subcontractor/expert is allocated to specific tasks with an expected level of contribution. The financial resources allocated to the subcontractor are calculated on this principle. For reasons linked to French social Regulations and to avoid a risk of subordinate relationship that could trigger negative consequences for ETSI, on advice of its lawyers, ETSI has abandoned the principle of a daily rate to contract its experts and ETSI works now under the principle of service contracts. ETSI Secretariat (Funded Activities, Technical officers…) will ensure the project planning and controlling with the Technical Committee without charging the related costs to the project, as the EC funds ETSI through an Operating Grant, whereas subcontractors will perform the development and technical execution of the project. ETSI Secretariat has no expert as staff thus all tasks are subcontracted. Besides the technical project management (WP1) will be handled by the selected subcontractor as Project Leader to ensure the technical tasks execution and quality by the other subcontractors. |  |  |  |

#### Timetable

| ACTIVITY |  | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12 | M 13 | M 14 | M 15 | M 16 | M 17 | M 18 | M 19 | M 20 | M 21 | M 22 | M 23 | M 24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task 1.1 - … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 1.2 - … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 1.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2.1 Batch 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2.2 Batch 2026/27-B (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2.3 Batch 2026/27-B (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2.4 Batch 2026/27-B (ENAP Comment) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.1 Batch 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.2 Batch 2026/27-A (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.3 Batch 2026/27-A (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.4 Batch 2026/27-A (ENAP Comments) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.5 Batch 2026/27-B (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.6 Batch 2026/27-B (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.7 Batch 2026/27-B (ENAP Comment) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 4.1 Batch 2026/27-A (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 4.2 Batch 2026/27-A (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 4.3 Batch 2026/27-A (ENAP Comments) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5.1 Batch 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5.2 Batch 2026/27-A (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5.3 Batch 2026/27-A (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5.4 Batch 2026/27-A (ENAP Comments) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5.5 Batch 2026/27-B (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5.6 Batch 2026/27-B (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 5.7 Batch 2026/27-B (ENAP Comment) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6.1 Batch 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6.2 Batch 2026/27-A (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6.3 Batch 2026/27-A (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6.4 Batch 2026/27-A (ENAP Comments) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6.5 Batch 2026/27-B (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6.6 Batch 2026/27-B (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 6.7 Batch 2026/27-B (ENAP Comment) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 7.1 Batch 2026/27-A (Stable draft) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 7.2 Batch 2026/27-A (TB Approve) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 8.1 – 8.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 8.7 to 8.9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 9.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

#§WRK-PLA-WP§#

#@ETH-ICS-EI@#

## 5. OTHER

### 5.1 Ethics

Ethics

Not applicable.

#§ETH-ICS-EI§# #@SEC-URI-SU@#

### 5.2 Security

Security

Not applicable.

#§SEC-URI-SU§# #@DEC-LAR-DL@#

## 6. DECLARATIONS

| Double funding |  |
| --- | --- |
| Information concerning other EU grants for this project Please note that there is a strict prohibition of double funding from the EU budget (except under EU Synergies actions). | YES/NO |
| We confirm that to our best knowledge neither the project as a whole nor any parts of it have benefitted from any other EU grant (including EU funding managed by authorities in EU Member States or other funding bodies, e.g. EU Regional Funds, EU Agricultural Funds, etc). If NO, explain and provide details. | YES |
| We confirm that to our best knowledge neither the project as a whole nor any parts of it are (nor will be) submitted for any other EU grant (including EU funding managed by authorities in EU Member States or other funding bodies, e.g. EU Regional Funds, EU Agricultural Funds, etc). If NO, explain and provide details. | YES |

Financial support to third parties (if applicable) If in your project the maximum amount per third party will be more than the threshold amount set in the Call document, justify and explain why the higher amount is necessary in order to fulfil your project’s objectives.

Not applicable.

#§DEC-LAR-DL§#

Annex I	Response to the Request for Proposals
CfE – STF 705 (REFERENCE BODY ESI)

Deadline: 17 November 2025

If you are an ETSI Member *

ETSI membership status (Indicate your status):

 Full

 Associate

 Observer

If you are not an ETSI Member *

Please indicate:

Full name of the ETSI member supporting the application (list of ETSI members on etsi.org):

-________________________

Official contact name of the ETSI member supporting the application:

-________________________

Note: A formal confirmation of the support from the Official contact is required (e.g. by e-mail sent to STFLINK@etsi.org) and an “ETSI Member Support Letter” will be required if you are selected.

| Contractor information * |  |  |  |
| --- | --- | --- | --- |
| Contractor name *: Indicate the Company/Organisation Name |  |  |  |
| Contact person for the technical aspects |  | Contact person for Decision on ETSI financial offer to this project (if any) |  |
| Title |  | Title |  |
| First name |  | First name |  |
| Last name |  | Last name |  |
| Role |  | Role |  |
| e-mail |  | e-mail |  |
| Phone |  | Phone |  |

|  | Yes | No |
| --- | --- | --- |
| Do you or any employee of your Company/Organisation hold an elected or appointed position in the Reference Body requesting the STF 705 creation? | o Indicate in which position: ----------------------------------- | o |
| If you are self-employed candidate: Do you currently have other contracts in progress with ETSI? | o | o |

All fields marked with an asterix (*) are mandatory

1.1	Introduction

A short presentation of the technical structure responsible for this activity, e.g.:

- Business area, number of employees, link to WEB site,

- Department(s)/team(s)/experts in charge of the technical activities related to this Project,

- Reference to products/services of your Company/Organisation or supporting Member to which the standards developed by this Project will apply,

- Motivation for your Company/Organisation or supporting Member to participate in this Project.

1.2	Proposed approach

1.2.1 Proposed Deliverables

In the following table indicate the % level of contribution proposed for each deliverable with a work package. For example:

- Rapporteur 	50%

- Major contributor	20%

- Reviewer		10%

Your company may contribute to more than one deliverable. Final assignments will be confirmed during the shortlist and preparatory meeting.

Information on deliverables can be found at: https://portal.etsi.org/xtfs/#/xTF/705/deliverables

Rapporteurs of Batch 2025 tasks may discuss with those who have submitted contributions to a deliverable, the equitable division of the % effort allocated to the relevant task for the 2025 deliverables.

Please provide the % level of contribution for each deliverable in the following table:

| WP# | Deliverable N° | Deliverable name | Identify the % level of contribution to Deliverable | For information: Tasks linked to each deliverable, for which you must indicate the percentage of coverage in Table section 1.2.2. | Batch | Indicative maximum expected effort per task for the selected deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| WP2 | D2.1 | TS 119 478 |  | T2.1 | 2025 | 40 |
|  | D2.8 | EN 319 478 |  | T2.2 | 26/27-B | 7,62 |
|  |  |  |  | T2.3 |  | 7,62 |
|  |  |  |  | T2.4 |  | 4,76 |
|  | D2.2 | TS 119 471 |  | T2.1 | 2025 | 40 |
|  | D2.9 | EN 319 471 |  | T2.2 | 26/27-B | 7,62 |
|  |  |  |  | T2.3 |  | 7,62 |
|  |  |  |  | T2.4 |  | 4,76 |
|  | D2.3 | TS 119 472-1 |  | T2.1 | 2025 | 40 |
|  | D2.10 | EN 319 472-1 |  | T2.2 | 26/27-B | 7,62 |
|  |  |  |  | T2.3 |  | 7,62 |
|  |  |  |  | T2.4 |  | 4,76 |
|  | D2.4 | TS 119 472-2 |  | T2.1 | 2025 | 40 |
|  | D2.11 | EN 319 472-2 |  | T2.2 | 26/27-B | 7,62 |
|  |  |  |  | T2.3 |  | 7,62 |
|  |  |  |  | T2.4 |  | 4,76 |
|  | D2.5 | TS 119 472-3 |  | T2.1 | 2025 | 40 |
|  | D2.12 | EN 319 472-3 |  | T2.2 | 26/27-B | 7,62 |
|  |  |  |  | T2.3 |  | 7,62 |
|  |  |  |  | T2.4 |  | 4,76 |
|  | D2.6 | TS 119 475 |  | T2.1 | 2025 | 40 |
|  | D2.13 | EN 319 475 |  | T2.2 | 26/27-B | 7,62 |
|  |  |  |  | T2.3 |  | 7,62 |
|  |  |  |  | T2.4 |  | 4,76 |
|  | D2.7 | TR 119 462 |  | T2.1 | 2025 | 40 |
|  | D2.14 | EN 319 486 |  | T2.2 | 26/27-B | 15,24 |
|  |  |  |  | T2.3 |  | 15,24 |
|  |  |  |  | T2.4 |  | 9,52 |
|  | D2.15 | TS 119 476-2 |  | T2.2 | 26/27-B | 20 |
|  |  |  |  | T2.3 |  | 20 |
|  | D2.16 | TS 119 476-3 |  | T2.2 | 26/27-B | 20 |
|  |  |  |  | T2.3 |  | 20 |

| WP# | Deliverable N° | Deliverable name | Identify the % level of contribution to Deliverable | For information: Tasks linked to each deliverable, for which you must indicate the percentage of coverage in Table section 1.2.2. | Batch | Indicative maximum expected effort per task for the selected deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| WP2 (cont.) | D2.17 | EN 319 487 |  | T2.2 | 26/27-B | 7,62 |
|  |  |  |  | T2.3 |  | 7,62 |
|  |  |  |  | T2.4 |  | 4,76 |
|  | D2.18 | EN 319 482-1 |  | T2.2 | 26/27-B | 15,24 |
|  |  |  |  | T2.3 |  | 15,24 |
|  |  |  |  | T2.4 |  | 9,52 |
|  | D2.19 | EN 319 482-2 |  | T2.2 | 26/27-B | 15,24 |
|  |  |  |  | T2.3 |  | 15,24 |
|  |  |  |  | T2.4 |  | 9,52 |
|  | D2.20 | EN 319 482-3 |  | T2.2 | 26/27-B | 15,24 |
|  |  |  |  | T2.3 |  | 15,24 |
|  |  |  |  | T2.4 |  | 9,52 |
|  | D2.21 | EN 319 482-4 |  | T2.2 | 26/27-B | 15,24 |
|  |  |  |  | T2.3 |  | 15,24 |
|  |  |  |  | T2.4 |  | 9,52 |
|  | D2.22 | EN 319 482-5 |  | T2.2 | 26/27-B | 15,24 |
|  |  |  |  | T2.3 |  | 15,24 |
|  |  |  |  | T2.4 |  | 9,52 |
|  | D2.23 | EN 319 482-6 |  | T2.2 | 26/27-B | 15,24 |
|  |  |  |  | T2.3 |  | 15,24 |
|  |  |  |  | T2.4 |  | 9,52 |

| WP# | Deliverable N° | Deliverable name | Identify the % level of contribution to Deliverable | For information: Tasks linked to each deliverable, for which you must indicate the percentage of coverage in Table section 1.2.2. | Batch | Indicative maximum expected effort per task for the selected deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| WP3 | D3.1 | EN 319 411-2 v2.6.1 |  | T3.1 | 2025 | 20 |
|  | D3.5 | EN 319 411-2 v2.7.1 |  | T3.2 | 26/27-A | 8,75 |
|  |  |  |  | T3.3 |  | 8,75 |
|  |  |  |  | T3.4 |  | 2,5 |
|  | D3.2 | EN 319 411-1 v1.5.1 |  | T3.1 | 2025 | 20 |
|  | D3.6 | EN 319 411-1 v1.6.1 |  | T3.2 | 26/27-A | 8,75 |
|  |  |  |  | T3.3 |  | 8,75 |
|  |  |  |  | T3.4 |  | 2,5 |
|  | D3.3 | TR 119 411-4 v1.3.1 |  | T3.1 | 2025 | 10 |
|  | D3.7 | TR 119 411-4 v1.4.1 |  | T3.5 | 26/27-B | 4 |
|  |  |  |  | T3.7 |  | 4 |
|  | D3.4 | EN 319 421 v1.3.1 |  | T3.1 | 2025 | 20 |
|  | D3.8 | EN 319 421 v1.4.1 |  | T3.2 | 26/27-A | 8,75 |
|  |  |  |  | T3.3 |  | 8,75 |
|  |  |  |  | T3.4 |  | 2,5 |
|  | D3.9 | EN 319 422 v1.2.1 |  | T3.2 | 26/27-A | 8,75 |
|  |  |  |  | T3.3 |  | 8,75 |
|  |  |  |  | T3.4 |  | 2,5 |
|  | D3.10 | TS 119 411-8 |  | T3.1 | 2025 | 40 |
|  | D3.11 | EN 319 411-8 |  | T3.5 | 26/27-B | 5,5 |
|  |  |  |  | T3.6 |  | 7,5 |
|  |  |  |  | T3.7 |  | 3 |
|  | D3.12 | TS 119 412-6 |  | T3.1 | 2025 | 40 |
|  | D3.13 | EN 319 412-6 |  | T3.5 | 26/27-B | 5,5 |
|  |  |  |  | T3.6 |  | 7,5 |
|  |  |  |  | T3.7 |  | 3 |
|  | D3.14 | TR 119 411-9 |  | T3.1 | 2025 | 40 |
|  | D3.15 | TS 119 411-9 |  | T3.2 | 26/27-A | 10 |
|  |  |  |  | T3.3 |  | 10 |

| WP# | Deliverable N° | Deliverable name | Identify the % level of contribution to Deliverable | For information: Tasks linked to each deliverable, for which you must indicate the percentage of coverage in Table section 1.2.2. | Batch | Indicative maximum expected effort per task for the selected deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| WP4 | D4.1 | EN 319 521 |  | T4.1 | 26/27-A | 6,86 |
|  |  |  |  | T4.2 |  | 6,86 |
|  |  |  |  | T4.3 |  | 3,43 |
|  | D4.2 | EN 319 522-1 |  | T4.1 | 26/27-A | 6,86 |
|  |  |  |  | T4.2 |  | 6,86 |
|  |  |  |  | T4.3 |  | 3,43 |
|  | D4.3 | EN 319 522-2 |  | T4.1 | 26/27-A | 6,86 |
|  |  |  |  | T4.2 |  | 6,86 |
|  |  |  |  | T4.3 |  | 3,43 |
|  | D4.4 | EN 319 522-3 |  | T4.1 | 26/27-A | 6,86 |
|  |  |  |  | T4.2 |  | 6,86 |
|  |  |  |  | T4.3 |  | 3,43 |
|  | D4.5 | EN 319 522-4-1 |  | T4.1 | 26/27-A | 6,86 |
|  |  |  |  | T4.2 |  | 6,86 |
|  |  |  |  | T4.3 |  | 3,43 |
|  | D4.6 | EN 319 522-4-2 |  | T4.1 | 26/27-A | 6,86 |
|  |  |  |  | T4.2 |  | 6,86 |
|  |  |  |  | T4.3 |  | 3,43 |
|  | D4.7 | EN 319 522-4-3 |  | T4.1 | 26/27-A | 6,86 |
|  |  |  |  | T4.2 |  | 6,86 |
|  |  |  |  | T4.3 |  | 3,43 |

| WP# | Deliverable N° | Deliverable name | Identify the % level of contribution to Deliverable | For information: Tasks linked to each deliverable, for which you must indicate the percentage of coverage in Table section 1.2.2. | Batch | Indicative maximum expected effort per task for the selected deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| WP5 | D5.1 | TS 119 432 |  | T5.1 | 2025 | 20 |
|  | D5.5 | EN 319 432 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.2 | TS 119 172-4 |  | T5.1 | 2025 | 20 |
|  | D5.6 | EN 319 172-4 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.3 | TS 119 441 |  | T5.1 | 2025 | 20 |
|  | D5.7 | EN 319 441 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.4 | TS 119 511 |  | T5.1 | 2025 | 20 |
|  | D5.8 | EN 319 511 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.9 | EN 319 102-1 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.10 | EN 319 102-2 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.11 | EN 319 431-1 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.12 | EN 319 182-1 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.13 | EN 319 512 |  | T5.2 | 26/27-A | 7,78 |
|  |  |  |  | T5.3 |  | 7,78 |
|  |  |  |  | T5.4 |  | 4,44 |
|  | D5.14 | TS 119 312 |  | T5.2 | 26/27-A | 10 |
|  |  |  |  | T5.3 |  | 10 |
|  | D5.15 | TS 119 152-1 |  | T5.1 | 2025 | 40 |
|  | D5.16 | EN 319 152-1 |  | T5.5 | 26/27-B | 8 |
|  |  |  |  | T5.6 |  | 8 |
|  |  |  |  | T5.7 |  | 4 |

| WP# | Deliverable N° | Deliverable name | Identify the % level of contribution to Deliverable | For information: Tasks linked to each deliverable, for which you must indicate the percentage of coverage in Table section 1.2.2. | Batch | Indicative maximum expected effort per task for the selected deliverable |
| --- | --- | --- | --- | --- | --- | --- |
| WP6 | D6.1 | TS 119 612 |  | T6.1 | 2025 | 0 |
|  | D6.11 | EN 319 612 |  | T6.5 | 26/27-B | 5,33 |
|  |  |  |  | T6.6 |  | 5,33 |
|  |  |  |  | T6.7 |  | 2,66 |
|  | D6.2 | TS 119 615 |  | T6.1 | 2025 | 20 |
|  | D6.12 | EN 319 615 |  | T6.5 | 26/27-B | 5,33 |
|  |  |  |  | T6.6 |  | 5,33 |
|  |  |  |  | T6.7 |  | 2,66 |
|  | D6.3 | TS 119 602 |  | T6.1 | 2025 | 80 |
|  | D6.13 | EN 319 602 |  | T6.2 | 26/27-A | 6 |
|  |  |  |  | T6.3 |  | 6 |
|  |  |  |  | T6.4 |  | 2 |
|  | D6.4 | TS 119 605 |  | T6.2 | 26/27-A | 12 |
|  |  |  |  | T6.3 |  | 12 |
|  | D6.5 | TS 119 461 |  | T6.1 | 2025 | 20 |
|  | D6.9 | EN 319 461 |  | T6.2 | 26/27-A | 6 |
|  |  |  |  | T6.3 |  | 6 |
|  |  |  |  | T6.4 |  | 2 |
|  | D6.6 | EN 319 401 v3.2.1 |  | T6.1 | 2025 | 20 |
|  | D6.10 | EN 319 401 v3.3.1 |  | T6.5 | 26/27-B | 5,33 |
|  |  |  |  | T6.6 |  | 5,33 |
|  |  |  |  | T6.7 |  | 2,66 |
|  | D6.7 | EN 319 403-1 |  | T6.2 | 26/27-A | 6 |
|  |  |  |  | T6.3 |  | 6 |
|  |  |  |  | T6.4 |  | 2 |
|  | D6.8 | EN 319 403-3 |  | T6.2 | 26/27-A | 6 |
|  |  |  |  | T6.3 |  | 6 |
|  |  |  |  | T6.4 |  | 2 |
| WP7 | D7.1 | TS 119 479-2 |  | T7.1 | 26/27-A | 20 |
|  |  |  |  | T7.2 |  | 20 |
|  | D7.2 | TS 119 479-3 |  | T7.1 | 26/27-A | 20 |
|  |  |  |  | T7.2 |  | 20 |
| WP9 | D9.1 | Testing framework study |  | T9.1 | 26/27-B | 100 |

1.2.2 Calculation of proposed contribution to tasks and related cost for deliverables contribution

Given the % level of contribution indicated in the above table calculate the contribution to be made to each task T2.1 to T7.2 and T9.1 as follows:

- For each deliverable for a task, calculate (the allocated effort) * (% level of contribution/100)

- For each task sum the values for related deliverables as calculated in (a) above

- Multiply the total task effort by daily rate of 650 €

- Put calculated Amount in Euro in the table below

- Calculate % of whole task as Amount in Euro / Max budget allocated

Example: If an expert works on D2.2 with a 50% level of contribution (as rapporteur), on D2.13 with a 20% level of contribution (as major contributor), and on D2.19 with a 10% level of contribution (as reviewer), then:

D2.2 is part of T2.1, so contribution to T2.1 is there of 50% of 40 days, i.e. 20 days

D2.13 is part of T2.2, so contribution to T2.2 is there of 20% of 7,62 days, i.e. 1,52 days

D2.13 is part of T2.3, so contribution to T2.3 is there of 20% of 7,62 days, i.e. 1,52 days

D2.13 is part of T2.4, so contribution to T2.4 is there of 20% of 4,76 days, i.e. 0,95 days

D2.19 is part of T2.2, so contribution to T2.2 is there of 10% of 15,24 days, i.e. 1,52 days

D2.19 is part of T2.3, so contribution to T2.3 is there of 10% of 15,24 days, i.e. 1,52 days

D2.19 is part of T2.4, so contribution to T2.4 is there of 10% of 9,52 days, i.e. 0,95 days

So the contribution to T2.1 is 20 x 650 = 13 000 €, which is 7,14% of task T2.1.

And the contribution to T2.2 is (1,52 + 1,52)  x 650 = 1976 €, which is 1,5% of task T2.2.

And the contribution to T2.3 is (1,52 + 1,52)  x 650 = 1976 €, which is 1,5% of task T2.3.

And the contribution to T2.4 is (0,95 + 0,95)  x 650 = 1235 €, which is 1,9% of task T2.4.

For task T1.2 offer the full amount if contributing as the STF leader who will be responsible for coordination across the STF and production of progress reports supported by WP leader.

For task T1.3 if contributing as work package leader, offer the percentage for the work packed leading as follows:

- WP2+WP7 lead (Both WPs to be managed together): 25%

- WP3 lead: 15%

- WP4 lead: 15%

- WP5 lead: 15%

- WP6 lead: 15%

- WP9 lead: 15%

For task T8.1, T8.3, T8.5, each of the STF leader and relevant WP leaders to contribute 15% of allocation to assist in the organisation of the workshops.

For tasks T8.2, T8.4 and T8.6, experts working as rapporteurs to contribute to presentations as a proportion of the number of deliverables under the relevant work packages.

Relevant WPs for T8.1 to T8.6

- T8.1, T8.2: (CA_Day): WP2+WP7, WP3, WP5, WP6, WP9

- T8.3, T8.4 (ERDS): WP4

- T8.5, T8.6 (Wallet): WP2+WP7, WP3 WP6, WP9

For T8.7 allocated for each of STF Lead (16%) and WP leaders (14% each) if offered under task 1.3.

For task T8.8, allocated by % of EC Engagement technical touchpoint meetings attended in 2025.

For task T8.9, allocated to experts attending EC Engagement technical touchpoint meetings in 2026/2027 [expected STF lead (20%) and WP leaders (10% each)].

Provide the calculated contribution in Euro for tasks to which your Company/Organisation is proposing to contribute by filling-in the table below:

| Task No | Task Description | Max Budget Allocated in Euro | Amount in Euro (mandatory) | % of whole Task (mandatory) |
| --- | --- | --- | --- | --- |
| 00 | T1.1 Project set-up | 0 | . | . |
| 01 | T1.2 Project management | 36 400 | . | . |
| 02 | T1.3 Work package lead | 32 500 | . | . |
| 03 | T2.1 Batch 2025 wallet publication confirmation | 182 000 | . | . |
| 04 | T2.2 Prepare stable drafts batch 2026/2027-B for wallet | 130 000 | . | . |
| 05 | T2.3 Prepare ETSI TB approval batch 2026/2027-B for wallet | 130 000 | . | . |
| 06 | T2.4 Prepare ENAP comment disposition batch 2026/2027-B wallet | 65 000 | . | . |
| 07 | T3.1 Batch 2025 certificates and timestamps publication confirmation | 123 500 | . | . |
| 08 | T3.2 Prepare stable drafts batch 2026/2027-A for certificates and timestamps | 29 250 | . | . |
| 09 | T3.3 Prepare ETSI TB approval batch 2026/2027-A for certificates and timestamps | 29 250 | . | . |
| 10 | T3.4 Prepare ENAP comment disposition batch 2026/2027-A for certificates and timestamps | 6 500 | . | . |
| 11 | T3.5 Prepare stable drafts batch 2026/2027-B for certificates and timestamps | 9 750 | . | . |
| 12 | T3.6 Prepare ETSI TB approval batch 2026/2027-B for certificates and timestamps | 9 750 | . | . |
| 13 | T3.7 Prepare ENAP comment disposition batch 2026/2027-B for certificates and timestamps | 6 500 | . | . |
| 14 | T4.1 Prepare stable draft batch 2026/2027-A for ERDS | 31 200 | . | . |
| 15 | T4.2 Prepare ETSI TB approval batch 2026/2027-A for ERDS | 31 200 | . | . |
| 16 | T4.3 Prepare ENAP comment disposition batch 2026/2027-A for ERDS | 15 600 | . | . |
| 17 | T5.1 Batch 2025 wallet publication confirmation | 78 000 | . | . |
| 18 | T5.2 Prepare stable drafts batch 2026/2027-A for signatures | 52 000 | . | . |
| 19 | T5.3 Prepare ETSI approval batch 2026/2027-A for signatures | 52 000 | . | . |
| 20 | T5.4 Prepare ENAP comment disposition batch 2026/2027-A for signatures | 26 000 | . | . |
| 21 | T5.5 Prepare stable drafts batch 2026/2027-B for signatures | 5 200 | . | . |
| 22 | T5.6 Prepare ETSI TB approval batch 2026/2027-B for signatures | 5 200 | . | . |
| 23 | T5.7 Prepare ENAP comment disposition batch 2026/2027-B for signatures | 2 600 | . | . |
| 24 | T6.1 Batch 2025 wallet publication confirmation | 91 000 | . | . |
| 25 | T6.2 Prepare stable drafts batch 2026/2027-A for trust framework | 23 400 | . | . |
| 26 | T6.3 Prepare ETSI TB approval batch 2026/2027-A for trust framework | 23 400 | . | . |
| 27 | T6.4 Prepare ENAP comment disposition batch 2026/2027-A for trust framework | 5 200 | . | . |
| 28 | T6.5 Prepare stable draft batch 2026/2027-B for trust framework | 10 400 | . | . |
| 29 | T6.6 Prepare ETSI TB approval batch 2026/2027-B for trust framework | 10 400 | . | . |
| 30 | T6.7 Prepare ENAP comment disposition batch 2026/2027-B for trust framework | 5 200 | . | . |
| 31 | T7.1 Prepare stable drafts batch 2026/2027-A for new technology | 26000 | . | . |
| 32 | T7.2 Prepare ETSI TB approval batch 2026/2027-A for new technology | 26 000 | . | . |
| 33 | T8.1 Certificate authority workshop - hosting | 6 500 | . | . |
| 34 | T8.2 Certificate authority workshop - Presentations | 13 000 | . | . |
| 35 | T8.3 ERDS workshop - hosting | 6 500 | . | . |
| 36 | T8.4 ERDS workshop - Presentations | 13 000 | . | . |
| 37 | T8.5 EUDI Wallet workshop - Hosting | 6 500 | . | . |
| 38 | T8.6 EUDI Wallet workshop - Presentations | 19 500 | . | . |
| 39 | T8.7 External liaison | 26 000 | . | . |
| 40 | T8.8 Liaison with EU DG connect 2025 | 46 800 | . | . |
| 41 | T8.9 Liaison with EU DG connect 2026/2027 | 46 800 | . | . |
| 42 | T9.1 Testing framework study | 65 000 | . | . |
|  | TOTAL: | 1 560 000 |  |  |

# Amount in Euro (mandatory): Indicate the price offered for your contribution to the task(s)

# % of whole task (mandatory): Indicate to which percentage of the execution of the whole task your offer corresponds

1.2.3 Competences, reference to related activities:

Provide a description of the proposed approach, competences, reference to related activities:

- Explain which part of the task is corresponding to the requested percentage that your Company/Organisation will handle,

- Explain the scope that your Company/Organisation will cover,

- Explain your approach to the management of the quality and,

- Explain your approach to the management of the risks and their mitigation,

- Describe and justify the proposed costs to achieve this project objectives.

Provide a description of the competences, references to related activities in particular:

Please indicate if you have contributed to a specific 2025 deliverable either as

a) Rapporteur, or

b) Other contributor.

Please provide details if you have been involved in activities relating the eIDAS including:

a) Member of EUDIW large scale pilot,

b) As a member of the NySci expert team supporting Commission activities,

c) Working DGITS eIDAS related projects,

c) Development of national EUDIW,

d) Contributing to ETSI standardisation for eIDAS.

For an expected rapporteur role, please indicate experience with supporting ETSI standardisation and understanding of ETSI editing rules.

For STF and WP leaders, please indicate experience is leading ETSI standardisation or similar activities.

Annex II	 Terms and Conditions
CfE – STF 705 (REFERENCE BODY ESI)

Deadline: 17 November 2025

2.1	Submission of Proposals

All proposals in response to this CfE shall be submitted before the deadline indicated in this Collective Letter, using exclusively the WEB application on the ETSI Portal at the following address: https://portal.etsi.org/cfe.

Proposals shall be composed of Curriculum Vitae of the proposed service providers’ personnel and the Annex I of this CfE duly filled-out.

Proposals that will be partial or incomplete at the deadline will not be accepted.

The Terms and Conditions in this Annex will apply.

2.2	Modification and Withdrawal of Proposals

Applicants may, without prejudice to themselves, modify or withdraw their proposal by written request, provided that the request is received by ETSI prior to the due date and time, at the address to which their proposal was submitted. The applicant may submit a new proposal provided that such new proposal is received prior to the deadline for responding which is specified in this Collective Letter.

2.3	Assessment of Proposals

The ETSI Director-General, in consultation with the Reference Body Chair, is responsible for the selection of the service providers that will be contracted to perform this Project work. The ETSI Director-General and the Reference Body Chair may be assisted by a Selection Panel to assess the applications received and make the final decision.

As per article 1.10.4 of the ETSI Directives, the Director-General may discard proposals that could be identified as creating potential conflict of interest.

The ETSI Secretariat will only communicate to the applicants the result of the selection (accepted or not accepted). Should applicants need more information on the rationale for the selection, they must address a formal request to the ETSI Director-General.

- The following evaluation criteria will be applied to all proposals, in order of priority:

- Evidence that the applicant has the necessary structure and expertise to ensure delivery

- Reference to current or previous activities in the specific technical domain of this project

- Critical review of the most efficient way to achieve the objectives in this Project ToR

- Effective proposed approach/methodology for the execution of the tasks

- Implementation schedule

- Clear pricing policy

Compliance with the first two (2) criteria is mandatory.

Proposals that are not considered compliant with these criteria will be discarded.

Priority will be given to technical quality of the proposals. Pricing considerations will be taken into account to ensure that the best value for money is achieved. Compatibility with the maximum budget allocated to this Project will be verified before placing a Service Contract.

Following the assessment process, ETSI reserves the right to grant contracts to other than the cheapest proposals, to accept or reject any offer completely or in part, or to reject all proposals, without providing the reasons. If no offer is accepted, ETSI may decide to abandon the work or proceed in any other manner ETSI may select.

2.4	IPR and confidentiality Agreements

The information provided in this CfE, as well as the fact that the applicant has received the CfE, is considered confidential and protected under copyright laws. The applicant may not discuss, share, or use the information in this CfE for any purpose other than the response to this CfE.

ETSI will not disclose the content of any proposals to other applicants or any other party, with the exception of the persons involved in the assessment process described in §2.3 above.

However, ETSI reserves the right to make use of the information provided in this proposal to improve this project definition for the purpose of this CfE or any other manner in which ETSI may decide to proceed to select the service providers.

If successful, the applicant will be required to sign a Service Contract, which includes IPR and Confidentiality clauses aligned with the relevant policies in the ETSI Directives.

2.5	Preparation cost

ETSI will not be responsible for any costs or expenses that the applicant may incur in preparing and/or submitting the proposal.

2.6	Service Contract

A Service Contract will be proposed to the applicants that will be selected to perform the work.

Details on the Terms and Conditions of this contract can be found on the ETSI Portal, at the following address: https://portal.etsi.org/STF/STFs/Contracts.aspx