ETSI/TA 11 (91) 15

Annex 2

Page 1

TERMS OF REFERENCE FOR PROJECT TEAM 18V

Reasons for proposing a Project Team:

The work to be undertaken by this Project Team is required as soon as possible in order to meet the timescale proposed in the Mandate from the Commission and to maximise the possible benefits from further work in this area.

2	Consequences if not agreed:

Failure to complete the Mandate and loss of possible benefits to industry and users from improvements in the availability and possible further harmonisation of PSTN access requirements in the areas to be covered.

3	Detailed description

3 .1	Subject title:

Analogue access not covered by prETS 300 001

3.2	Reference TC:

BT

3.3	Other interested TC (if any):

NA, TE

3.4	Duration:

6 months, for completion by TA 12 (March, 1992

3.5	Target date for start of work:

October 1991

3.6	Necessary manpower:

8 man months and cooperation from network operators and national approval and standards bodies.

3.7	Context of the study:

The European Commission has issued a Mandate for an examination of the possibility of harmonising testing methods for PSTN attachments. To facilitate this work a survey is to be undertaken to evaluate the feasibility and usefulness of preparing a document containing a structured collection of existing national approval requirements for access to those presentations of the PSTN that are outside the scope of ETS 300 001 (aspects related to ETS 300 001 are being covered by a separate Project Team). The document, if produced, would adopt a common format for those aspects of national requirements that fall within the definition of "essential requirements".

The project Team will be managed by an Ad Hoc Group of BT2. Experts from Technical Committees NA and TE will be invited to attend this group.

3.8	Related activities in other bodies and necessary coordination of schedules:

Account should be taken of the work of the TRAC Ad Hoc Group that is interpreting the Essential Requirements in Directive 9112631EEC.

WPM125619 1 /AB/hg

ETSI/TA 11 (91)) 15

Annex 2

Page 2

3.9	Scope of the Terms of Reference and relevant study items:

The Project Team should:

-	identify the different interfaces (analogue only) to the PSTN not covered in ETS 300 001 available in different countries, and the approximate number of customers for each type of interface,

-	identify the different standards or attachment requirements in different countries, their length, degree of completeness, the languages that they are available in, the ease with which the information can be obtained, and the availability of appropriately skilled manpower to work on a representation of the standard,

-	for the types of interface with the largest number of users, assess the work necessary to convert each standard or requirement into a common form, and estimate the future useful life of the standard/requirement,

-	recommend the interfaces for which having standards readily available in a common form would be expected to produce the greatest benefit.

Priority should be given to those presentations of the PSTN that are used by PBXs.

3.10	 Reference specifications) and existing documents including member contributions:

prETS 300 001

Relevant national requirements and test specifications

Directive 91t263/EEC

Draft BT2 Technical Report (BT-2009) on Type Approvals

3.11	Part of the ETSI Work Programme (EWPI for which the PT is required:

DTR/BT-20 1 4

3.12	Expected outputs:

An ETR containing the results of the survey, interviews and analysis, and recommendations, together with a list of the interfaces for which further work on a re-presentation of standards would yield the greatest benefits. The Project Team should identify the scale and feasibility of whatever further work it recommends.