TERMS OF REFERENCE FOR PROJECT TEAM 35

ON IMCC/JEEC SUPPORT TEAM

as approved by TA 11

1.  Reasons for proposing a PT

To assist the ETSI Director in managing the activities concerning "narrowband ISDN and PTN Standardization" and the setting-up/operation of the JEEC/IMCC committees and their related activities.

2.  Consequences if not agreed

Not relevant, already agreed, see minutes of TA 10.

3.  Detailed description

3.1.  Subject title:	IMCC/JEEC Support Team

3.2.  Reference TC:	IMCC

3.3.  Other interested TCs (if any):	As defined by those items in the ETSI Work Programme 					which are within the scope of IMCC.

3.4.  Duration:	15 months

3.5.  Target date for start of work:	November 1991

3.6.  Necessary manpower:	16 man months

3.7.  Context of the study:

Support to IMCC, management and technical co-ordination of ISDN standards, both public and private. Items which are relevant to the ETSI/ECMA agreement should be flagged to JEEC for further consideration.

3.8.  Related activities in other bodies and necessary co-ordination of schedules:

Not applicable

3.9.  Scope of the Terms of Reference and relevant study items:

The PT provide support to IMCC in the following areas:

1. Management

The PT will perform management functions as follows:

a)	identification of standards required;

b)	identification of interdependencies between standards;

c) 	establishment and co-ordination of a time schedule for the production of 			standards and co-ordination of necessary resources in co-operation with the 			working bodies involved and the ETSI Secretariat.

2. Technical Co-ordination

The PT will perform technical co-ordination between the working bodies concerned as 	necessary to the management. This may include:

a)	checking of the consistency between draft standards prepared by the 			committees;

b)	participation at the various committee meetings;

c)	liaison between the various committees;

d)	preparation of contributions on co-ordination aspects and technical aspects;

e)	initiation of rapporteurs meetings if necessary;

f)	assurance of consistency of terminology in conjunction with ETSI SMD.

3. Support to the IMCC

a)	identification of problem areas which need resolution by IMCC;

b)	preparation of proposals to resolve conflicts;

c)	preparation of meetings reports;

d)	maintenance of listed items to be included in the status report and the ETSI 			ISDN standards guide.

In a first phase the following specific tasks must be undertaken in addition to the above 	activities:

a)	produce a new status list derived from the latest versions of the ISM and 			ITAEGT status lists, with necessary amendments, and including standards 			associated with new co-ordination activities as proposed by ISM and agreed 			by the Technical Assembly;

b)	prepare the documentation needed for the transfer of the contracts BC74-77 			from CENELEC to ETSI;

c)	prepare a new ETSI ISDN standards guide, derived from the existing ETR 10 			and the M-IT-05 taxonomy.

3.10.  Reference specification(s) and existing documents including member contributions:

-	ETSI Work Programme;

-	M-IT-05 and supplement;

-	BCs 74-77;

-	ETR10;

-	report of the ad-hoc group revising the BC's.

3.11.  Part of the ETSI Work Programme (EWP) for which the PT is required:

Not applicable

3.12.  Expected output(s):

-	ETSI ISDN standards guide;

-	status lists;

-	documentation for transfer of BCs 74-77.

MANPOWER ALLOCATION IN 1993 FOR PROJECT TEAM 35 ON SUPPORT OF IMCC

At the 11th Technical Assembly, Project Team 35 was created in order to provide support for IMCC.

The necessary resource must be made available for the whole duration of the activities of IMCC/JEEC, up to end 1993.

The IMCC estimates that the team would require one expert full-time and for experts part-time for a total resource of 24 man months in 1993.

BUDGET ALLOCATION FOR PROJECT TEAMS

(Contribution of the TC/ATM Acting Chairman)

Current 1993 allocation of resources for our Project Teams is only made of the part of the budget of the Project Teams approved in 1992, that could not reasonably be spent in 1992.

That is to say 8 mm for PT 37 (out of 20), 6 mm for PT 38 (out of 12), 4 mm for PT 39 (out of 12), 7 mm on PT 24V (out of 12).

This covers (on average) work to be done in first half of 1993.

It is hard to believe that ATM work can be contained with the termination of all Project Teams. I rather think that without a follow-up plan for some of these Project Teams, the efforts made in 1992 will not be exploited. In particular, TC/ATM efforts to support other TCs and PTs more aggressively, will be in jeopardy.

Having reviewed our priorities, may I ask you to consider the following provisional request:

1	PT 37: + 10 mm in 1993. Extension to provide guidance on protocol specification in SDL and in prose, not limited to testing considerations. That may include intitial work on validation constraints.

2	PT 39: + 8 mm in 1993. To provide an extended consultation service on Conformance Testing and TTCN. That may include co-operation with ETSI Secretariat, and special emphasis on TBRs.