Updated Terms of Reference for the extension of PT 39

"CONFORMANCE TESTING CONSULTING GROUP 1994-1995"

as approved by TA 20

1 REASONS FOR PROPOSING A PROJECT.

PT 39 is an essential ingredient in the development of testing  specifications  in  ETSI. Normally, one PT39 expert attends all kick-off meetings of Conformance Testing  Project (STC  or  PTs)  in  charge  of  developing  PICS and/or test suites.

Initially, PT 39 was staffed only for 1992-1993.

The  team  of  three  permanent  experts,  members  of  ESTI secretariat  for  two years will decrease the need for PT 39 advice starting 3Q 1993, for the Project Teams  they  assist directly.  But at the same time, the number of PT working on test specification is rapidly increasing (from  6  to  16  -6/93 to 6/94 respectively).

Estimate  of TC MTS chair and PT 39 team leader is that 8 mm in 1994 (and probably 6 mm in 1995) would still be necessary to maintain the role of PT39 as it is to-day, and  ensure  a good cooperation with the Permanent Experts (initial experience shows that PT39-PEX meetings will speed-up the analysis of  problems, but not reduce the needed level of assistance in the short-term).

2  CONSEQUENCES IF NOT AGREED

Suspension of an initiative that has proven  useful  to  all existing  Project  Teams in charge of testing and PICS specifications.

Committee  work cannot help in this area, on a continous basis, although MTS plans to dedicate  more  time  to  back-up PT39  (and PEX) in the future.  Assistance must be organized by a leader dispatching available experts, within a budget.

3 DETAILED DESCRIPTION

3.1 SUBJECT TITLE:

CONSULTING  GROUP FOR SUPPORTING THE DEVELOPMENT OF CONFORMANCE TESTING STANDARDS IN THE FRAMEWORK OF ISO/IEC 9646  AND TC MTS METHODOLOGY.

(Two year extension).

3.2 REFERENCE TC : MTS

3.3 OTHER INTERESTED TC : RES, SPS, SMG, TE...

3.4 DURATION : 24 MONTHS

3.5 TARGET DATE FOR START OF WORK : JAN 1994

3.6 NECESSARY MANPOWER : 5 + 9 MENMONTHS OVER 2 YEARS (14).

Expertise : same as PT 39.

Good knowledge of the documents mentioned in 3.10.

Knowledge  of  CT  projects in ETSI, EWOS and/or CTS program desirable.

3.7 CONTEXT OF THE STUDY

Pending approval of revised Terms of Reference, TC  MTS  had decided  in  July  1993 to sort out its activities along the following lines :

·	  STC MTS1 "WG1-projects", in charge of the PRODUCTION  of

ETSI documents related to SPECIFICATION styles and TESTING  methodologies.  These  documents  can be ETS, ETRs, TCR-TR, MTS-TR, depending on the importance and maturity of the topic.

·	  STC MTS1 "WG2-projects", to support this  production  by  appropriate (and limited) INVESTIGATIONS.

·	  STC MTS2, in charge of PROMOTING ETSI methodologies documented by STC MTS1 on behalf of TC MTS, and of all necessary  ASSISTANCE  and  liaisons,  as  far as resources permit.

Extension of Project Team 39 corresponds  to  an  additional effort  in  the MTS2 area, to provide ASSISTANCE to Conformance Testing Projects in ETSI, and make sure MTS1  and  MTS as a whole consolidate the PT39 proposed solutions.

3.8   RELATED  ACTIVITIES  IN  OTHER  BODIES  AND  NECESSARY COORDINATION :

Coordination  with  the  "PEX"  group,  and  with  STC  MTS1 projects.

3.9    SCOPE  OF  THE  TERMS OF REFERENCE AND RELEVANT STUDY ITEMS

(same as PT39) " This proposed PT should act on a consultancy basis to the different STCs during the entire development phase of the abstract test suites.

The selected ETSI PT eperts would help to initiate the test suite development by srtting up realistic project schedules, using a systematic approach and guidance in the use of check-lists.

They should show up at scheduled time intervals to support the TCs to carry the development forward when getting into detailed problems and aid in the use of the TTCN language.

The PT experts should not be used to do the job. They should only provide support to the ETSI STC groups by promoting learning by doing"

3.10  REFERENCE  SPECIFICATIONS   AND   EXISTING   DOCUMENTS INCLUDING MEMBER CONTRIBUTIONS

ISO/IEC 9646 (CCITT X.290) - all parts, new parts and amendments.

ETS/ETR produced by TC MTS on testing : TCR-TR 006, ETR 021, 022, 025, 040.

Deliverables of PT38 (Projects MTS-01007-*).

3.11 ETSI WORK PROGRAMME REFERENCE : MI/MTS-01010

3.12 EXPECTED OUTPUT

Same as PT 39. Consulting and follow-up. Feedback to TC MTS. "A  consultancy  service  to  be offered on demand and/or at scheduled checkpoints".