TERMS OF REFERENCE FOR PROJECT TEAM W

ON ALGORITHMS FOR CRYPTOGRAPHY

NOTE: THESE ToR INCLUDE THE ACTIVITY ON GSM EXPORT ALGORITHM, WHICH WAS APPROVED AT TA 16

# 1	Reasons for proposing a Project Team

The reason for SAGE to request funding is that the Security Algorithms Group of Experts, being a closed group with only 7 companies participating, has scheduled a large number of activities for the coming period (see for details below). It will not be possible to carry out all the desired activities without external funding. (It should be noted that when SAGE was started it was expected that the group would design an average of one algorithm per year.)

To carry out all its activities SAGE will need at least a funding of 4 man years (48 man months) in 1993 and half a man year (6 man months) in 1994.

One of the activities is funded via a CEC mandate (12 man months in 1993), for another external funding is being sought (also 12 man months in 1993). For the missing part PT funding is requested.

For the last quarter of 1992, 1993, and the first half of 1994, the SAGE has scheduled the following activities.

a)	Design of an authentication and key loading algorithm for STC TE9 (multi application smart card)

-	Scheduled:	April 1992 - March 1993

-	Manpower:	8 man months 1992, 4 man months 1993.

-	Funding:	No funding to date, work paid for by 5 companies participating in SAGE.

b)	 Design of an encryption algorithm for (future) STC TE/AVM standard

-	Scheduled:	October 1992 - July 1993, start delayed pending formal CEC and ETSI TA approval.

-	Manpower:	3 man months 1992, 12 man months 1993.

-	 Funding:	15 man months CEC mandate.

c)	Design of an alternative encryption algorithm for GSM (which will allow GSM to be exportable outside Europe)

-	Scheduled:	October/November 1992 - June 1993.

-	Manpower:	3 man months 1992, 12 man months 1993.

-	Funding:	No funding yet, funding will be requested from either CEC DG XIII or the 
	GSM MoU.

d)	Design of an authentication algorithm for STC NA7 (UPT)

-	Scheduled:	January 1993 - September 1993.

-	Manpower:	9 man months 1993.

-	Funding:	No funding to date.

e)	Design of a general PNO block cipher algorithm to be used for the protection of public Telecommunication networks (e.g. GSM).

-	Scheduled:	January 1993 - May 1994.

-	Manpower:	12 man months 1993, 6 man months in 1994.

-	Funding:	No funding to date.

f)	Design of cryptographic algorithms for TV broadcast systems (potential activity)

-	Scheduled:	Not yet known, ETSI, EBU and CEN/CENELEC will start to discuss this 
	issue in the next months.

-	Manpower:	Estimate 9 to 15 man months 1993/1994.

-	Funding:	No funding to date.

# 2	Consequences if not agreed

Activity a. (TE9 algorithm): no consequences, will be finalised as scheduled. Activity b. (AVM algorithm): no consequences, will be carried out provided the mandate is approved by the CEC and ETSI TA. Activity c. (GSM algorithm): will only be carried out if funding is provided. Activities d, e, f: without funding at most one of these will be carried out, and probably with significant (more than three months) delay.

# 3	Detailed description

## 3.1	Subject title:

Design of cryptographic algorithms for European standards

## 3 .2	Reference TC:

S A G E.

## 3.3	Other interested TCs:

TE (act. a., b. and e.); NA (act d. and e.): SMG (act. c).

## 3.4	Duration:

18 man months; January 1993 - June 1994

## 3.5	Target date for start of the work:

January 1993

## 3.6	Necessary man power:

At least 48 man months in 1993 and 6 man months in 1994. (Depending on the actual schedule for activity f. more might be needed). A CEC mandate for 12 man months in 1993 is awaiting formal approval. Action is being taken to find another 12 man months (external) funding for 1993, but there is no guarantee this will succeed.

## 3.7	Context of work:

Design of cryptographic algorithms for integration in European telecommunication standards on request of responsible standardisation committees.

## 3.8	Related activities in other bodies and necessary co-ordination:

Act b. Co-ordination with relevant CCITT standardisation. Act c. Integration in next GSM implementation phase Act e. Possible co-ordination with Eurescom Act f. Possible co-ordination with EBU and CEN/CENELEC

## 3.9	Scope of the Terms of Reference and Relevant study items:

a)	Design of an authentication and key loading algorithm for STC TE9 (multi application smart card).

b)	Design of an encryption algorithm for (future) STC TE/AVM standard.

c)	Design of an alternative encryption algorithm for GSM (which will allow GSM to be exportable outside Europe).

d)	Design of an authentication algorithm for STC NA7 (UPT).

e)	Design of a general PNO block cipher algorithm to be used for the protection of public Telecommunication networks.

f)	 Design of cryptographic algorithms for TV broadcast systems (potential activity)

## 3.10	Reference specifications:

[TE9-1]	Terminal equipment (TE) Requirements for IC cards and terminals for

telecommunication use. D/EN/TE/090001.

Part 0 - System overview.

Part 1- Security framework.

Part 2 - Application independent card requirements.

Part 3 - Application independent card related terminal requirements.

Part 4 - Payment methods.

Part 5 - Telecommunication features.

[GSM-1]	Rec. GSM 02.09, Security aspects, (general description of GSM security).

[GSM-2]	Rec. GSM 03.20, Security related network functions (specification of security features).

[AVM-1]	Draft CCITT Rec. on Confidentiality system for audio-visual services (to be adopted as ETS).

[AVM-2]	Draft CCITT Rec. on Authentication and encryption key management system for audio-visual services.

[UPT-1]	Draft version of 'General UPT security architecture', DTR/NA70401.

## 3.11	Part of the ETSI work Programme (EWP) for which the PT is required:

This includes at least: the specification of the multi application smart card for telecommunications (TE9); the specification of standards for audio visual services  (TE/AVM); The specification of GSM phase II; and the specification of standards for Universal Personal Telecommunications (UPT, NA7).

## 3.12	Expected outputs:

a)	An authentication and key loading algorithm for use on the multi application smart card;

b)	An encryption algorithm for use in audio visual standards;

c)	An export encryption algorithm for GSM;

d)	Design of an authentication algorithm for UPT;

e)	A general PNO block cipher algorithm;

f)	Cryptographic algorithms for TV broadcast systems (possibly).