DRAFT TERMS OF REFERENCE FOR PROJECT TEAM 56V

ARCHITECTURE of HIPERLAN

as approved by TA 17

1.  Reasons for proposing the PT

A standard like HIPERLAN should be as open as possible, and should not be build in order to address one particular application area This means that the architecture of the radio transmission specifications and the protocols specifications must be totally independent of the application in which they will be used

2.  Consequences if not agreed

It will be impossible to meet the time schedule as indicated in the BC-T-043-SI The application areas of the future HIPERLAN standard might be unnecessary limited

3.  Detailed description

3 1.  Subject Title:	Architecture of HIPERLAN (High Performance European Radio Local Area Networks)

3 2.  Reference Technical Committee:		Radio Equipment and Systems

3 3.  Other interested TCs:	BT

3 4 duration:	About 1 year

3 5 Target date for the start of the work:	June 1993

3 6.  Necessary Manpower (qualification and amount):

A total manpower of 20 manmonths is required, of which 15 man months during 1993 and 5 	man months during 1994

Project team members should have knowledge of recent developments in radio and local area 	networks.

3.7.  Context of the study:

-	 To develop HIPERLAN with the objective of a radio LAN standard for frequency allocations at 5 	and 17 GHz, offering 20 Mb/s to the terminal and 1000 Mb/s/hectare/floor of total media 	throughput.

- 	To perform specific developments and extensions needed by new application classes that will 	emerge due to the performance of HIPERLAN (e.g. Multimedia)

3.8.  Related activity in other bodies and necessary coordination of schedules:

-	Frequency allocation harmonisation - CEPT FM and SE

-	Related work on IEEE 802.11

3.9.  Scope of the Terms of Reference and Relevant Study items:

-	To perform studies according to the tasks defined by RES 10, and to draft and edit the 	corresponding documents (ETR);

-	To gather and provide the available and necessary information on the subject;

-	To implement operational decisions on texts taken by RES 10 and its working groups;

-	To report results and progress of its activities in accordance with the rules of liaison.

3.10.  Reference Specifications and Documents:

-	CEPT Recommendations for HIPERLAN

-	HIPERLAN Services & Facilities (ETR 069)

3.11.  Part of the ETSI Work Programme (EWP) for which the PT is required:

EWP DTR/RES 10-06

3.12.  Expected Output:

-	ETR on (Extension of) the Architecture of HIPERLAN.

-	Relevant parts of this ETR will be usable for the ETS(s) for HIPERLAN.