Updated Terms of reference for Project Team 60

METHODOLOGY GUIDE FOR THE PRODUCTION OF SDL SPECIFICATIONS IN EUROPEAN TELECOMMUNICATIONS STANDARDS

(updated following TC MTS meeting June 94 and TCC18 September 94)

as approved by TA 20

1.	Reasons for proposing to continue the Project Team in 95:

SDL, the formal notation specified in the ITU-T recommendation Z.100, is used in a wide variety of ETSI standards, tackling protocols and services, under the aegis of TCs like SPS, RES, TE, BTC, NA,...

More than a fact, the use of SDL is today an ETSI policy. TA19 agreed to amend the TAWP with the following statement :

"ETSI standards shall, where applicable, use standardised languages and notations (such as SDL, MSC,ASN.1 and TTCN). Non-standard languages and notations may be used only when no applicable standardised language or notation exists".

TC MTS has been working on methodologies for SDL since 1992.

ATM-01004 "Specification styles for SDL in order to develop testable specifications" (PT37) concentrated on the testability aspects of specifications. The prETS 300 414, containing rules guiding the use of SDL, is now in PE62, on its way to become an ETS and a TCR-TR.

Beyond the testability aspects - primary concern of TC ATM in 1992 - and following the extension of TC MTS to specification aspects, the design of a complete methodology has been initiated in 1993-1994.

MTS-00013 (PT60) "Methodology for the specification of ETSI protocols and services when using SDL" designs a methodology extending "from the generation of an informal description of the requirements to the generation of a document containing a formal description in SDL, or a formal model in SDL for validation".

According to the plans, PT60 has drafted a methodology, which was sent for comment to all TC/STC Chairpersons in July 94.

The next phase of PT 60 is concerned, now, with the refinement of the methodology, focusing more closely on users' opinions and needs. Promotion and tutorial actions are an essential complement. A methodology should not be defined by an enclosed community.

The initial plan for 95 has been defined to cover

-	revision of the draft methodology, in accordance with comments, and production of the final version of the methodology,

-	production of tutorial material.

The new plan was to include a pilot project with a real development project in ETSI (in TC SPS, for instance), in order to get valuable experience and feed-back.

After TCC18, taking into account the available extension, no pilot project will be carried out.

2.	Consequences if not agreed:

The effort made by PT60 has led to a valuable piece of methodological documentation, which cannot be efficiently used if it is not completed with the pragmatic learnings of a pilot project, and accompanied with tutorial material.

The risk to have a theoretical piece of work is high if feed-back is not gathered by MTS.

The schedules are tight : the work with SDL is currently being generalised (the engagement of a Permanent EXpert is envisaged). The methodology should be ready before bad habits are taken.

3.	Detailed description:

3.1.	Subject title:

METHODOLOGY GUIDE FOR THE PRODUCTION OF SDL SPECIFICATIONS IN EUROPEAN TELECOMMUNICATIONS STANDARDS - PHASE 2 : TUTORIAL AND PILOT TRIAL.

3.2.	Reference TC: MTS

3.3.	Other interested TCs (if any): SPS, RES, TE, BTC, NA

3.4.	Duration: 12 months

3.5.	Target date for the start of work: January 95

3.6.	Necessary manpower (expertise, mix of skills and amount): 8 man.months reduced after TCC18 to 6 man.months

Experts should have expertise in at least one of the following areas:

-	development of SDL and/or SDL tools

-	practical use of SDL, especially for service/protocol specification

-	experience of protocol specification, if possible in ETSI

-	experience of implementing products from SDL specifications

-	experience in transferring technology to work teams

-	experience in a support role for a technology or procedure, good communication abilities.

The team in 95 should ideally be composed of two experts.

3.7.	Context of the study:

The emerging harmonisation and rationalisation of the use of formalisms in ETSI appears as the most significant contextual factor, with in particular:

-	generalisation of quality improvement actions to the work undertaken in TCs, quality assurance and validation,

-	generalisation of the use of tools (e.g. SDT), and accompanying support,

-	considered creation in ETSI of a centre of competence on languages (TTCN, SDL, ASN.1, etc.).

3.8.	Related activity in other bodies and necessary coordination of schedules:

ETSI NA - DASH

ETSI PT65 on validation

3.9.	Scope of the terms of reference and relevant Work Items:

See 1. The main focus in 95 should be on the elaboration of examples and tutorial.

3.10.	Reference specification(s) and existing documents, including ETSI member contributions:

ITU-T Z.100, Z.120, Z.105

ATM 12/92 TD.13 = ETSI TA 16 TD 48

ATM 9/92 TD.13 on validation = ETSI TA 15 TD 29

prETS 300 414

3.11.	Work Item(s) from the ETSI Work Programme (EWP) for which the PT is required:

DE/MTS-00013

3.12.	Expected output(s):

a)	DE/MTS-00013, which is to become an ETS and TCR-TR, comprising two parts

a.1)	the basic methodological description (for which a draft exists today)

a.2)	tutorial and examples

a.3)	final report

b)	achievement of a pilot project. Pilot dropped due to TCC 18 budget reduction in 95.