Terms of Reference for Project Team 67 V Extension A (BC 317/3)

TBRs for DECT/GSM Radio access

1.	Reasons for Proposing a Project Team

During 1994 ETS 300 370 was approved which describes the DECT/GSM interworking profile access and mapping. Based on ETS 300 370 a test specification is currently developed by RES03-PT62V. TBRs are needed for the following reasons:

To get a seamless DECT/GSM service to DECT/GSM customers.

To define requirements for type approval for DECT/GSM Portable Parts and for DECT-GSM dual mode portables/mobiles.

2.	Consequences if not agreed

To allow the market entrance of DECT/GSM terminals, a base for certification is needed which allows mutual recognition of DECT/GSM portable/mobiles.

A non-agreement would limit the ability of free movement of DECT/GSM

portables/mobiles and limit the right to connect to any GSM PLMN.

3	Detailed Description

3.1	Title

TBRs for DECT/GSM portables for 3.1 kHz speech applications.

3.2	Reference

TC-RES (STC RES-03)

3.3	Other Interested TCs

-	SMG

-	TE

-	MTS

3.4	Duration

6 months

3.5 Target Date for Start of Work

June 1995

3.6	Necessary Manpower

9 man-months

3.7	Context of Study

The work shall take into account:

-	development of the DECT Test Case Library

-	development of the DECT Application Test Specifications

-	the work of the CTS-5 consortium

3.8	Related Activities and Necessary Co-ordination of Schedules:

-	Evolution of ETS 300 370 (DECT/GSM IWP)

-	The completion and approval of the DECT/GSM interworking profile test specification

-	The completion and approval of ETS 300 466 (DECT/GSM FP-MSC interconnection)

-	The completion and approval of TBR22

-	For the approval of dual mode portables/mobiles also the appropriate GSM standards have to be considered.

3.9	Scope of Terms

To define the Technical Base for Regulation (TBR) for DECT/GSM

portables/mobiles with the aim of achieving interoperability for DECT/GSM portables/mobiles and GAP or GSM infrastructure.

The PT shall investigate which additional essential requirements in addition to TBR22 have to be considered for DECT/GSM type approval, based upon ETS 300 370. A  scope for a TBR for DECT radio access to GSM PLMN may include portable parts as well as parts of fixed parts.

The PT shall investigate which additional essential requirements to TBR22 and the GSM TBRs have to be considered for DECT/GSM dual mode portables/mobiles type approval

3.10	Reference Specifications and existing documents including member contributions:

ETS 300 370;  pr ETS 300 466;  pr ETS 300 444 (GAP)

3.11	Expected Liaisons

-	RES03-T working party

-	RES03-N working party

-	RES03-GSM working party

-	PT 66V

-	PT67V

-	PT 12

-	MTS

3.12	Part of the ETSI Work Programme (EWP) for which the PT is required

-	DE/RES- 03059

-	DE/RES- 03060

3.13	Expected Outputs

TBR for DECT/GSM Radio Access

TBR for DECT/GSM dual mode portable/mobiles

NOTE:	The abbreviation "TBR" is here used synonymous to "Harmonised Standard"