Terms of reference for Project Team 69V extension

PROMOTION OF TC MTS ACTIVITIES IN ETSI

as approved by TA 23

# 1.	Reasons for proposing the Project Team extension:

PT69V was launched at the end of 1994, on the recognition that the “horizontal” role of TC MTS, related to the methodologies for standards development, needed to be publicized in ETSI, in the TCs, in the Secretariat, in the member companies.

The objective of publicizing the work of TC MTS is a general improvement of the quality of ETSI outputs, in the area of testing as well as in the area of base standards.

In 1995, after having issued a communication plan that received a good appraisal from TC MTS and the European Commission, PT69V has undertaken a number of activities related to the development of background material, to communication to standards developers, to communication to managers of the standardisation process.

For instance, PT69V wrote articles, made presentations, held seminars, took practical actions to make technical documentation available to standards developers. At the end of 1995, an “MTS book” will be published. A special activity consisted in presenting the different aspects of standards validation, testing, etc. to the High Level Task Force implementation group, with an analysis of the objectives made in reference to the interest of manufacturers, operators, users.

After a year of existence, PT69V appears credible. Communication actions are still needed, and should be carried out to publicize the latest results of TC MTS.

Several achievements from TC MTS deserve to be brought into more light:

- the work done on SDL validation, in relation with different TCs/STCs (SPS3, SMG...), by PT65,

- the revison of TCR-TR 006, that re-define the question of test specification in ETSI,

- the project team on Quality of Standards (PT76V), that will develop criteria, methods and quality mechanisms applicable to standards making.

# 2.	Consequences if not agreed:

Status quo, based on limited volunteer resources. Chances of additional cost later on to re-align diverging practices. Chances of loosing the benefit of current MTS developments.

# 3.	Detailed description:

## 3.1.	Subject title: "PROMOTION OF TC MTS ACTIVITIES AND TECHNICAL QUALITY PRACTICES IN ETSI"

## 3.2.	Reference TC: TC MTS

## 3.3.	Other interested TCs (if any): ALL

## 3.4.	Duration: 12 MONTHS

## 3.5.	Target date for the start of work: January 1996

## 3.6.	Necessary manpower (expertise, mix of skills and amount):

The estimate need for manpower is 6 person.months. The profile of experts should be as follows:

Experts need practical expertise in the standards making process; they shall have participated to projects in ETSI (STC work or PTs) developing standards, or in other standards bodies (ISO, ITU,...).

Experts should be knowlegdeable on the activities of TC MTS, and should have participated in these activities.

Experts should have a good presentation and communication abilities.

Experts are not required to be specialists in formal notations.

## 3.7.	Context of the study:

- The evolution of ETSI in the framework of the HLTF implementation: The definition of a new way for ETSI requires to be actively monitored, in particular the recommendation on standards validation (rec.31); positioning MTS in this evolving context is essential.

- The new works of TC MTS on quality of standards, validation, etc. that need to be publicized.

## 3.8.	Related activity in other bodies and necessary coordination of schedules:

As in the current phase of PT69V, all entities in ETSI: TCs, STCs, Secretariat, TA, HLTF Implementation Group, etc. Some entities outside may require communication, like associations of members, etc.

Related activities are the different missions of the Secretariat representatives (PEX, Technical editors), who are involved in the work of the different committees, and may carry some essential messages from TC MTS.

Existing vehicles, such as the Rapporteurs’ Survival Guide, will be used to convey to rapporteurs messages about the available techniques and tools.

## 3.9.	Scope of the terms of reference and relevant Work Items:

This PT should complete the communication plan of PT69V. It should take into account the new audience (HLTF Implementation Group and new entities that will emerge) and the new works of TC MTS that deserve to be publicized.

The emphasis on SDL made during the first phase of PT69V (specific material has been written on the subject, and seminars have been held) should not continue, this particular aspect being taken in charge by the PEX, and specific SDL deployment projects.

## 3.10.	Reference specification(s) and existing documents, including ETSI member contributions:

TC MTS (95) 09	PT69V Communication Plan

TC MTS (95) 10	The future in ETSI of Quality of standards-making, Validation and Testing, v.1.0

All deliverables from MTS, on specification, testing, validation.

Work on the ASN.1 library from SPS2: ETS 300 655; ETR 210; TCRTR 046; TCRTR 019; TCRTR 047.

## 3.11.	Work Item(s) from the ETSI Work Programme (EWP) for which the PT is required:

MI/MTS-00006

## 3.12.	Expected output(s):

a)	Revised communication plan;

b)	Communication material and actions;

c)	Progress report to TC MTS and European Commission.