Terms of Reference for PT 89 on ATS / PIXIT for V5.2 (extension PT54)

as approved by Technical Assembly 23

1.	Reason for Proposing a Project Team

The task for the project team 54 (PT54) was to do the conformance testing for both V5.1 and V5.2 standards. End of 1994 was the  PT54 closed with for the time reachable status of the task. The base standard was

1)	V5.1 interface	ETX 300 324-1 and PICS ETS 300 324-2

2)	V5.2 interface	ETX 300 347-1 and PICS ETS 300 347-2

This liaison statement is based on discussions with Mr. Andreas Malzach (PEX) and afterwards a fax that summarise the V5 status. The fax was addressed to PT54 members and ETSI Technical Editor.

Both the V5.1 and V5.2 ETSI interface standards have been published (part 1

and 2). V5.1 has come a little bit further than V5.2 which is natural.

The TSS&TP of the V5.1 CTS are currently on voting and also been validated by various companies and there are not any serious problems expected.

The TSS&TP of the V5.2 CTS are currently on PE and that differs from V5.1 because it has never been validated by anyone.

To obtain the same level of validation and quality of the V5.2 CTS as for V5.1 some work needs to be done.

The amendments for V5.2 also add some new functionality that today not are included in the CTS and ATS for V5.2.

SPS3 have to decide if a project team has to be set up (or a continuation of PT54). If so a work item must be defined with estimated work load of 4 men months.

2.	Consequence If Not Agreed

Many European Telecom manufacturers are working on V5.2 interfaces that provide Access Networks with concentration capability. The test specifications for V5.2 is an extremely important tool to ensure a certain degree of interworking between Access Networks and Local Exchanges. If no test specification is available, the V5.2 interface can not be classified as an open interface as specified by ONP.

3.	Detailed Description

3.1	Subject Title

Harmonising the V5.2 TSS&ATS&PIXIT to be in line with V5.2 specification and amendments.

3.2	Reference TC

ETSI TC SPS

3.3	Other Interested TC

ETSI TC MTS

3.4	Duration

One year.

3.5	Target Date for Start of Work

Beginning of 1996 but not before the resolution meeting of amendments for V5.2.

3.6	Necessary Manpower

4 man months are estimated as needed. 1 man month for the TSS&TP and 3 man months for the ATS&PIXIT. The repartision of work is as follows:

-	for the TSS&TP parts:	1 man month of V5 competence

-	for the ATS&PIXIT parts:	3 man month of PEX competence.

3.7	Context of Study

The mandate given by the TA (costed work programme).

3.8	Related Activities in Other Bodies and Necessary Co-ordination of 	Schedule

ETSI TC MTS for reusability  of ATS and test specification for object.

3.9	Scope of Terms of Reference and Relevant Study Items

Specification of amendments for the V5.2 TSS&TP&&ATS&PIXIT

3.10	Reference Specifications and Existing Document Including Member Contributions

ETS 300 347-1	V5.2 interface	(published)

ETS 300 347-2	V5.2 PICS interface	(published)

ETS 300 347-3	V5.2 ATS TSS&TP L3 AN	(PE 81)

ETS 300 347-4	V5.2 ATS&PIXIT L3 AN

ETS 300 347-5	V5.2 ATS TSS&TP L3 LE 	(PE 81)

ETS 300 347-6	V5.2 ATS&PIXIT L3 LE

ETS 300 347-7	V5.2 ATS TSS&TP L2 	(PE 81)

ETS 300 347-8	V5.2 ATS&PIXIT L2

ETS 300 347-9	V5.2 test L1	(PE 81)

ETS 300 347-1/A1	V5.2 interface	(for STC approval in October 1995)

ETS 300 347-2/A1	V5.2 PICS	(for STC approval in October 1995)

3.11	Part of ETSI Work Programme (EWP) for which the PT is required

DE/SPS-03003.1	V5.2 TSS & TP, L3 AN
DE/SPS-03003.2	V5.2 TSS & TP, L3 LE
DE/SPS-03003.3	V5.2 TSS & TP, L2
DE/SPS-03003.5	V5.2 TSS & PIXIT, L3 AN
DE/SPS-03003.6	V5.2 TSS & PIXIT, L3 LE
DE/SPS-03003.7	V5.2 TSS & PIXIT, L2

The base protocol standards to which the V5.2 TSS, TP and PIXIT refer are in Work Items:

RE/SPS-03035-1	Interface spec. V5.2
RE/SPS-03035-2	PICS

3.12	Expected Output

Amendments for all affected parts of the V5.2 interface:

ETS 300 347-3/A1	V5.2 ATS TSS&TP L3 AN	[RE/SPS-03xxx-1]

ETS 300 347-4/A1	V5.2 ATS&PIXIT L3 AN	[RE/SPS-03xxx-2]

ETS 300 347-5/A1	V5.2 ATS TSS&TP L3 LE 	[RE/SPS-03xxx-3]

ETS 300 347-6/A1	V5.2 ATS & PIXIT L3 LE 	[RE/SPS-03xxx-4]

ETS 300 347-7/A1	V5.2 ATS TSS&TP L2	[RE/SPS-03xxx-5]

ETS 300 347-8/A1	V5.2 ATS & PIXIT L2	[RE/SPS-03xxx-6]

3.13	Reporting Arrangements

Co-ordination of the project team work shall be performed by STC SPS3. The members of the project team shall provide progress reports including up-to-date versions of the expected deliverables.