|  | ToR STF 349 (TB MTS) |
| --- | --- |
|  | Version: 2.2 - Date: 25 April 2008 |
|  | Author: Ina Schieferdecker |
|  | Last updated by: Gyorgy Rethy / Alberto Berrini |
|  | page 1 of 12 |

Terms of Reference for Specialist Task Force STF 349
(TB MTS) on ”TTCN-3 extensions”

Document status

| Current status of these ToR | For OCG#35/Board#67 approval. |
| --- | --- |
| ToR TB approval reference | These ToR have already been approved by TC MTS. Ref: MTS#45, 46TD39 |
| Work Items approved | Yes |

# Reasons for proposing the Specialist Task Force (STF)

Over the last few years TC MTS has put a considerable amount of effort into specifying the third generation of the standardised testing language TTCN (known as TTCN-3). The language is also an ITU-T recommendation (Z.140 series).

TTCN-3 has become a significantly important testing technology with very high deployment at some ETSI member companies. With the decision of 3GPP RAN5 and TISPAN to move to TTCN-3 from Release 8 onwards and with the uptake by the WiMAX Forum, its role is becoming even more important in standardization. Hence there is a real need to address a number of outstanding extension and maintenance issues.

This resource extension request is due to the changed situation: As a result of an analysis performed by TF160, 3GPP RAN5 have come with new TTCN-3 language requirements and new language issues that were not known when the original STF349 resource request was written.

These new requirements were communicated to MTS in a liaison in March 2008 (attached to the present document as Annex 1).

MTS have considered this request positively, and accepted to work on solutions for the CRs raised by RAN5 with the highest priority. However, this has been at the expense of the pre-existing CRs that STF349 was established to resolve.

As a result, an interim release of the TTCN-3 standards (v3.4.1) will be presented to MTS in time for approval in June 2008. The release will cover the all 3GPP RAN / RAN5 requirements received.

This additional interim release will enable TTCN-3 tool providers to implement these features in due time and thus support the work of 3GPP RAN5.

However as the original budget allocation for STF349 did not encompass this extra piece of work (which has been treated with high priority and will be finished by end of June) the current remaining resource will not suffice to cover the original target that MTS had originally set for STF349.

For these reasons TB MTS asks additional resource in order to cover 2 work sessions (2 x 1 week) for the four STF349 experts.

## Overview of the proposal

### Purpose of the work

The extension work will comprise the following tasks:

Review and resolve open change requests by 3GPP and prepare an intermediate version of the TTCN-3 standard capturing the solutions for the 3GPP-related issues

Review and resolve change requests by ETSI members and the TTCN-3 community, develop proposals for agreed extensions, and develop proposals to solve indicated technical defects

Implement agreed solutions

Manage change request (CR) process

### Relation with the ETSI Strategic Objectives

This STF directly supports the ETSI strategic objectives "Interoperability and Testing" and "Next Generation Networks (NGN)".

### Market impact, benefits to be gained

Strategic importance behind the work: the decision of 3GPP RAN5 and TISPAN to move to TTCN-3 from Release 8 onwards triggered an urgent need to address various TTCN-3 extensions to increase the applicability of TTCN-3 for 3GPP.

### Stakeholders interest

Today as the 3GPP test teams have started to use TTCN-3 as their Conformance and Benchmarking test suites development language, the biggest potential stakeholder is the 3GPP community: operators, equipment manufacturers and test equipment manufacturers.

### Relation with other activities within ETSI and/or related organizations

TTCN-3 is THE programming language used by all ETSI TBs producing conformance test suites. It is also used for benchmarking test suites, interoperability test suites and interworking test suites.

### Priority within the TB

This NEW STF proposal has a HIGH priority in order to enable the further spread of TTCN-3 in 3GPP.

### Motivation why the work cannot be performed within the TB

The parts mentioned in clause 3.14 are of high importance, they require an intensive effort to analyse the extension requests listed in clause 1.2.1 and change requests captured in the Mantis CR system for TTCN-3. Only by concerted efforts the changes can be implemented within the time period required by 3GPP.

In parallel, MTS is also maintaining the other parts of the TTCN-3 standards on a voluntary basis, however these parts are of a lesser importance and do not require the same level of urgency

### Stakeholders’ interest and active support from the ETSI Members

The following MTS members have indicated a high interest for this maintenance activity, they are already involved in the ttcn-3 maintenance work on a voluntary basis and will actively follow and support the STF team:

Telefon AB LM Ericsson

Nokia Siemens Networks GmbH

IITB

FOKUS

Testing Technologies

Siemens

## Organization of the work

### Identification of tasks, phases, priorities, technical risk

The STF will develop TTCN-3 extensions for the following TTCN-3 extension requests:

- Parameterization

type parameterization of types

function/altstep-type formal parameters

default values of formal parameters or overloading

assignment notation in actual parameter lists

passing omit to value parameters

- Library support

Identifying library-internal functions and data

Function references

Runs on self in function reference type definitions

- Configuration and deployment support

Static test configuration

Calling test cases from running test components

Support of test component distribution

Parallel execution of test cases

Test component synchronization

- Interworking with other languages

- Update ASN.1 to TTCN-3 mapping to the latest ASN.1 recommendations

The bullet items for extension 1) to 4) define the proposals to be considered, but not necessarily that for every proposal an extensions will be implemented in TTCN-3.  Still, for 1) to 3) appropriate language support in TTCN-3 will be provided. The appropriateness of solutions will be discussed with the TTCN-3 steering committee.

In addition, the STF will develop solutions for 5) and 6) As these are however less clear, the solutions will be first applied in representative case studies by ETSI members, so that the feedback can be used to assess the appropriateness of the TTCN-3 extensions for later implementation in the standard itself.

- Real-time, simulated time and performance extensions

Real-time semantics

Timing constraints

Support for simulated time

- Other advanced TTCN-3 features

Improved error handling (exception handling, isbound)

Break-continue support

Hex representation for integers

Macro definitions

Time-constraint send operations

Some new predefined functions (record/set of manipulation)

Features for more flexible logging

Sending templates over connected ports

In addition, the new CRs in Mantis will be handled. The CRs can be reviewed via:

http://t-ort.etsi.org/view_all_bug_page.php?project_id=22

### Outcome of the STF

See clauses 3.15 and 3.16.

# Consequences if not agreed:

The transition of 3GPP to TTCN-3 testing technology will potentially be put at risk, if this extension and maintenance work is not done. The uptake and usefulness of the language will be adversely affected, thus jeopardizing ETSI’s significant contribution to this work.

Also, a number of proposed extensions are CRed by ETSI member companies, using the language. If these are not addressed within a limited amount of time, tool-specific solutions do appear that endanger the compatibility and re-usability of the TTCN-3 code base.

If the request for the additional allocation in clause 3.8 is not agreed, the original targets of STF349, i.e. edition 4 of the TTCN-3 language, would be put on threat. Thus both ETSI members and the TTCN-3 community would suffer.

# Detailed description:

## Subject title:

TTCN-3 extensions

## Reference Technical Body:

MTS

## Other interested TBs (if any):

3GPP, TC TISPAN, TC BRAN

These TBs use TTCN-3 as test suites development language.

WiMAX Forum is using TTCN-3 to develop and maintain a conformance test suite.

## Steering Committee

MTS Committee has established a TTCN-3 Steering Group for the direct steering of TTCN-3 maintenance STFs that will closely follow the progress of this STF. STF outputs will also be reviewed and approved by TC MTS. It is very likely that some active TC MTS members will apply to be involved in this STF and will hence be in direct contact with TC MTS via the usual communication means (MTS_GEN mailing list, MTS face-to-face meetings, conference calls).

Support from the CTI department will also be requested and is seen as being vital to the success of this work.

## Support from ETSI Members

- Dr. György RÉTHY, Telefon AB LM Ericsson

- Dr. Colin WILLCOCK, Nokia Siemens Networks GmbH

- Prof. Dieter HOGREFE, IITB

- Prof. Ina SCHIEFERDECKER, FOKUS

- Theofanis VASSILIOU-GIOLES, Testing Technologies IST GmbH

The above mentioned members are members of the TTCN-3 SG of MTS and will be actively involved in the follow-up of the STF work.

## Target date for the start of work:

1 March 2008

## Duration and target date for the conclusion of the work (TB approval):

Until December 2008

## Resources required

Total additional resource required: 2 sessions of 1 week for the four current experts:

40 days, equivalent to 24 000 EUR

### Experts manpower

Total manpower resources required for drafting/updating of deliverables: 40 working days (24 000 EUR)

### Travel cost:

Two MTS meetings are scheduled to be held in Sophia Antipolis during the duration of this STF (MTS#46 and MT#47). STF representation at those MTS meetings will be a voluntary contribution. Additional cost: 0 EUR

### Other cost:

None

## Experts qualification required, mix of skills

Essential skills in TTCN-3 and Conformance Testing are needed.

Additional skills in ASN.1 and compiler theory would be appreciated.

Support from the CTI will be vital to the success of this work.

The current four experts of the STF have the required skills to take over this work.

## Scope of Terms of Reference:

See Clause 1

## Organization of the work in tasks and/or phases:

The work will be organized in sessions located in ETSI premises, no phases are required as the STF duration will not exceed 12 months.

Tasks are described in clause 1.1.1.

## Validation

Not applicable

## Related activity in other bodies and co-ordination of schedules:

The STF should co-ordinate with:

ETSI TBs such as TISPAN and 3GPP;

ITU-T SG17 Q.6

ISO/IEC

## Base documents and their availability

TTCN-3 v3.2.1 as indicated below:

ES 201 873-1 	3.2.1	TTCN-3: Core Language

ES 201 873-2 	3.2.1	TTCN-3: TFT

ES 201 873-3	3.2.1	TTCN-3: GFT

ES 201 873-4	3.2.1	TTCN-3: OS

ES 201 873-5	3.2.1	TTCN-3: TRI

ES 201 873-6	3.2.1	TTCN-3: TCI

ES 201 873-7	3.1.1	TTCN-3: Using with ASN.1

These base documents are all published.

The STF work will also be based upon the following documents.

| Work Item | Title | Start of work | Stable draft | TB approval | Publication (after MAP) |
| --- | --- | --- | --- | --- | --- |
| RES/MTS-00090-1 [3] | TTCN-3 Core Language | 15/09/07 | 01/10/07 | 25/12/07 | April 2008 |
| RES/MTS-00090-5 [3] | TTCN-3 Edition 3: TRI | 15/09/07 | 01/10/07 | 25/12/07 | April 2008 |
| RES/MTS-00090-6 [3] | TTCN-3 Edition 3: TCI | 15/09/07 | 01/10/07 | 25/12/07 | April 2008 |
| RES/MTS-00090-7 [3] | Using ASN.1 with TTCN-3 | 15/09/07 | 01/01/08 | MTS#46 | April 2008 |
| DES/MTS-00090-9 | Using XML with TTCN-3 |  |  | 18/04/08 | 18/06/08 |

## Work Items from the ETSI Work Programme (EWP) for which the STF is required:

To meet 3GPP's strict timescale the STF will produce an interim set of TTCN-3 documents identified as “Edition 3.4.1” listed below:

| Work Item | Title | Start of work | Final draft | TB approval | Publication (after MAP) |
| --- | --- | --- | --- | --- | --- |
| RES/MTS-00108-1 T3 ed341 core | TTCN-3 Edition 3.4.1 Core Language | 01/03/08 | 30/05/08 | 27/06/08 | Sept 2008 |
| RES/MTS-00108-4 T3 ed341 OS | TTCN-3 Edition 3.4.1 Operational Semantics | 01/03/08 | 30/05/08 | 27/06/08 | Sept 2008 |
| RES/MTS-00108-6 T3 ed341 TCI | TTCN-3 Edition 3.4.1: Control Interface | 01/03/08 | 30/05/08 | 27/06/08 | Sept 2008 |
| RES/MTS-00108-10 T3 ed341 DOC | TTCN-3 Edition 3.4.1 documentation tags | 01/03/08 | 30/05/08 | 27/06/08 | Sept 2008 |

The STF will also carry on it work on the fourth edition, revision 4.1.1 of the TTCN-3 documents listed below according to the following time scale for TB approval:

| Work Item | Title | Start of work | Final draft | TB approval | Publication (after MAP) |
| --- | --- | --- | --- | --- | --- |
| RES/MTS-00107-1 T3 ed4 core | TTCN-3 Edition 4.1.1Core Language | 01/03/08 | 12/12/2008 | 09/01/2009 | April 2009 |
| RES/MTS-00107-4 T3 ed4 OS | TTCN-3 Edition 4.1.1Operational Semantics | 01/03/08 | 12/12/2008 | 09/01/2009 | April 2009 |
| RES/MTS-00107-5 T3 ed4 TRI | TTCN-3 Edition 4.1.1 TRI | 01/03/08 | 12/12/2008 | 09/01/2009 | April 2009 |
| RES/MTS-00107-6 T3 ed4 TCI | TTCN-3 Edition 4.1.1 TCI | 01/03/08 | 12/12/2008 | 09/01/2009 | April 2009 |
| RES/MTS-00107-7 T3 ed4 asn1 | Use of ASN.1 with TTCN-3 Edition 4.1.1 | 01/03/08 | 12/12/2008 | 09/01/2009 | April 2009 |
| RES/MTS-00107-9 T3 ed4 XML | Use of XML with TTCN-3 Edition 4.1.1 | 01/03/08 | 12/12/2008 | 09/01/2009 | April 2009 |

## Planned output schedule:

The STF will produce the deliverables according to the following time scale:

TTCN-3 Edition 3.4.1:

|  | RES/MTS-00108-1 T3 ed341 core | ES 201 873-1 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 3.4.1 Core Language |
| title: | Methods for Testing and Specification (MTS); |  |
|  | The Testing and Test Control Notation version 3; |  |
|  | Part 1: TTCN-3 Core Language |

|  | RES/MTS-00108-4 T3 ed341 OS | ES 201 873-4 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 3.4.1 OS |
| title: | Methods for Testing and Specification (MTS); |  |
|  | The Testing and Test Control Notation version 3; |  |
|  | Part 4: TTCN-3 Operational Semantics |

|  | RES/MTS-00108-6 T3 ed341 TCI | ES 201 873-6 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 3.4.1: TCI |
| title: | Methods for Testing and Specification (MTS); |  |
|  | The Testing and Test Control Notation version 3; |  |
|  | Part 6: TTCN-3 Control Interface (TCI) |

|  | RES/MTS-00108-10 T3 ed341 DOC | ES 201 873-10 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 3.4.1 documentation tags |
| title: | Methods for Testing and Specification (MTS); |  |
|  | The Testing and Test Control Notation version 3; |  |
|  | Part 10: TTCN-3 Documentation Comment Specification |

| Status | Milestone | Target Date |
| --- | --- | --- |
| 0 |  | Creation of WI by WG/TB | 2008-03-19 |
| 0 | a | TB adoption of WI | 2008-03-19 |
| 1 |  | Start of work | 2008-03-19 |
| 5 | S | Early Draft | 2008-04-25 |
| 5 | S | Final Draft - ready for approval | 2008-05-30 |
| 7 | A | Start of TB approval process | 2008-05-30 |
| 7 | B | End of TB approval process | 2008-06-27 |
| 8 |  | TB approval | 2008-06-27 |
| 10 | FM | Start of Membership Vote | 2008-07-18 |
| 10 | GM | End of Membership Vote | 2008-09-16 |
| 11 |  | Vote result determination (adopted) | 2008-09-16 |
| 12 |  | Publication | 2008-09-30 |

TTCN-3 Edition 4.1.1:

|  | RES/MTS-00107-1 T3 ed4 core | ES 201 873-1 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 4.1.1 Core Language |
| title: | Methods for Testing and Specification (MTS); |  |
|  | The Testing and Test Control Notation version 3; |  |
|  | Part 1: TTCN-3 Core Language |

|  | RES/MTS-00107-4 T3 ed4 OS | ES 201 873-4 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 4.1.1 OS |
| title: | Methods for Testing and Specification (MTS); |  |
|  | The Testing and Test Control Notation version 3; |  |
|  | Part 4: TTCN-3 Operational Semantics |

|  | RES/MTS-00107-5 T3 ed4 TRI | ES 201 873-5 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 4.1.1: TRI |
| title: | Methods for Testing and Specification (MTS); |  |
|  | The Testing and Test Control Notation version 3; |  |
|  | Part 5: TTCN-3 Runtime Interface (TRI) |

|  | RES/MTS-00107-6 T3 ed4 TCI | ES 201 873-6 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 4.1.1: TCI |  |
| title: | Methods for Testing and Specification (MTS); |
|  | The Testing and Test Control Notation version 3; |
|  | Part 6: TTCN-3 Control Interface (TCI) |

|  | RES/MTS-00107-7 T3 ed4 asn1 | ES 201 873-7 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 4.1.1: the Use of ASN.1 |  |
| title: | Methods for Testing and Specification (MTS); |
|  | The Testing and Test Control Notation version 3; |
|  | Part 7: Using ASN.1 with TTCN-3 |

|  | RES/MTS-00107-9 T3 ed4 XML | ES 201 873-9 |
| --- | --- | --- |
| working title: | TTCN-3 Edition 4.1.1: the Use of XML |  |
| title: | Methods for Testing and Specification (MTS); |
|  | The Testing and Test Control Notation version 3; |
|  | Part 9: Using XML with TTCN-3 |

| Status |  | Milestone | Target Date |
| --- | --- | --- | --- |
| 0 |  | Creation of WI by WG/TB | 2007-09-21 |
| 1 |  | Start of work | 2008-03-01 |
| 5 | S | Stable Draft | 2008-10-01 |
| 5 | S | Final Draft - Ready for Approval | 2008-12-12 |
| 7 | A | Start of TB approval process | 2008-12-12 |
| 7 | B | End of TB approval process | 2009-01-09 |
| 8 |  | TB approval | 2009-01-09 |
| 10 | FM | Start of Membership Vote | 2009-02-06 |
| 10 | GM | End of Membership Vote | 2009-04-07 |
| 11 |  | Vote result determination (adopted) | 2009-04-07 |
| 12 |  | Publication | 2009-04-21 |

In addition, the STF will produce the following reports:

- Final Report 	31/12/08

# Performance indicators

The STF performance will be indicated by the timely availability of the new TTCN-3 versions 3.4.1 and v4.1.1 (in cooperation with MTS), by the growing application of TTCN-3 by other technical bodies (as essential language extensions will be implemented) and by the timely deployment of the new TTCN-3 features in a range of TTCN-3 tools (by interaction with TTCN-3 tool vendors).

# ANNEX 1: Liaison Statement from 3GPP RAN5 to MTS (March 2008)

The liaison hereafter was dealt with during the MTS#46 meeting as 46TD12, a liaison response was sent to RAN & RAN5 as 46TD38r2.

Liaison Statement

| Title: | TTCN3 LTE Related Concerns |
| --- | --- |

| From: |  |
| --- | --- |
| Organisation: | 3GPP TSG RAN WG5 |
| Approval Date: |  |
| Technical Contact: | Phil Brown phillip-ml@nttdocomo.co.jp |
| Reply to: | Phil Brown phillip-ml@nttdocomo.co.jp |

| To: |  |
| --- | --- |
| Organisation: | ETSI MTS |
| Contact Person: | Dieter Hogrefe |
| e-mail: | hogrefe@informatik.uni-goettingen.de |

| For: |
| --- |
| Action: | X |
| Information: |  |

1. Overall Description:

During the review of the TF 160 report at RAN5#38, a number of concerns were raised regarding the rate at which critical corrections can be updated into the current TTCN3 due mainly to infrequency of updates and publications of the TTCN3 core specifications.

RAN5 cannot emphasise enough to ETSI MTS the critical importance of the early development of ATS in TTCN3 in support of the LTE signalling test case programme and that any delays in this development will have serious consequences for the LTE programme as a whole. Furthermore, RAN5 is becoming increasingly concerned about the lack of support from TTCN3 tool vendors in this respect.

RAN5 appreciates that there will always be resource issues but asks to treat all requests for changes from RAN5 (via TF 160) with the highest priority and to further strongly encourage better support from the test tool vendors. Finally RAN5 asks that ETSI MTS provides a written update on LTE related progress, to be presented by the TF160 manager at each of the RAN5 quarterly meetings.

2. Actions:

To ETSI MTS

ACTION:

RAN5 kindly asks to treat all requests for TTCN3 changes from RAN5 (via TF 160) with the highest priority and to further strongly encourage better support from the test tool vendors. Particularly, the outstanding change requests raised in 2007 from RAN5 (via TF 160) must be resolved and published by the mid of 2008.

RAN5 also asks that ETSI MTS provide a written update on LTE related TTCN3 standards progress, to be presented by the TF160 manager at each of the RAN5 quarterly meetings.

3. Date of Next TSG-RAN WG5new Meetings:

TSG-RAN WG5 Meeting #39	5 - 9 May 2008		Kansas City

TSG-RAN WG5 Meeting #40	18 – 22 Aug 2008	Seoul

# Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 1.0 | 19 Sept 07 | MTS | Proposed for Approval MTS#45 | First draft ToR |
| 1.1 | 21 Sept 07 | MTS | Proposed for Approval MTS#45 | Revised draft ToR |
| 2.0 | 18 Mar 08 | MTS | Approved MTS#46 | Revised ToR. Additions due to new 3GPP requirements are inserted. |
| 2.1 | 25 Apr 08 | G. Rethy |  | Text tuned, Edition 3.4.1 new WIs added, Edition 4.1.1 WIs schedules updated, RAN5 Liaison added as annex 1. |
| 2.2 | 5 May 08 | Berrini | For Board#67 approval | Editorials |