|  | ToR STF AB (TC RRS/WG3) |
| --- | --- |
|  | Version: 1.4 |
|  | Author: Markus Mueck – Date:23 April 2015 |
|  | Last updated by: Alberto Berrini – Date:9 September 2015 |
|  | page 1 of 10 |

Terms of Reference - Specialist Task Force

STF AB (TC RRS/WG3)

Reconfigurable Radio Security

Summary information

| Approval status | Approved by RRS#30 (5-6 June 2015) Approved by Board#103 (9-10 June 2015) with allocated budget 52 000 € |
| --- | --- |
| Funding | TC request (these ToR): 65 400 € 134 working days (104 days remunerated = 62 400 € and 30 days voluntary contribution = 22% of total manpower) and 3 000 € for travels. |
| Time scale | Mid-September 2015 to 10 March 2016 |
| Work Items | DTR/RRS-03010 (TR 103 087) Security related use cases and threats in Reconfigurable Radio Systems DTS/RRS-03012 Security Requirements for reconfigurable radios |
| Board priority | Emerging domains for ETSI |

Part I – Reason for proposing the STF

# Rationale

Reconfigurable radio solutions for a more efficient use of the spectrum (e.g., cognitive radio in general and white spaces solutions in particular) or reconfigurable mobile devices are gaining momentum. In particular, the new Radio Equipment Directive (RED) mentions related Software Reconfiguration Mechanisms in Articles 3(3)(i) and 4. However, security aspects have to be taken into consideration before those same solutions can be safely deployed. This means that security threats have to be properly investigated and measures to overcome those same threats developed. With the creation of a Technical Specification defining the security requirements related to reconfigurable radio systems, it will be possible to have a baseline for the improvements of the related reconfigurable architectures which are currently under development in TC RRS.

# Objective

The objective of this STF proposal is to i) identify security threats, ii) identify available countermeasures, iii) identify a lack of countermeasures and define the security requirements related to reconfigurable radio systems. Security requirements are essential for defining reconfigurable radio architectures, for instance for defining the reconfigurable radio architecture for Mobile Devices.

# Relation with ETSI strategy and priorities

This action supports the ETSI Long Term Strategy item(s) to:

create high quality standards for global use and with low time-to-market

stay in tune with changing nature of the global ICT industry (innovation)

establish leadership in key areas impacting members' future activities

This action has a priority category of “Emerging Domain for ETSI”.

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Intel | Markus Mueck | Mobile Device chipsets |
| Hanyang University | Choi, Seungwon | Very important topic for research |
| BMWi | Paul Bender | Reconfigurable radio security is very important for placing products on the market |
| LG | Vladimir Ivanov | Security is very important for reconfigurable mobile devices |
| NSN | Gundlach, Michael | Very important for an efficient management of the network as well |
| Ministry of Economic Affairs - Netherlands | Ben Smith | Security is also linked to spectrum use: the more secure, the more trust in these new techniques, and the better spectrum can be utilized |
| Joint Research Center of the European Commission (JRC) | Support as ETSI counsellor | Security is also linked to spectrum use: the more secure, the more trust in these new techniques, and the better spectrum can be utilized |
| University of Bradford | Fun Hu | very important topic for research |

## Market impact

Reconfigurable Radio platforms have been used for a long time (for instance in Base Stations) although the solutions have been always proprietary. With the development of standardised solutions for new advanced features such as cognitive radio, it is expected that more and more devices will make use of a reconfigurable implementation. While the market impact is not quantifiable now, it is clear that much will depend on the reliability of such solutions not only in terms of QoS but also in terms of security. If proven reliable, it could even open a completely new market of so called “radio apps”.

## Tasks that cannot be done within the TB and for which the STF support is necessary

The identification of the security requirements for reconfigurable platforms requires a deep knowledge of SW and HW security aspects, which are not generally available in the Technical Committee.

## Related voluntary activities in the TB

Delegates within TC RRS and TC RRS WG3 will review the deliverable in order to evaluate the impact of security requirements on the reconfigurable architectures (reconfigurable Mobile Device architecture, LSA related architecture, White Space related architecture, etc)

## Outcome from previous funded activities in the same domain

This is the first time TC RRS requests funding for an STF.

## Consequences if not agreed

Reconfigurable platforms have been used for a long time but, until now, the solutions have been proprietary and (radio) reconfigurability has been limited and decided by the manufactures themselves, which has limited the vulnerability of the platforms to cyber-attacks. Future reconfigurable platforms, such as mobile devices, are expected to be more open: for instance a reconfigurable mobile device might be (radio) reconfigured by a third-party application. Even the new Radio Equipment Directive (RED) introduces new specific requirements related to software reconfiguration of radio equipment and security aspects will be very important for fulfilling those same requirements.

Security requirements are therefore of paramount importance in order to make the reconfigurable platform future-proof and secure. If these requirements are not properly defined, there is a high risk that a reconfigurable platform, wherever applied, will be “weak” and therefore could be subjects to cyber-attacks, which could damage not only the end user (denial of service, decrease in QoS, etc.) but also the overall management of the radio spectrum.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TC RRS WG3 (Chairman: Dr. Markus Mueck) will be the leading group within TC RRS

## Other interested ETSI Technical Bodies

Support of TC CYBER may be required to help defining the security requirements.

Support from TC ERM for solutions related to Software Reconfiguration mechanisms related to Articles 3 (3) (i) and 4 of the Radio Equipment Directive (RED)

## Other interested Organizations outside ETSI

Wireless Innovation Forum (WINNF), ETSI Partner, which has been involved in Software Defined Radio (SDR) related activities for a very long time.

# Working method/approach

## Organization of the work

The work will be steered by TC RRS WG3. Three WG meetings and a number of dedicated phone calls/remote sessions are planned before formal TB approval from August 2015 to March 2016.

## Base documents

| Document | Title | Current Status |
| --- | --- | --- |
| TR 102 967 | Use Cases for Dynamic Equipment Reconfiguration | Published |
| TS 102 969 | Radio Reconfiguration related Requirements for Mobile Devices | Published |
| TS 103 146-1 | Mobile Device Information Models and Protocols; Part1:Multiradio Interface (MURI) | Published |
| TS 103 146-2 | Mobile Device Information Models and Protocols; Part2:RRFI | Published |
| TS 103 095 | Radio Reconfiguration related Architecture for Mobile Devices | Published |
| EN 302 969 | Radio Reconfiguration related Requirements for Mobile Devices | Published |
| DTR/RRS-03010 (TR 103 087) | Security related use cases and threats in Reconfigurable Radio Systems | Early draft |

NOTE: these use cases do not include security aspects.

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | DTR/RRS-03010 (TR 103 087) | Security related use cases and threats in Reconfigurable Radio Systems |
| D2 | DTS/RRS-03012 | Security Requirements for reconfigurable radios |

## Deliverables schedule:

DTR/ RRS-03010 Security related use cases and threats in Reconfigurable Radio Systems

Start of work	15-09-2015 	RRS#31

Stable draft	23-11-2015	RRS#32

WG approval	29-02-2016

TB approval	03-03-2016	RRS#33

Publication	10-04-2016

DTS/ RRS-03012 Security Requirements for Reconfigurable Radio Systems

Start of work	15-09-2015	RRS#31

ToC and scope	23-11-2015	RRS#32

Final draft	12-02-2016

WG approval	29-02-2016

TB approval	03-03-2016	RRS#33

Approval by RC	31-03-2016

Publication	10-04-2016

## Work plan, time scale and resources

| N | Task / Milestone / Deliverable | From | To | Contracted experts (days total) |  |
| --- | --- | --- | --- | --- | --- |
| M0 | Start of work | 15-09-2015 |  |  |
| T0 | Project management | 15-09-2015 | 03-03-2016 |  |  |
| T1 | Description of use cases | 15-09-2015 | 23-11-2015 | 20 (30) |  |
| T2 | Definition of threats for reconfigurable radios | 15-09-2016 | 23-11-2015 |  | 15 (25) |
| T3 | Definition of security requirements | 15-09-2015 | 23-11-2015 | 10 (15) |  |
| M1 | Use case stable draft for WG (RRS WG3#28) | 23-11-2015 |  |  |
| T4 | WG3 review (DTR/RRS-03010) | 23-11-2015 | 20-12-2015 | 10 |  |
| T5 | Review of use case deliverable | 23-11-2015 | 03-03-2016 |  |  |
| M2 | Security requirements stable draft for WG review | 26-01-2016 |  |  |
| T6 | Development and WG3 review (DTS/RRS-030XX) | 23-11-2015 | 05-02-201635 | 35 (42) |  |
| T7 | Review of security requirement deliverable | 08-02-2016 | 12-02-2016 | 5 |  |
| M3 | Stable drafts for TB review | 15-02-2016 |  |  |
| T8 | Finalisation of deliverables | 18-02-2016 | 23-02-2016 | 7 |  |
| M4 | Final drafts for TB approval | 29-02-2016 |  |  |
| M5 | TB approval (RRS#29) | 03-03-2016 |  |  |
| M6 | STF Final Report | 03-03-2016 |  |  |
| M7 | Publication | 10-03-2016 |  |  |
| Work plan with budget granted by Board#103 (Priority 1 only) Work plan for TC RRS requirement (requires budget extension) | 102 (134) |  |

## Task and milestone description

Task 1 – Description of use cases

Definition of use cases which can give raise to possible threats;

Objectives for tasks 1, 2 and 3

Use-cases at Radio Application Package level (priority 1)

Use cases for handling of Statement of Conformity (StoC) related to RE-Directive e.g. certificate chain, history file (priority 2)

Input

RRS documents

  - ETSI TR 102 967, Use Cases for Dynamic Equipment Reconfiguration

  - ETSI TS 102 969, Radio Reconfiguration related Requirements for Mobile Devices

  - ETSI TS 103 146-1, Mobile Device Information Models and Protocols; Part1:Multiradio Interface (MURI)

  - ETSI TS 103 146-2, Mobile Device Information Models and Protocols; Part2:RRFI

  - ETSI TS 103 095, Radio Reconfiguration related Architecture for Mobile Devices

  - ETSI EN 302 969, Radio Reconfiguration related Requirements for Mobile Devices

  - ETSI TR 103 062, Use Cases and Scenarios for Software Defined Radio (SDR)

European Reconfigurable Radio Equipment Directive (RED)

  - DIRECTIVE 2014/53/EU OF THE EUROPEAN PARLIAMENT AND OF THE COUNCIL of 16 April 2014 on the harmonization of the laws of the Member States relating to the making available on the market of radio equipment and repealing Directive 1999/5/EC

WINNF (Wireless Innovation Forum)

  - WINNF-08-P-0013 “Securing Software Reconfigurable Communications Devices”

TCG

  - Trusted Platform Module (TPM) use cases, architecture, threat analysis

Output:

Draft of use-case deliverable (11 UC’s identified, in order of priority to be determined during initial phase of the STF to assure TC RRS that the use cases selected for detail analysis address the maximum coverage of contexts and stakeholders)

Priority 1: Use-cases related to Radio Application Package (RAP) life-cycle (7 UC):

  - transmission,

  - installation,

  - un-installation,

  - instantiation

  - de-instantiation,

  - activation

  - de-activation

Priority 2: Use-cases related to Statement of Conformity (4 UC)

  - installation,

  - query,

  - update,

  - validation

Interactions

RRS WG3

Regulators:  administrative requirements, management of certification

Deployment models for Radio Application Packages

Review

TC CYBER

Presentation and peer review

WINNF

Identify existing solutions, inform TC RRS if applicable

ISG NFV

Inform TC RRS on protection methods for virtualized functions

TC ESI

Inform TC RRS on Signature and Certificates management

Task 2 – Definition of threats for reconfigurable radios

Definition of threats based on the identified use cases, using the Threat Vulnerability Risk Analysis (TVRA) method as defined in ETSI TS 102 165–1;

Input

same as task 1

existing research on relevant threats, attack vectors, vulnerabilities (e.g. for Cognitive Radio, package signature)

Output

- For each use case in Task 1, definition of assets, threats, threat agents, weaknesses, risk

Interactions

- Same as task 1

Task 3 – Definition of security requirements

Based on the identified threats, a first set of security requirements is identified

Input

- The outputs of tasks 1 and 2

Output

- Preliminary draft of DTS/RRS-03012 identifying in outline the potential security measures applicable to mitigate threats

Interactions

- RRS WG3 for review and detailed discussion

- TC CYBER for review

Resource requirement:

It should be noted that tasks 1, 2 and 3 have to be performed together for each use case.

Resources allocated to STF: For Task 1 = 20 days, Task 2 = 15 days, for Task 3 = 10 days. As these tasks will be undertaken in parallel, the individual allocations may change with the constraint that the total allocation across these tasks shall not exceed 45 days with the current budget allocation.

We expect to require at least 35 days to perform an analysis on priority 1 use cases (Radio Application Package). Within the currently allocated budget, this will limit the ability to handle priority 2 Use Cases (Certificate of Conformity) as there will be less than 10 days left. The later use cases should however not be neglected, since they are key to enable regulatory compliance of Reconfigurable Radio Systems.

Early interactions with RRS delegates indicate that the handling of Statement of Conformity is still under discussion within RRS and that an in-depth security analysis would be highly valuable also in order to influence the design of Statement of Conformity management. A budget allocation to the level of the initial request of 65 400 € would allow for proper contribution in this area by allocating 25 additional days within tasks 1, 2, and 3, and 7 additional days to task 6.

Milestone 1 – Use case stable draft for WG3 review

Stable draft DTR/RRS-03010 (TR 103 087) for WG3 review in RRS#32 Mainz, 23-27 November).  Document must be submitted one week before the start of the meeting.

Task 4 – WG3 review (DTR/ RRS-03010)

The Stable draft DTR/RRS-03010 will be distributed to RRS WG3 mailing list for review as well as to TC CYBER mailing list for comments (2 weeks planned, including the RRS#32 meeting).  Comments must then be available for the STF before 4 December.

Task 5 – Review of use case deliverable (DTR/RRS-03010)

Update the technical report on use cases and threats according to the comments received from RRS WG3 and possible comments from TC CYBER and produce a final draft for RRS WG3 review.

Output: Final draft for WG approval available by mid-February

Resources required:

See comment above. For this particular activity, the STF shall assign to task 4 and task 5 10 days in combination (depending on the results of the review period this assignment between the tasks may be flexible).

Milestone 2 – security requirements Final draft for WG review and TC CYBER review

The draft DTR/RRS-03010 will be distributed to RRS WG3 mailing list for final review by RRS#32 and RRS#33, 29 February – 4 March 2016, Paris (tbc), as well as TC CYBER mailing list for comments (2 weeks planned)

Task 6 – WG and TC CYBER review (DTS/RRS-03012)

The development of DTS/RRS-03012 will proceed in parallel to TR 103 087.

ToC and Scope and highlight content will be presented to RRS#32 (Mainz).

The Final Draft will be presented to RRS#33 (Paris).

The deliverable will be distributed to RRS WG3 mailing list for review as well as TC CYBER mailing list for comments (2 weeks planned)

Resource allocation for this development and consolidation task: 35 STF days (or 42 with full budget allocation)

Task 7 – Review of security requirements deliverable (DTS/RRS-03012)

Update the Technical Specification according to the comments received from RRS WG3 and TC CYBER and produce a final draft for TC RSS review. Resource required 5 days (depending on the results from the review period)

Milestone 3 – Stable drafts for TB review

The finalized Stable drafts will be available for TC RRS review one week before RRS#33 (i.e. 22-Feb) and will be distributed to TC RRS mailing list for a Remote Consensus.

Task 8 – Finalisation of deliverables

Integrate the comments from TC RRS, and produce final versions for TC RRS approval by RC. Resource required 7 days.

Milestone 4 – Final draft for TB approval

Final drafts are available for TC RRS approval and publication.

Summary of STF resource allocation under current and requested budget

| Task | Contracted expert days under current budget allocation | Contracted expert days under allocation requested by TC RRS |
| --- | --- | --- |
| 1 | 45 | 70 |
| 2 |  |  |
| 3 |  |  |
| Milestone 1- Use case stable draft for WG3 review |
| 4 | 10 | 10 |
| 5 |  |  |
| 6 | 35 | 42 |
| Milestone 2 - Security requirements stable draft for WG3 |
| 7 | 5 | 5 |
| Milestone 3 - Finalised drafts for TB review (both TS and TR) |
| 8 | 7 | 7 |
| Milestone 4 - Final draft for TB approval (both TS and TR) |
| Total (days) | 102 | 134 |

# Required expertise

At least 2 experts to ensure the following mix of skills:

Experience in security

Experience in Software Defined Radio and reconfigurable radio in general

Part III:	Financial conditions

# Estimated cost

## Cost estimated by TC RRS

Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 104 | 600 | 62 400 |
| Contracted experts (voluntary) | 30 | 0 | 0 |
| Total manpower cost | 134 |  | 62 400 |

Travel cost

| Description | Cost estimate |
| --- | --- |
| RRS#32, 23-27 November 2015 Mainz | 1 500 |
| RRS#33 29 February – 4 March 2016, Paris (tbc) | 1 500 |
| RRS#34 30 May – 3 June Saint Diego | N/A |
| Total cost | 3 000 |

## Funding approved by Board#103

Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 82 | 600 | 49 200 |
| Contracted experts (voluntary) | 20 | 0 | 0 |
| Total manpower cost | 102 |  | 49 200 |

Travel cost

| Description | Cost estimate |
| --- | --- |
| RRS#32, 23-27 November 2015 Mainz | 1 400 |
| RRS#33 29 February – 4 March 2016, Paris (tbc) | 1 400 |
| RRS#34 30 May – 3 June Saint Diego | N/A |
| Total cost | 2 800 |

## Other Costs

None.

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from ETSI Members to STF work

Voluntary work of experts (free of charge)

Direct contribution of delegates (e.g. number of documents/comments/e-mail)

Development of related standards by delegates

Contribution from STF experts to ETSI work (e.g. liaison with TC CYBER, ERM)

Contributions presented to TB/WG meetings (number, type, comments received)

Contributions/presentations to other ETSI TBs

Contributions received from other ETSI TBs

Liaison with other stakeholders, e.g. Wireless Innovation Forum (WINNF)

Stakeholder participation in the project (category, business area)

Cooperation with other standardization bodies

Potential interest of new members to join ETSI

Liaison to identify requirements and raise awareness on ETSI deliverables

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Quality review by TB

Quality review by ETSI Secretariat

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 1.0 | 23-Apr-2015 | Markus Mueck | Draft |  |
| 1.1 | 11-May-2015 | Berrini | OCG/ Board consultation | Editorials |
| 1.2 | 15-May-2015 | Markus Mueck | OCG/ Board consultation | Editorials |
| 1.3 | 10-Jun-2015 | Berrini | Board approval | Updated budget allocation and time scale (start at RRS#31 Sep 2015) |
| 1.4 | 09-Sep-2015 |  | To be approved by RRS WG3 | Revised task description and workload evaluation |