|  | ToR STF 482 (TC INT) |
| --- | --- |
|  | Version: 0.4 - Date: 10 June 2014 |
|  | Author: TC INT Date 20 May 2014 |
|  | Last updated by: Alberto Berrini – Date 10 June 2014 |
|  | page 1 of 10 |

Terms of Reference for Specialist Task Force 
STF 482 (TC INT) 
“Validation of the Conformance Test Specifications for the Diameter Protocol over the S6a and S9 reference points”.

Document status

| Current status ToR | Approved by Board#98 (2nd allocation ETSI budget 2014) |
| --- | --- |
| Funding required | Total budget: up to 60 600 €. Contracted experts up to 120 working days, including 24 days voluntary contribution (20% of total) = 57 600 €. Travel cost 3 000 € Additional support (15 working days) from CTI (out of budget) |
| Work items | RTS/INT-00114-1 revised version of TS 103 161-1 (DTS/INT-00093-1) Diameter Conformance testing for S6a interface Part 1: Protocol Implementation Conformance Statement (PICS) RTS/INT-00114-2 revised version of TS 103 161-2 (DTS/INT-00093-2) Diameter Conformance testing for S6a interface Part 2: Test Suite Structure (TSS) and Test Purposes (TP) RTS/INT-00114-3 revised version of TS 103 161-3 (DTS/INT-00093-3) Diameter Conformance testing for S6a interface Part 3: Abstract Test Suite (ATS) and partial Protocol Implementation eXtra Information for Testing (PIXIT) proforma specification RTS/INT-00115-1 revised version of TS 103 162-1 (DTS/INT-00093-1) Diameter Conformance testing for S9 interface Part 1: Protocol Implementation Conformance Statement (PICS) proforma RTS/INT-00115-2 revised version of TS 103 162-2 (DTS/INT-00093-2) Diameter Conformance testing for S9 interface Part 2: Test Suite Structure (TSS) and Test Purposes (TP) RTS/INT-00115-3 revised version of TS 103 162-3 (DTS/INT-00093-3) Diameter Conformance testing for S9 interface Part 3: Abstract Test Suite (ATS) and partial Protocol Implementation eXtra Information for Testing (PIXIT) proforma specification |

Part I – Reason for proposing the STF

# Rationale

The Diameter protocol was initially developed to provide an Authentication, Authorization, and Accounting (AAA) framework that could overcome the limitations of RADIUS. RADIUS had issues with reliability, scalability, security and flexibility. The Diameter protocol defines a policy protocol used by clients to perform Policy, AAA and Resource Control. This allows a single server to handle policies for many services.

The main targets of the EPC architecture which offers the key access technology for LTE networks are to provide a flexible and efficient IP-connectivity layer, capable of handling Inter-System Handovers, Policy and Charging Control as well as security for transparent IP services. This applies in particular when users are roaming and connect via a visited network.

If a roaming user acts in a visited network (VPLMN) it is necessary that the Policy and Charging rules functions (PCRF) in both home (HPLMN) and visited network interact. This is done via the S9 interface. The protocol used on that interface is the Diameter protocol as defined in RFC3588 and profiled for the S9 interface in ETSI TS 129 215. Two Diameter applications are used over the S9 reference point: S9 and Rx. The purpose of the S9 Diameter application is to install PCC rules or QoS rules generated in the HPLMN into the VPLMN and transport the events that may occur in the VPLMN to the HPLMN. When the AF is in the VPLMN, Rx is used over the S9 reference point to exchange service session information from the V-PCRF to the H-PCRF.

The Mobility Management Entity (MME) is the key control-node for the LTE access-network. It is responsible for authenticating the user in conjunction with the Home Subscriber Server (HSS). The HSS is a network database that holds both static and dynamic data elements related to subscribers. The HSS provides user profile information to the MME during user authentication. The S6a interface that enables transfer of subscription and authentication data for authenticating/authorizing user access to the LTE network is located between the Mobility Management Entity (MME) and the Home Subscriber Server (HSS). The protocol used on that interface is also the Diameter protocol as defined in RFC3588 and profiled for the S6a interface in ETSI TS 129 272.

The following two figures illustrate the two different network configurations for the roaming architecture and the network interfaces.

Figure 1: Roaming architecture for home routed and PMIP based

Figure 2: Roaming architecture for local breakout, VPMN routed

Given that there is already a test specifications related to the Diameter protocol profile for the S6a and S9 reference points under implementation, it seems reasonable to validate these test specification.

Following the methodologies developed and used by ETSI, the validation is based on the Abstract Test Suite of the S6a and S9 Test Specifications, and can start as soon as the final drafts have been approved. Approval is planned at the INT#25 meeting (Vienna, June 24-26, 2014).

Experience with the validation of other testing standards has shown that involvement of experts on conformance testing of protocols requires highly specialised knowledge in testing methodology, TTCN-3 language and dedicated tools. There is an advantage if testing experts are disjoint from experts developing the protocol specifications. In addition, the validation of this kind of specifications requires significant effort and it cannot be expected that this effort can be provided on a voluntary basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the test adaptors. These testing experts are not available on TC INT level and need to be recruited on a funded basis. The experts will use TTCN-3 platforms available at ETSI.

Past ETSI experience has shown that an STF, supported by the ETSI CTI, is the most effective and cost-efficient way to develop and validate test specifications.

# Objective

Recently major efforts have been made by LTE component providers to inter-connect complete networks, i.e. connecting the single components that comprise an LTE network of different operators to allow seamless roaming. This is mainly done via the S6a and the S9 interfaces. Experiences from those trials have shown that there are implementations of the Diameter protocol that have massive interconnection issues due to different interpretation of the protocol standards.

Given that the test specifications related to the Diameter protocol profile for the Rx and the Gx reference points have been validated by STF450 against equipment of a significant number of vendors, it seems reasonable to extend the INT set of validated test specifications to also cover Diameter on the S6a and S9 reference point. Members of INT have already expressed the wish to provide access to equipment to validate against.

Experience with the validation of other testing standards has shown that involvement of experts on conformance testing of protocols requires highly specialised knowledge in testing methodology, TTCN-3 language and dedicated tools. There is an advantage if testing experts are disjoint from experts developing the protocol specifications. In addition, the validation of this kind of test specifications requires significant effort and it cannot be expected that this effort can be provided on a voluntary basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the Test Specifications. These testing experts are not available on TC INT level and need to be recruited on a funded basis. The experts will use dedicated software tools available at ETSI.

# Relation with ETSI strategy and priorities

This STF is directly related to ETSI strategic objective "Major Strategic Topics - NGN" and “Service level interconnection of IP-Based Services” and corresponds to the “Standards enablers/facilitators (conformance testing, interoperability, methodology)” category.

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Telecom Italia | Giulio Maggiore | Tests used to get detailed information from vendors about Interoperability Testing before coming to the market |
| Telekom Austria | Martin Brand | Tests needed for internal network testing |
| Deutsche Telekom | Gerhard Ott | Tests needed for internal network testing |
| AT&T | Dewayne Sennet | Tests used to promote conformance testing for Public Safety |
| Telekom Slovenjia | Matjaz.Bericic | Test used to promote interoperability among vendors |
| Cisco | Jesus Trujllo Gomez | Test will be used for quality enhancement of IMS&EPC products |
| ZTE | David Huo | Test will be used for quality enhancement of IMS&EPC products |
| Neustar | Andreas Roeth | Test to improve IMS Enabling solution |
| Iskratel | Primoz Svigeli | Test will be used for quality enhancement of IMS&EPC products |
| Italtel | Diego Saiu | Test will be used for quality enhancement of IMS&EPC products |
| Arcatech | Terence A, Simpson | Provide test system for functional and performance test. |
| Codenomicon | Ari Takanen | Provide test system to test protocols |
| Confomiq | Stephan Schulz | Generation of tests for testing protocol |
| Testing Tech | Theofanis Vassiliou-Gioles | Provide the Test System for the test cases implementation and execution |
| Fokus | Axel Rennoch | Research Institute, advanced automated/standardized test solutions with TTCN-3 |
| Technical University of Berlin | Julius Muller | Research Institute, EPC/NGN evolution |
| Elvior | Andres Kull | Tool Provider, Provide the Test System for the test cases |
| Tektronix Communications | Kanthi, Prakash | Tool Provider, Provide the Test System for the test cases |
| Mavenir Systems | Jim McGlade | Test will be used for quality enhancement of IMS&IPC products |
| NTIA-ITS | Kameron Behnam | To check LTE network elements for conformance before deploying in a public safety nationwide network. |
| Keynote Sigos | Shicheng Hu | Try to establish the synergy between the network conformance and the network e2e tests. Provide the Test System for the global roaming and the e2e QoS / QoE tests |

## Market impact

Public Safety Projects have become recently a major context where operators required full compliance of products against the base specification. National Organizations and Government are going towards a fully compliant VoLTE network with priorities management. Validation of Conformance Test Specification allow not only to test early implementation but also to provide feedback to 3GPP in time to validate the standard before the mass market application.

The availability of reliable and validated test specifications will allow implementers of LTE components and protocol stacks (for HSS, MME and PCRF) to test the conformance of their products against the protocol specifications. Conformance testing during the whole development phase of all LTE products will significantly reduce the time-to-market of the LTE architecture, as protocol conformant products will be of an enhanced quality level and will hence be less likely to cause interoperability problems with the products of other vendors.

Protocol conformant products will therefore provide the network operators with the means to deliver fully LTE compliant services to their end customers in a continuously high quality, with reliable service functionality, without communication failures and generally with the optimum quality of service for the transported media.

The validated tests for the S6a and S9 interface will allow consequently allow faster connection of the LTE networks of different operators due to well tested and interoperable LTE entities that form the border of the adjacent networks and are responsible for the key functionalities policy, charging and authentication.

## Tasks that cannot be done within the TB and for which the STF support is necessary

- LTE networks are currently being deployed in the telecoms industry. They must operate alongside and interwork correctly with the existing IMS networks already installed.

- Consequently there is the need to allow seamless roaming functionalities between the networks of different operators.

- Field trials showed massive interoperability problems related to Diameter implementations of different vendors. Therefore detailed Abstract Test Specifications are urgently required to complete the overall testing framework.

- To complete the testing work, and to capitalise on the investment done during the field trials, the corresponding Abstract Test Suite is urgently needed.

- The ETSI members do not have sufficient resources to create an Abstract Test Suite on time, and with the high quality that has been experienced with using STF resources for this purpose in the past.

- It is essential that this work is done in a timely manner in order to synchronise with global testing activities, especially in the context of LTE.

## Related voluntary activities in the TB

The ETSI Members supporting the creation of the STF are committed to supporting this STF in terms of participation in the STF Steering Group, providing input and review to the STF, providing test bed structures and test tools.

## Outcome from previous funded activities in the same domain

STF466 Conformance Test Specifications for the Diameter Protocol over the S6a and the S9 reference points.  Resource: 160 remunerated and 40 voluntary effort days, 99 000€

## Consequences if not agreed

LTE networks are currently being deployed in telecoms networks during the progression towards fully LTE compliant network architectures. Thorough conformance testing will increase the level of confidence that equipment from various suppliers will interwork. This in turn will reduce implementation and rollout times. Not providing timely validated and reliable test specifications, would ultimately delay the deployment of LTE.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TC INT, Giulio Maggiore

## Other interested ETSI Technical Bodies

- 3GPP CT1

- 3GPP CT3

- 3GPP SA3

- ETSI TC MTS

## Other interested Organizations outside ETSI

- GSMA IREG

# Working method/approach

## Organization of the work

The work can be separated in 4 main tasks:

Task T0: Project Management	15 working days in total

Task T1: Codec and TA

- Codec and TA development	30 working days in total

Task T2: ATS Validation

- S6a	38 working days in total

- S9	32 working days in total

Task T3: TS update

- S6a	10 working days in total

- S9	10 working days in total

## Base documents

| Document | Title | Current Status |
| --- | --- | --- |
| DTS/INT-00093-1 | Diameter Conformance testing for S6a interface; Part 1: PICS | Approval INT#25 (June 2014) |
| DTS/INT-00093-2 | Diameter Conformance testing for S6a interface; Part 2: TSS&TP | Approval INT#25 (June 2014) |
| DTS/INT-00093-3 | Diameter Conformance testing for S6a interface; Part 3: ATS&PIXIT | Approval INT#25 (June 2014) |
| DTS/INT-00094-1 | Diameter Conformance testing for S9 interface; Part 1: PICS | Approval INT#25 (June 2014) |
| DTS/INT-00094-2 | Diameter Conformance testing for S9 interface; Part 2: TSS&TP | Approval INT#25 (June 2014) |
| DTS/INT-00094-3 | Diameter Conformance testing for S9 interface; Part 3: ATS&PIXIT | Approval INT#25 (June 2014) |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | RTS/INT-00114-1 | Diameter Conformance testing for S6a interface; Part 1: PICS |
| D2 | RTS/INT-00114-2 | Diameter Conformance testing for S6a interface; Part 2: TSS&TP |
| D3 | RTS/INT-00114-3 | Diameter Conformance testing for S6a interface; Part 3: ATS&PIXIT |
| D4 | RTS/INT-00115-1 | Diameter Conformance testing for S9 interface; Part 1: PICS |
| D5 | RTS/INT-00115-2 | Diameter Conformance testing for S9 interface; Part 2: TSS&TP |
| D6 | RTS/INT-00115-3 | Diameter Conformance testing for S9 interface; Part 3: ATS&PIXIT |

## Deliverables schedule:

- Start of work	02-Sep-2014	INT#26

- ToC and scope	05-Oct-2014

- Early validation results	16-Dec-2014	INT#27

- Further validation results	Feb/Mar-2015	INT#28

- Final validation results	May/Jun-2015	INT#29

- Stable draft of all docs	May/Jun-2015	INT#29

- TB approval	May/Jun-2015	INT#29

- Publication	Jul-2015

## Work plan, time scale and resources

| N | Task / Milestone / Deliverable | Target date | Testing experts (days) | CTI contrib. (days) |
| --- | --- | --- | --- | --- |
| M0 | Start of work | 02-Sep-2014 |  |  |
| T0 | Project management, reporting | Sep 2014 – Jun 2015 |  | 15 |
|  | CTI supervision |  |  |  |
| T1 | Codec and Test Adaptor (TA) development | Sep 2014 – Dec 2014 | 30 |  |
| M1 | First Progress Report (INT#27) | Dec 2014 |  |  |
| T2 | ATS Validation | Oct 2014 – May 2015 |  |  |
| T2.1 | S6a |  | 38 |  |
| T2.2 | S9 |  | 32 |  |
| M2 | First Progress Report (INT#28) | Feb 2015 |  |  |
| T3 | TS Updates | Jan 2015 – May 2015 |  |  |
| T3.1 | S6a |  | 10 |  |
| T3.2 | S9 |  | 10 |  |
| M3 | Approval of all revised TS document, Final Progress Report (INT#29) | Jun 2015 |  |  |
| Total |  |  | 120 | 15 |

INT meetings

INT#27	16-18 Dec 2014	tbd	first report

INT#28	Feb/Mar 2015	tbd	second report

INT#29	May/Jun 2015	tbd	final drafts for approval

## Task and milestone description

Task T0: Project Management (CTI supervision)

- Drafting non-published documents:	  6 working days in total

- Attending Technical Body and WG meetings: 	  9 working days in total

Task T1: Codec and TA development		30 working days in total

Task T2: ATS Validation		70 working days in total

- S6a	35 working days

- S9	35 working days

- Task T3: TS Update	20 working days in total

- S6a	10 working days

- S9	10 working days

Milestone 1 – First Report on Validation Activities

Approval of Progress Report by INT#27 (Dec 2014) plenary

Milestone 2 – Second Report on Validation Activities

Approval of Progress Report by INT#28 (Feb/Mar 2015) plenary

Milestone 3 –Approval of all revised documents, STF Final Report

Approval of final drafts of PICS, TSS&TP and ATS&PIXIT documents

Approval of Final Report by INT#29 (May/Jun 2015) plenary

The draft documents must be uploaded by the STF Leader on the TB contributions area of the ETSI Portal two weeks before INT#29.

# Required expertise

The following experts are required to perform the work. The actual number of experts and mix of skills may depend on the actual applications received and will be decided when setting up the STF.

Number of experts required: 2-3

Relevant expertise required:

- Expert knowledge of DIAMETER protocols and LTE architecture

- Expert knowledge in procedures on the S6a and S9 interfaces

- Expert knowledge in validating DIAMETER test specification from earlier STFs (e.g. STF450)

- Expert knowledge in implementing Abstract Test Suites in TTCN-3

- Awareness of outputs from earlier STFs on Diameter testing (e.g. STFs 434, 443, 450, 466)

Part III:	Financial conditions

# Estimated cost

## Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 96 | 600 | 57 600 |
| Contracted experts (voluntary) | 24 | 0 |  |
| CTI staff from ETSI budget | 0 | 0 |  |
| CTI staff (voluntary) | 15 | 0 |  |
| Total manpower cost | 135 | - | 57 600 |

## Travel Costs

| Description | Cost estimate |
| --- | --- |
| INT#27, INT#28, INT#29 | 3 000 |
| Total cost | 3 000 |

## Other Costs

None

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Key performance indicators suitable for this kind of STF projects are the following:

Contribution from ETSI Members to STF work

- Voluntary work of experts (free of charge or with partial remuneration)

- Steering Group meetings (number of participants/duration)

- Delegates attending meetings/events related to STF (number of participants/duration)

- Direct contribution of delegates (e.g. number of documents/comments/e-mail)

- Support to the STF work (e.g., provision of test–beds, organization of workshops, events)

- Contributions/presentations to other ETSI TBs

- Contributions received from other ETSI TBs

Contribution from STF experts to ETSI work

- Contributions presented to TB/WG meetings (number, type, comments received)

- Presentations in workshops, conferences, stakeholder meetings

Liaison with other stakeholders

- Stakeholder participation in the project (category, business area)

- Cooperation with other standardization bodies

- Potential interest of new members to join ETSI

- Liaison to identify requirements and raise awareness on ETSI deliverables

- Comments received on drafts (e.g. on WEB site, mailing lists, etc.)

Quality of deliverables

- Approval of deliverables according to schedule

- Respect of time scale, with reference to start/end dates in the approved ToR

- Quality review by TB

- Quality review by ETSI Secretariat

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

| Ver. | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 2014-04-15 | Giulio Maggiore | Draft | First draft |
| 0.2 | 2014-04-30 | Berrini | For Board approval | Revised budget, clarifications |
| 0.3 | 2014-05-20 | Giulio Maggiore | For Board Approval | Clarifications on roaming configurations |
| 0.4 | 2014-06-10 | Berrini | Approved Board#98 | Work Item codes, to be approved by INT#25 (24-26 June) |