|  | ToR STF 483 (TC MSG) |
| --- | --- |
|  | Version: 0.6 |
|  | Author: Sebastian Muller – Date:20 Mar 2014 |
|  | Last updated by: Alberto Berrini – Date:9 September 2014 |
|  | page 1 of 7 |

Terms of Reference - Specialist Task Force STF 483

(TC MSG)

”eCall HLAP Conformance Test Specifications Validation”

Summary information

| Approval status | Approved by TC MSG (doc ref: MSG(14)000008) Approved by Board#98 (5-6 June 2014) |
| --- | --- |
| Funding | Total cost: 36 400 €: contracted expert 63 working days (50 days @ 600€/day = 30 000 € + 13 days free of charge, 20% of total), travel cost 6 400 €. Additional 17 working days from CTI (no cost for ETSI budget) |
| Time scale | Aug 2014 to Dec 2014 |
| Work Items | DTS/MSG-0015 approved 20 February 2014 |
| Board priority category | Standards enablers/facilitators (e.g. conformance test/interoperability/methodology) Recommendations: use of TTCN and CTI supervision, require average 20% voluntary contribution from Companies sending experts. |

Part I – Reason for proposing the STF

ITS technologies are becoming more and more complex, collaborative and interdependent. Furthermore, ITS systems are often specified by multiple standards from different standardization development organisations (SDOs). These factors potentially lead to non-interoperability standards. The development of products that rely on non-interoperable standards can eventually result in fragmented markets, all of which can impact the global trust in the eCall technology.

Various measures can significantly improve the reliability and interoperability of complex systems such as ITS. The development of test specifications for conformance and interoperability can be coupled with validation activities, such as building prototype test systems. Likewise, the prototype test systems can be used at interoperability events. Consequently, the project contributes to the effort of testing and validation ITS systems with the goal to bring the ITS systems to a stage where end users trust the services provided.

# Rationale

ERTICO, in collaboration with ETSI, has organized the latest in a series of interoperability events for eCall. This event was hosted by CETECOM, from 9 to 13 September 2013 in Essen, Germany (see http://www.etsi.org/news-events/events/677-2013-ecall-plugtests). More than 30 vendors attended the interoperability event which manifests the high interest of industry in eCall tests. A next interoperability event is planned in Q4 2014. As a prerequisite, an eCall conformance test suite is needed in order to ensure the compliance of devices to the base standards. The eCall conformance test suite may also be used in upcoming certification programs.

# Objective

Currently eCall end to end testing specification CEN TS 16454 provides high level test descriptions not containing enough details on the test process to ensure that test labs can replicate the tests with comparable result everywhere. Providing a TTCN-3 test specification is needed to obtain a complete test description.

The result of the last eCall interoperability event in October 2013 was an early draft TTCN-3 test specification based on test purpose defined in CEN TS 16454. This was draft was contributed ETSI TC MSG#38 (Work Item DTS/MSG-0015, ECall High Level Application Protocol (HLAP) Conformance Testing).

The objective of this present STF proposal is to complete the development of the TTCN-3 test specification according to ETSI CTI methodology and validation against at least two eCall implementations. Furthermore the objective is to validate the TTCN-3 test specifications during the next ITS eCall interoperability event in Q4 2014.

# Relation with ETSI strategy and priorities

This action supports the ETSI Long Term Strategy item(s) to:

create high quality standards for global use and with low time-to-market.

establish leadership in key areas impacting members' future activities

This action has a priority category of

Standards enablers/facilitators (conformance testing, interoperability, methodology)

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| CETECOM GmbH | Martin Albrink | Provision of standardized test suites for certification purposes |
| Gemalto M2M GmbH | Jens Raabe | ETSI standards successfully implemented in our products. Conformance test and early validation is needed to ensure quality of our devices |
| Testing Technologies | Stephan Pietsch | Provision of eCall specific test software for the certification process |
| Telit | Daniele Scalembra | Validate our product before next interoperability event |
| Sierra Wireless | Benoît Tournier | eCall validation needed to support certification activities |
| NXP Semiconductors | Jean-Michel Prodhomme | eCall validation needed to ensure quality and interoperability of products |

## Market impact

eCall aims at issuing an automated call, based on 112, to emergency services including data such as exact location of the crash site, the identification of the vehicle, the number of passengers, etc., which is called the Minimum Set of Data (MSD). With this information emergency services will be able to provide a faster response. The EC wants all new vehicle types placed on the market after October 2015 to implement eCall, the PSAPs to be upgraded to handle the eCalls, and is making recommendations to Member States to draw up detailed rules for public mobile network operators operating in their countries on handling eCalls.

The TTCN-3 test specification must be available in 2014 for product validation in order to ensure product market entry by 2015, as required by the EC.

Interoperability is a key factor that enables the use of new technologies and provides all benefits attached to them, such as competitiveness, innovation and reliability.

Directive 2010/40/EU on the framework for the deployment of Intelligent Transport Systems, in the field of road transport and for interfaces with other modes of transport, included harmonised provision for an interoperable EU-wide eCall service as a priority action.

On 8th September 2011, the European Commission adopted the Recommendation C(2011) 626 addressing the EU Member States requesting them to call on the mobile network operators to set up their networks in such a way that they correctly transmit automatic 112 emergency calls generated by cars (eCalls). The adoption of this Recommendation is the first step of a tripartite legislative process. Later on, legislative initiatives on the eCall device to be fitted into the cars and on the technical specifications of the emergency call centres will follow.

The Rolling plan for ICT standardisation (2013) (Domain 3.1: Societal Changes - eCall) encourages “The development of technical specification/standards for the implementation of eCall in Vehicles” and “The provision of guidelines on certification of eCall systems (in particular for aftermarket in-vehicle devices)”.

## Tasks that cannot be done within the TB and for which the STF support is necessary

Experience with the development of other standards has shown that involvement of experts on conformance and interoperability testing of protocols requires highly specialised knowledge in testing methodology. The generation of this kind of specifications requires significant concentrated effort that can be done in this case by experts provided on a funded basis. Hence the involvement of testing experts is needed in order to assure timely completion and high quality of the Test Specifications. The experts will use dedicated software tools available at ETSI. Test adapter development and test suite validation are expert tasks which cannot be provided by a TB.

## Related voluntary activities in the TB

- Delegates within the TC will review the deliverables

- Companies will provide the devices that are being tested and support for installation free of charge. The devices are Public Safety Answering Points (PSAP) and the in-vehicle systems (IVS)

- Companies will provide the hardware of the eCall test platform during the project, i.e. eCall modem etc

- Companies will provide the TTCN-3 test adapter and codec of the eCall test platform during the project. TTCN-3 test adapter and codec will not be released

## Outcome from previous funded activities in the same domain

NA

## Consequences if not agreed

The production of test specifications as described in the present document is key to the testing and potential certification activities that should assure the interoperability of ITS equipment. Such devices are required to have high levels of interoperability if the safety on road is to be kept at the highest level. The non-availability of such standards may cause problems of interoperability.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TC MSG

## Other interested ETSI Technical Bodies

NA

## Other interested Organizations outside ETSI

ERTICO - ITS Europe and ETSI have a MoU in place which defines amongst other activities the cooperation on ‘Testing support and certification initiative’ and ‘HeERO PSP EU project– Harmonised eCall European Pilot’.

The HeERO EU funded pilot project, coordinated by ERTICO – ITS Europe, started in 2011 and will conclude in 2014, aims to prepare Pilot Sites in many EU Member States for the deployment of the eCall system in 2015.

CEN TC278 WG15 (eSafety) develops the set of eCall High Level Application protocols on which the test specifications are based.

# Working method/approach

## Organization of the work

The work will be done in two waves. In the first wave the test specifications will be updated, and validated against at least two IVS devices and two PSAP devices. The second wave consists of the test specification validation during the next eCall interoperability event in Q4 2014.

## Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| CEN TS16454:2011 | Intelligent transport systems – eSafety - eCall end to end conformance testing | Published |  |
| CEN TS16454:2014 | Intelligent transport systems – eSafety - eCall end to end conformance testing | Stable draft | March 2014 (In Ballot) |
| CEN EN16062:2011 | Intelligent Transport Systems – eCall – High Level Application Protocols | Published |  |
| CEN EN16062:2014 | Intelligent Transport Systems – eCall – High Level Application Protocols | Stable draft | March 2014 (In Ballot) |
| CEN EN15722:2011 | Intelligent Transport Systems – eCall – Minimum Set of Data | Published |  |
| CEN EN15722:2014 | Intelligent Transport Systems – eCall – Minimum Set of Data | Stable draft | March 2014 (In Ballot) |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | DTS/MSG-0015 | Title: Mobile Standards Group (MSG); ECall HLAP Conformance Testing Abstract Test Suite (ATS) and Protocol Implementation eXtra Information for Testing (PIXIT) Scope: Develop an ATS for the test purposes defined in CEN/TS 16454:2013: Intelligent transport systems - ESafety - ECall end to end conformance testing |

## Deliverables schedule:

DTS/MSG-0015

Start of work	20-Feb-2014

ToC and scope	20-Feb-2014

Early draft	3-Mar-2014 (TC SMG)

Stable draft	26-Sep-2014

TB approval	17-Dec-2014	RC

Publication	28-Jan-2015

## Work plan, time scale and resources

| N | Task / Milestone / Deliverable | From | To | Funded experts (days) | CTI (days) |
| --- | --- | --- | --- | --- | --- |
| Wave 1: Test standard DTS/MSG-0015 ECall HLAP Conformance Testing Abstract Test Suite (ATS) |
| M1.0 | Start of work | 15 Sep-2014 |  |  |
| T0 | Project management | 15 Sep 2014 | 10-Dec 2014 |  | 5 |
| T1 | Review CEN TS 16454:2013 | 15 Sep 2014 | 17-Oct 2014 | 12 |  |
| T1b | Define subset of test | 15 Sep 2014 | 14 Oct 2014 |  |  |
| T2 | Update TTCN-3 scripts according to ETSI CTI methodology and feedback from task T1 | 15 Sep 2014 | 24 Oct 2014 | 10 |  |
| T3 | Creation of the ETSI TS document | 15-Sep 2014 | 31 Dec 2014 |  | 5 |
| T4 | Quality Check of Test Standard | 01 Nov 2014 | 31 Dec 2014 |  | 3 |
| M1.1 | Test subset for WG approval (MSG#41) available one week before the meeting | 21-22 Oct-2014 |  |  |
| T5 | Include WG comments, if any | 25 Oct 2014 | 31 Oct 2014 |  | 1 |
| T6 | Installation of SUTs and coordination with SUT operators | 15-Sep 2014 | 10-Oct 2014 | 5 |  |
| T7 | Validation | 15-Sep 2014 | 10-Oct 2014 | 23 |  |
| M1.2 | Final Draft for WG approval (MSG#42) | 12 Dec 2014 |  |  |
| T8 | Include TB comments, if any | 13 Dec 2014 | 31 Dec 2014 |  | 1 |
| Total Wave 1 | 50 | 15 |

| N | Task / Milestone / Deliverable | From | To | Funded experts (days) | CTI experts (days) |
| --- | --- | --- | --- | --- | --- |
| Wave 2 – Validation of Test standard DTS/MSG-0015 during an eCall interoperability event (to be organized in Q4 2014) |
| M2.0 | Plugtest Attendance | 27-31 Oct 2014 |  |  |
| T9 | Project Management | Oct 2014 | Dec 2014 |  | 2 |
| T10 | Validation at INTEROPERABILITY EVENT | Oct 2014 | Oct 2014 | 10 |  |
| T11 | Correction of DTS/MSG-0015, if any | 3-Nov 2014 | 7-Nov 2014 | 3 |  |
| Total Wave 2 | 13 | 2 |

NOTE: This estimate is based upon the assumption that:

- two IVSs are validated against 38 tests; total of 76 tests

- two PSAPs are validated against 15 tests; total of 30 tests

- 106 tests / 23 days provides a ratio of ~5 tests per day

CTI has evaluated these figures and are considered to be reasonable for the complexity of the technology.

## Task and milestone description

Task 0. Task 9 – Project Management and Code Review

Coordination, communication, reporting and leading of activities.

Task 1 – Review CEN TS 16454 and if applicable provision of change requests

If differences between the test purposes defined in CEN TS 16454 and the TTCN-3 implementation in DTS/MSG-0015 appear, then these differences will be documented and provided as change requests to the HeERO standardization task force. The HeERO EU funded pilot project, coordinated by ERTICO – ITS Europe, will support the liaison with CEN TC278 WG15. CEN TS 16454 :2014 is actually in ballot and the STF will align its change requests with this latest base specification.

Task 2 – Update TTCN-3 scripts according to ETSI CTI methodology and feedback from task T1

Update TTCN-3 scripts to be in line with ETSI Naming Conventions according to ETSI EG 202 798: "Intelligent Transport Systems (ITS); Testing; Framework for conformance and interoperability testing". Modify TTCN-3 scripts according to feedback from task 1.

Task 3 – Quality Check of Test Standard

Check of TTCN-3 scripts with T3Quality tool. Peer review of ATS document.

Task 4 – Creation of the ETSI TS document

Fill the editHelp TS skeleton with test suite specific information such as test configuration, abstract test method etc.

Task 5, Task 7 – Include WG/TB comments, if any

Modify ATS document according to received comments. In case no comments are received, this task is not relevant.

Task 6 – Installation of SUTs and coordination with SUT operators

Installation of test bed with SUTs. Online support from SUT operators on SUT errors, SUT triggers etc

Task 7 – Validation

This STF will provide level 2 validation as shown in the table below. The eCall test suite shall be validated against a minimum of at least two IVSs and two PSAPs. These SUTs need to be available and at a mature state of implementation. The responsibilities shown in the table below shall be shared by the STF team. In addition and beyond the STF effort, it is expected to get documentation and support from the company providing the SUTs on any issues that may arise. This support shall be limited to reasonable effort. The validation is on TTCN-3 script level only, and not on test system level. Thus a test adapter and a codec must be present during validation, but no software code will be released. In terms of hardware a laptop, an eCall modem and a SIM card from a commercial mobile operator must be provisioned.

Table 3: Responsibilities of validation

| Basic Validation (Level 1) | Strong Validation (Level 2) |
| --- | --- |
| Provision of TTCN-3 analyser/compilers |  |
| Compilation of the test suite on at least 3 TTCN-3 compilers |  |
| Reporting of errors in the tools |  |
| Reporting of errors in the ATS |  |
| Updating of ATS |  |
| Compilation of validation report |  |
|  | Provision and installation of SUT(s) |
|  | Execution of the tests |
|  | Reporting and fixing of errors in the TTCN-3 scripts |
|  | Validation of test verdicts |

Task 10 – Validation at an interoperability event

Devices attending the interoperability event will be offered to run the conformance tests. It is expected that at least one, possibly two test system operators attend the interoperability event. The validation will be handled on a best effort basis.

Task 11 – Correction of DTS/MSG-0015, if any

Issues detected during the interoperability event will be fixed in this task.

# Required expertise

Experts must ensure the following mix of skills:

expert knowledge on CEN TS 16454 and CEN EN 16062;

expert knowledge on TTCN-3 ES 201 873;

good practical experience on implementing conformance test suites and coordinating interoperability testing;

expert knowledge in eCall modems

Part III:	Financial conditions

# Estimated cost

## Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 50 | 600 | 30 000 |
| Contracted experts (voluntary) | 13 | NA | NA |
| CTI staff (voluntary) | 17 | NA | NA |
| Total manpower cost | 80 |  | 30 000 |

## Travel Costs

| Description | Cost estimate |
| --- | --- |
| Travel of two persons to validation session | 3 200 EUR |
| Travel of two persons to an interoperability event | 3 200 EUR |
| Total cost | 6 400 EUR |

## Other Costs

NA

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from the ETSI Members

Voluntary work of experts provided free of charge in form of CRs being reviewed. This action will be documented through meeting minutes

Interest from stakeholders other than ETSI Members

Number of implementations using the test system during the interoperability event

Quality of deliverables

Approval of deliverables from the Reference TB according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.0 | 20-Mar-2014 | Sebastian Müller | Draft | For TC MSG approval |
| 0.4 | 06-Jun-2014 |  |  | Approved by Board#98 |
| 0.5 | 11-Jun-2014 | Berrini | Board approved | Time scale updated |
| 0.6 | 09-sep-2014 | Berrini | Prep. Meet. | Time scale updated |