|  | ToR STF 504 (TC STQ) |
| --- | --- |
|  | Version: 0.11 |
|  | Authors: Kamcke / Holub – Date: 9 October 2014 |
|  | Last updated by: Holub/Kamcke – Date 24 September 2015 |
|  | page 1 of 9 |

Terms of Reference - Specialist Task Force

STF 504 (TC STQ) on “Detection of Emotions in Telecommunication Measurement Applications”

Summary information

| Approval status | Approved during STQ#49 1-July2015 (TC STQ) Approved by Board#104 |
| --- | --- |
| Funding | Budget: 62 400 € ETSI FWP Contracted experts: up to 124 working days, including voluntary contribution (20% of total) Manpower cost: up to 99 days @ 600 €/day = 59 400 € + 25 days free of charge Travel cost up to 3 000 €. |
| Time scale | October 2015 to July 2016 |
| Work Items | DTS/STQ-236, TS 103 296 Approved by TC STQ#47 (6-10 Oct 2014) |
| Board priority category | ETSI STF funding criteria • Emerging domains for ETSI • Standards enablers/facilitators (conformance testing, interoperability, methodology) |
| Notes from TC STQ | Changes to previous version presented to Board#100: The request is now totally concentrated on Standardization. Taken out the development on a common method to describe the uncertainty of the result produced by Emotion Detectors of text and for spoken sentences as well. Version number 0.9 is re-phrased (in the sense as requested) and the time scale has been updated. |

# Rationale

The telecommunications experience rapid development in many areas, among others:

Networks continue to be based on IP technologies.

Bandwidth for voice services is increasing from 3,1 kHz to 7 kHz, 14kHz or even to 20 kHz.

Emotional detectors both for written and spoken content play more and more important role in daily telecommunications in various application areas like security, safely and marketing. Use of Emotional Detector has been also successfully demonstrated for elimination of emotionally sub-optimal test sentences for subjective listening testing used widely for speech transmission quality evaluation

New measurement methodologies and concepts are needed to improve the quality of the results..

New telecommunication technologies and services need totally new approaches in measurements.

On the other hand, uncertainties in the results can be reduced by new measurement methods. Emotion detectors are becoming more and more deployed components in telecommunications, however, with no or minimum standardization effort devoted, resulting in many proprietary application-driven solutions.

# Objective

The well-known quantity “MOS” characterising the quality of speech services is based of subjective tests. This methodology is widely used. E.g. more than 1,4mio€ has been spent (3GPP SA4) for subjective testing of the new EVS Codec for mobile telephony. The methodology itself is found in technical Standards and literature, e.g. Recommendation ITU-T P.800; P.Vary/U.Heute/W.Hess: Digitale Sprachsignalverarbeitung, Teubner 1998; CCITT Handbook on Telephonometry 1993 /2001 and ITU-T Handbook on Practical Procedures on Subjective Testing 2011 etc.

In order to reduce the effort also objective test are in use. They are designed to produce the same result as subjective tests (of cause: in a range of an accepted uncertainty).

Remarks: Subjects = human beings; Objects = measurement instruments; MOS = Mean Opinion Score.

The definition of subjective tests is very detailed (e.g. language and social aspects are carefully controlled), as there is a strong (usually even legal) need to compare different labs results etc. However, some of the parameters are known as to be “for improvement”. One of them is the emotional influence by the content and by the recording of test sentences used for “listening only tests”. Some approaches for improvements have been done so far In order to reduce the particular uncertainty component coming from the current manual approach, this STF is for the production of a standard for mandatory inputs, outputs and accuracy evaluation methods of Emotion Detectors serving this task. These kind of instruments promise to become a solution for the missing instrumental based emotion check. It will work not only for the traditional 3,1kHz telephony service but also for the emerging domain of voice services with extended bandwidth.

Since some years Emotion Detectors are in use, however, all of them are designed for very special purposes. However, looking on the wide range of the subject “emotion”, it has to be noted that an Emotion Detector for telecommunication measurements has not been defined so far, neither for written text nor for spoken sentences.

Despite the rapid development and increase usage of those Emotion Detectors, no systematic classification or even standardization of input and output parameters, related terminology and minimum requirements exist, not in general and not for the subject telecommunications as well. First experience by STQ members show that there are more than one basic algorithm possible for an Emotion Detector examining written text. The study of literature results in the findings that there is very little agreement on parameters and input and output variables.. It is proposed to work on these non-standardized items and to fill the gap in order to provide basic standardization framework for this kind of measurement methodology, namely A) Special parameters for written text and B) Special parameters for spoken speech. Both has to include a listing on the particular advantages and disadvantages resulting from certain algorithms. The results from task A) and B) are used to define minimum requirements for an Emotion Detector for the assessment of test sentences used in subjective tests.

.

The proposed work exceeds the expertise found in the proposing TB. That is the true for both Emotion Detector for written text’ and ‘Emotion Detector for spoken test sentences’ as well.

# Relation with ETSI strategy and priorities

The STF will contribute to the following ETSI Long Term Strategy [GA58(11)22r1]:

stay in tune with changing nature of the global ICT industry (innovation)

establish leadership in key areas impacting members' future activities

engage in other industry sectors besides telecoms, (cross-sector ICT)

This request is in following the priority category [BOARD(12)88_030r1]

Emerging domains for ETSI

Standards enablers/facilitators (conformance testing, interoperability, methodology)

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Gigaset Communications GmbH | Andreas Kamcke | Measurement must not be based on prototype instruments but they have to be based on equipment working in a standardized well-defined manner |
| Mesaqin.com | Jan Holub | The emotion detection is a promising tool that can, among other things, help to allocate just the right amount of bandwidth in VoIP or VoLTE for great user experience but saving the resources at the same time. |
| Audience, Inc. | Scott Isabelle | I consider it technically quite interesting. For utility, if such a tool had existed when we were creating our 'conversational' corpus, it would have been useful to filter out samples with excessive emotional loading. When the tool is completed, we can use it to revise our conversational corpus. |
| Ministry of Transport, Construction and Regional Development | Peter Počta | As a topic of this STF/WI is highly innovative and an innovation is listed between our priorities, therefore we highly support this STF/WI. Moreover, this topic is also of interest of our state R&D organizations involved in telecommunications. |
| Telekom Austria | Martin Brand | I consider it technically quite interesting. A tool is highly needed that filters out samples with excessive emotional loading. With the results received by subjective tests will be more accurate. |
| JYM CIS | Jean-Yves Monfort | Initial works have been done but not in standardization. My two interests are the detection of acoustic events (e.g. in the context of smart cities), and additionally the automatic detection of emotions in speech, may improve the identification of stress and be beneficial in emergencies. In the context of call centres and relationship between users and companies, an automatic detection of the mood of the speaker (using telephony services) may improve the dispatching of the calls. |
| NCIA | Michael Street | NCIA would be happy to support as the topic is quite up-to-date and no standardization effort has been spent on Emotion Detector yet. |

## Market impact

New telecommunication technologies and services need totally new approaches in measurements. There is a fixed coupling between emerging domains and the need for new approaches in measurements. That means for voice services:

A good End-to-End quality is a key point of the business in voice services. It has to be ensured that quality measurements are as correct as possible not only for the narrowband but for upcoming voice service bandwidth as well.

## Tasks that cannot be done within the TB and for which the STF support is necessary

Important parts of the work are based on social psychology and psychoacoustics.

Other parts need deeply knowledge of methods in voice signal processing and analyses.

Furthermore, specialist knowledge in measurement uncertainties is also needed.

In these three subjects, no expertise on the needed level exits in the proposing TB.

## Related voluntary activities in the TB

The members of the TB will follow the work and contribute by making proposals to the working steps. The members are also ready for any technical discussion with the STF team when there is a need for it.

## Outcome from previous funded activities in the same domain

There were no activities funded by ETSI in this domain yet.

## Consequences if not agreed

Because no standardization has been done so far, ETSI would miss the opportunity of standardizing the Emotion Detector for telecommunication needs, which promise to become a measurement solution not only for the current 3,1 kHz voice service but also in the emerging domain of voice services with extended bandwidth.

If this work is not undertaken, Emotion Detection developments will continue in their proprietary and application-driven ways, lacking any way for their comparison or performance assessment.

From the business point of view, influences from text and spoken emotions will remain a non-standardized quantity. That will have deep negative impact e.g. for voice service business, because the complete set of technical devices found in the end to end chain will then be designed based on non-standardized results for the important parameter of speech quality.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

The leading TB is ETSI TC STQ.

## Other interested ETSI Technical Bodies

TC DECT

## Other interested Organizations outside ETSI

FEE CTU Prague,

ITU-T SG12,

3GPP SA4

# Working method/approach

## Organization of the work

Three major parts are envisaged (both covered by these ToR):

Development of common minimum requirements for Emotion Detectors used for Telecommunication Measurement Applications

Development of an approach to classify Emotion Detectors both for written text and for spoken speech.

Development of methodology to assess Emotion Detectors performance.

.

Furthermore, as a by-product, an analysis of existing solutions including possible trials and demonstrations will be performed for both spoken speech and written text emotion detectors

## Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| ETSI TS 103 226 | Methodology for objective emotion identification | Ongoing work | Oct., 2015 |
| STQ(14)47_025 | Presentation of the Emotion Detector for written text developped at CTU Prague | ready | Presented at STQ#47 |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | DTS/STQ-236 TS 103 296 | Working title Requirements for Emotion Detectors used for Telecommunication Measurement Applications Detectors for written text and spoken speech. Scope: Classification of and Requirements for Emotion Detectors and assessment of their performance and uncertainties. |

## Deliverables schedule:

DTS/STQ-236, TS 103 296

Working title: Requirements for Emotion Detectors used for Telecommunication Measurement Applications. Detectors for written text and spoken speech text.

Start of work	1 October 2015

ToC and scope	28 December 2015

Early draft	31 December 2015

Stable draft	15 March 2016

TB approval	14 April 2016	TC STQ#52

Publication	14 May 2016

## Work plan, time scale and resources

## Task and milestone description

| N | Task / Milestone / Deliverable | From | To | Funded experts (days) |
| --- | --- | --- | --- | --- |
| M0 | Start of work | 12-Oct-2015 |  |
| T0 | Project management | 12-Oct-2015 | 8 July 2016 | 6 |
| T1 | Classification of emotion detection for written text and its performance assessment | 12-Oct-2015 | 8 Feb 2016 | 22 |
| T2 | Classification of emotion detection for speech and its performance assessment | 12-Oct-2015 | 8 Feb 2016 | 41 |
| M1 | 1st draft for TB review | 8 February 2016 |  |
| T3 | Minimum mandatory and optional input and output requirements, memory and power requirements, and types of operation | 29 Feb 2016 | 16-May-2016 | 44 |
| M2 | 2nd draft for TB review | 16 May-2016 |  |
| T4 | Final draft for Approval | 20 June-2016 |  |
| M3 | STF Final Report + TB approval (TC STQ) | 8 July-2016 (STQ#52) |  |
| Total | 113 |

The following allocation of tasks has been agreed:

Task 0 – Project Management

Task 1 – Classification of Emotion Detectors for written text and its performance assessment

This includes analysis of existing solutions including possible trials and demonstrations that will be performed for written text Emotion Detectors. The complexity of Emotion detectors for spoken text is much higher than for written text. This is reflected by the different estimated effort in Task 1 and Task 2.

This task requires elaboration of detailed overview of existing approaches, algorithms, ideas (and terminology) for written text emotion detectors. As various research teams dealing with the topic use different vocabularies and approaches (e.g. even in basic classification), an expert experience in this field is required to perform the assessment. Based on the assessment, the “common core” points and ideas should be distilled in draft within the relevant clauses.

Task 2 – Classification of Emotion Detectors for spoken speech and its performance assessment

This includes analysis of existing solutions including possible trials and demonstrations that will be performed for speech. The complexity of Emotion detectors for spoken text is much higher than for written text. This is reflected by the different estimated effort in task1 and task2.

This task deals with speech processing approaches.

This task requires elaboration of detailed overview of existing approaches, algorithms, ideas (and terminology) for speech emotion detectors. As various research teams dealing with the topic use different vocabularies and approaches (e.g. even in basic classification), an expert experience in this field is required to perform the assessment. Based on the assessment, the “common core” points and ideas should be distilled in draft within the relevant clauses.

Task 3 - Development of common minimum requirements for Emotion Detectors used for Telecommunication Measurement Applications.

Based on the results of tasks 1 and 2, the set of minimum requirements for emotion detectors in telecommunications will be defined. The final clause elaborated within this task will contain minimum mandatory and optional input and output requirements, memory and power requirements, and types of operation.

This task will also include the preparation of the draft at the various stages and will take into account, and look after, the feedback from the TB.

# Required expertise

Project supervision - 6 working days,

Classification of emotion detection for written text and its performance assessment, 26 working days

Classification of emotion detection for speech and its performance assessment – 46 working days

Minimum mandatory and optional input and output requirements, memory and power requirements, and types of operation - 46 working days

Up to 4 experts to ensure the following mix of skills:

Knowledge in Telecommunication Voice Quality Measurement methods.

Knowledge in social psychology or psychoacoustics.

Deep knowledge of methods in voice signal processing and analyses.

Knowledge in measurement uncertainties.

Knowledge in methods of emotion detection.

Part III:	Financial conditions

# Estimated cost

## Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 99 | 600 | 59 400 |
| Contracted experts (voluntary) | 25 | zero |  |
| Total manpower cost | 124 |  | 59 400 |

## Travel Costs

| Description | Cost estimate |
| --- | --- |
| Travels | 3 000 Euro |
| Total cost | 3 000 Euro |

## Other Costs

No other costs expected.

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from ETSI Members to STF work

Direct financial contribution (co-funding)

Voluntary work of experts (free of charge or with partial remuneration)

Steering Group meetings (number of participants/duration)

Delegates attending meetings/events related to STF (number of participants/duration)

Direct contribution of delegates (e.g. number of documents/comments/e-mail)

Development of related standards by delegates

Support to the STF work (e.g., provision of test–beds, organization of workshops, events)

Contribution from STF experts to ETSI work

Contributions presented to TB/WG meetings (number, type, comments received)

Presentations in workshops, conferences, stakeholder meetings

Contributions/presentations to other ETSI TBs

Contributions received from other ETSI TBs

Liaison with other stakeholders

Stakeholder participation in the project (category, business area)

Cooperation with other standardization bodies

Potential interest of new members to join ETSI

Liaison to identify requirements and raise awareness on ETSI deliverables

Comments received on drafts (e.g. on WEB site, mailing lists, etc.)

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Quality review by TB

Quality review by ETSI Secretariat

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators. The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 29-Sept-2014 | Kamcke/Holub | Initial Version | Approval by TC STQ expected by 17 Oct 2014 |
| 0.2 | 2-Oct-2014 | Kamcke | Corrected version, Before TB approval | Proposed changes from Mr. Berrini were incorporated and typing errors are corrected. This ToR got some slides as background information (acc. To Mr. Berrini’s suggestion). |
| 0.3 | 6-Oct-2014 | Kamcke | Correction ZN to ZQ, Same staus as in o.2 | Renamed by request from Mr. Berrini. |
| 0.4 | 9-Oct-2014 | Kamcke | Approved by STQ#47 | Additional supporter and approval during STQ#47 |
| 0.5 | 14-Oct-2014 | Berrini | Editorial improvements | Comments AB1 to AB4 |
| 0.6 | 15-Oct-2014 | Holub/ Kamcke | Additions | Editorial improvements, corrections in the tables for working days, additional information in the descriptions of Task1 to Task4. |
| 0.7 | 25-Apr-2015 | Holub/ Kamcke | OCG/Board consultation | Concentration of standardization matters. Taken out: The development on a common method to describe the uncertainty of the result produced by Emotion Detectors of text and for spoken sentences as well. |
| 0.8 | 16-June-2015 | Berrini | Call for experts version | Prepared for the Call for Experts, according to the decision of the Board. |
| 0.9 | 18-June-2015 | Holub/ Kamcke | Version for final Board decision | Reworded text and new time line. |
| 0.10 | 24-Sept-2015 | Rizzo | Updated version following Board#104 approval decision | To update the timeline of the various milestones/tasks and to simplify the related table, page 6 of this document. |
| 0.11 | 29-Sept-2015 | Berrini | Prep. Meet. | Review effort per task (estimated 113 days vs. 124 max allowed). |