|  | ToR STF DJ (TC MTS / WG TDL) |
| --- | --- |
|  | Version: 1.5 |
|  | Author: WG MTS TDL – Date: 16 Apr 2019 |
|  | Last updated by: Andreas Ulrich – Date: 24 Jun 2019 |
|  | page 1 of 14 |

Terms of Reference – Specialist Task Force

STF DJ (TC MTS / WG TDL)

TDL and TOP Enhancements and Maintenance

Summary information

| Approval status | Approved by TC MTS by Remote Consensus on 26 April 2019 (doc ref: MTS(19)000019) Approved by Board#123 (12-14 June 2019) |
| --- | --- |
| Funding | Maximum budget: 94 600 € ETSI FWP |
| Time scale | Sep 2019 to Jun 2020 |
| Work Items | RES/ES 203 119-1 V1.5.1; RES/ES 203 119-2 V1.4.1; RES/ES 203 119-3 V1.4.1; RES/ES 203 119-4 V1.4.1; RES/ES 203 119-6 V1.2.1; RES/ES 203 119-7 V1.2.1; RTS/TR 103 119 V1.2.1 |
| Board priority | ETSI STF funding criteria: Standards enablers / facilitators (conformance test / interoperability / methodology) |

Part I – Reason for proposing the STF

# Rationale

In recent years ETSI TC MTS has invested heavily into the development of the Test Description Language (TDL) and the associated TDL Open Source Project (TOP). TDL supports the stepwise transformation from requirements over test purpose specifications to test descriptions. It offers the necessary concepts for modelling tests and expressing these models in textual and graphical syntaxes. Moreover, a TDL specification enables a semi-automatic transformation to executable tests, whether being expressed in TTCN-3 or another programming language. Complementary to the standardization of TDL, the tools developed in TOP provide a proof-of-concept of all designed TDL concepts and, more importantly, serve as a common platform to accelerate the adoption of TDL and lower the barrier to entry for both, users and tool vendors. Meanwhile, TDL and TOP have reached a level of maturity that enables first applications of this technology within ETSI TBs and elsewhere in industry.

TDL seeks to bridge the methodological gap between declarative test objectives and executable test cases by providing a formalised model-based solution for the specification of test descriptions. At its core there is a common meta-model (abstract syntax) with well-defined semantics which can be represented by means of different concrete notations (concrete syntaxes). A TDL test description created in one notation can be reviewed and approved in other notations, customised to suit the preferred notational conventions of different stakeholders. TDL can also serve as an exchange and visualisation platform for generated tests, contributing to the ongoing activities within ETSI TC MTS to establish MBT technologies within standardisation.

The principles which allow the adaptation of TDL according to the users’ needs are based on a formal basis, which in turn paves the way to tool support and the introduction of the approach to different application domains. The TDL user community as well as first ETSI internal projects adopting TDL and TOP tools create additional needs on the available technologies. It is essential for the continued acceptance of TDL that the language specification keeps evolving to address these needs. Additionally, the tool implementations need to comply with these changes.

# Objective

The work of the proposed STF will concentrate on resolving the submitted change requests to the TDL standard series and the TOP tools. Additionally, it will ensure that all parts remain consistent and that the TOP implementation faithfully implements TDL language features. The results of this STF will be the delivery of the updated ETSI standard series ES 203 119 (multi-part document) in September 2020 and an update of the aligned reference tool implementations that are part of TOP. In more details this includes:

- Part 1: An adaptation and extension of the current TDL meta-model addressing change requests handed in from the TDL user community;

- Part 2: An adaptation of the TDL graphical syntax according to the changes in Part 1, including change requests from users;

- Part 3: An adaptation of the TDL exchange format specification according to the changes in Part 1;

- Part 4: An adaptation and extension of the capabilities for structured test objective specification to include additional features that are in the interest of ETSI technical bodies and other users;

- Part 6: An adaptation and extension of the mapping from TDL to TTCN-3 to offer a wider semantical coverage of language concepts and to furnish evidence of a workable solution for early adopters;

- Part 7: An adaptation of the TDL Extended Test Configurations features according to changes in part 1;

- Updated TOP tools together with an updated Technical Report documenting the available tools and their usage.

# Relation with ETSI strategy and priorities

The proposed STF falls into the category “Standards enablers / facilitators (conformance test / interoperability / methodology)”. As such it contributes to the following aspects of the ETSI long-term strategy and priorities:

- Keep ETSI effective, efficient and recognised as such

- Create high quality standards for global use and with low time-to-market

- Stay in tune with changing nature of the global ICT industry (innovation)

- Establish leadership in key areas impacting members’ future activities

- Engage in other industry sectors besides telecoms (cross-sector ICT)

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Cinderella ApS | Finn Kristoffersen | Cinderella ApS supports the work on TDL to enable more efficient development and better quality of test specifications. The success of TDL is based on high quality standards and supporting reference tools to grow the user community and enable the market for TDL based tools and test services. This project is an important activity to ensure this aim. |
| Elvior LLC | Martti Käärik | TDL has recently evolved into a stable and generally usable language and in order to gain further traction it is important at this stage to listen and react to the feedback from early adopters in a timely manner. Equally important for gaining further interest among users is updating the reference implementation with minimum viable functionality to support the basic test specification workflow and providing better end-user documentation and white papers introducing the TDL to casual observers. |
| Ericsson Hungary Ltd | Dr. György Réthy | Over the past decade automated testing and in particular TTCN-3 has gained a major role in our software product development from functional to performance and robustness testing. However, to further increase test development efficiency and thus decrease time-to-market requires raising the abstraction level at which testers are describing their test cases and automate test case generation. TDL is an enabler for this. Also, TDL is an enabler to specify high quality test standards, based on a unified methodology. TDL is a new language and as such user requirements and requests for clarifications and corrections shall be handled in a timely manner. Ericsson supports this STF request. |
| Institut für Informatik, Universität Göttingen | Prof. Dr. Dieter Hogrefe | The University of Göttingen is interested in the further development and maintenance of TDL and especially in its mapping to TTCN-3, since we are involved in various initiatives where testing with TDL and TTCN-3 plays a central role. TDL and TTCN-3 have also found their way in the Computer Science curriculum at the university with numerous successful students’ projects related to both technologies. TDL and TTCN-3 can only keep such a central role, if both technologies are continuously maintained and adapted to the new challenges of testing. The mapping between both languages provides a solid foundation for further integration into the Computer Science curriculum and strengthens the position of the university in research activities. |
| Siemens AG | Dr. Andreas Ulrich | TDL is a key technology that combines behaviour-driven development and agile development practices with model-based testing. Ensuring a broad acceptance by test engineers, maintenance and evolution of this technology is indispensable. The same arguments apply to TOP which provides the necessary tooling for applying TDL in projects and is therefore vital to its success. Cancelling the planned activities would endanger application of TDL which also has to compete with other proprietary and open source solutions. |

## Market impact

The ETSI TTCN-3 standard has been in place for over ten years and can now be considered as a mature technology for the handling of test automation of very large software systems. Although TTCN-3 was designed with multiple representation formats in mind, only the textual representation is used in practice. On the other hand, UML has become the ubiquitous modelling notation replacing even well-established technologies such as SDL or MSC. However, the imprecise semantics of UML leads to very different tool-dependent solutions, even when the same kind of modelling diagrams are used. This observation extends also to the UML Testing Profile.

TDL provides a precise notation and semantics for the task of specifying test descriptions for black-box tests of communicating and reactive systems. Black-box testing becomes the major testing approach since it offers good support for test-driven and agile software development processes that more and more replace traditional waterfall and iterative processes.

In the standardization of conformance and interoperability test suites TDL offers a clear step forward from detailing test case specifications in TTCN-3 to the specification of more abstract test descriptions. Also, it enables the deployment of model-based testing methods in standardisation. Therefore, the TDL standard impacts tremendously the way tests are designed and described in a broad range of application areas, also beyond telecommunications.

The successful uptake of TDL by technical bodies at ETSI and in organisations outside is very much dependent on the maintenance and evolution of the TDL standard and the corresponding reference implementation in TOP. The availability of tools must be complemented with user guidelines which are a significant aspect for the further growth of the TDL user community.

Subsequently:

- TC MTS is convinced that it is highly desirable to develop an established ETSI standard on a common test description language to set the pace for the design of tests for current and future systems. If this work would be delayed, there is the danger that ETSI can lose the grip on the testing market;

- The penetration of ETSI’s TTCN-3 test language has reached a mature state and will not likely progress beyond the current scope of covered domains and applications, most of which are already mature. TDL will offer a clear way forward from that state to a model-based design of tests;

- TDL allows industry to develop automated tests more efficiently and to apply test automation more widely. Leveraging TDL relieves the test engineer from working on details of test implementations and does not require him to use programming languages.

- The standardised mapping of TDL to TTCN-3 enables test engineers further to save and reuse their existing investments in TTCN-3 based test tools and frameworks for test execution and to benefit from a consistent mapping across different TDL tools.

- The development and maintenance of the TDL standard based on user requests and the alignment of the TDL reference implementation as part of the TOP are essential to the growing user community, the ETSI TC’s adopting TDL as part of their test specification process, and test tool providers integrating support for TDL.

- The TOP user guideline will help new users to adopt TDL as part of their test methodology and hence further support the growth of the TDL user community.

## Tasks for which the STF support is necessary

The previous STFs 454, 476, 492 and 522 created the foundation for TDL in terms of a well-defined modelling concepts, an exemplified application of suggested concrete syntaxes in the context of 3GPP and IMS, a standardized graphical syntax and exchange format, as well as support for test objective specifications. Further efforts to boost the TDL adoption and application in order to create a high impact on the testing and modelling communities were addressed by providing a TDL open-source project (TOP) that contains a TDL reference implementation of some essential tools like editors that help users and tool vendors alike getting started with TDL. The additionally provided standardised mapping of TDL to TTCN-3 offers a consistent way to bridge high level test descriptions and executable test cases.

The development and maintenance of the TDL standard and the alignment of the reference implementation as part of the TOP project require expertise not commonly available in standardisation bodies or from industrial members. Although such knowledge is available from academic partners, i.e. research institutes and universities, they are not in the position of financing voluntary contributions to the development and maintenance of TDL and its implementation in the time frame requested by the user community.

The adoption and application of a new modelling language is a laborious activity when it needs to cover the different requirements from various stakeholders within their respective working environments. This requires close collaboration with stakeholders involved in both the standardisation process, as well as the common use within industry. The application of TDL, the structured test objective specification, and the mapping of TDL to TTCN-3 require close interactions with CTI and other experts at ETSI to ensure the acceptance of TDL by other ETSI technical bodies.

## Related voluntary activities in the TB

The MTS TDL working group was created at the MTS#76 plenary meeting. This working group will take over the task of overseeing and advising the work of the proposed STF. Besides these activities, additional, voluntary efforts will be spent to validate the proposed CR resolutions and new design features in use cases of the individual MTS members. Further efforts will flow into contributions to the TDL open-source project (TOP) to enhance the existing tools.

## Previous funded activities in the same domain

The previous standardisation efforts on TDL can be briefly summarised as follows:

- STF 454 (TDL phase 1) laid the foundation of TDL in 2013 in terms of the basic concepts and their semantics. It also experimented with various syntaxes and demonstrated how TDL could be applied to the domain of 3GPP for the specification of User Equipment conformance test descriptions and IMS interoperability testing. Validation activities within the STF showed that the suggested design of TDL is feasible.

- STF 476 (TDL phase 2) added the necessary functionality to integrate TDL test descriptions into test automation frameworks. It also developed a standardized concrete graphical syntax for end-users, a TDL exchange format to be used by tools as well as an extension to test objective specifications.

- STF 492 (TDL phase 3) accelerated the adoption of TDL by providing a reference implementation of TDL to lower the barrier to entry for users and tool vendors. The reference implementation comprises graphical viewers, textual editors as well as a UML profile for TDL to enable its interoperability with UML-based environments. STF 492 contributed to the public launch of TDL at UCAAT 2015, a major milestone in the development of TDL.

- STF 522 (TDL phase 4) established the connection between the two standardised ETSI languages TDL and TTCN-3, enabling the semi-automatic generation of executable tests from TDL and allowing the re-use of existing TTCN-3 tools and frameworks for test execution. In addition, continuous language maintenance was performed based on CRs submitted by users, and new features deemed necessary for the mapping of TDL to TTCN-3.

The extended scope of TDL led to an increased interest among various stakeholders in adopting TDL, prompting the need for the availability of additional means to apply TDL in their respective working environments and building upon the current momentum of TDL.

## Consequences if not agreed

Establishing this STF as a continuation of the work done in earlier STFs will speed up progress in the adoption of TDL. Without this STF, the application of the TDL standard by end users such as other ETSI technical bodies and industrial partners would be delayed. Users will continue with their largely informal solutions that are mainly designed ad-hoc and thus, without proper tool support, tend to be error-prone and expensive.

Other standardization bodies, notably OMG, will continue their activities on formalising and extending UML that might gain popularity over TDL in the long run. In addition, more and more practises on system and software design are influenced from open-source technologies that implement commonly agreed approaches in system and software engineering and make them freely available. This development might be not in ETSI’s interest as it needs a strong and sound formal approach for describing conformance and interoperability tests of the complex systems it designs. Moreover, ETSI would lose influence in the area of modern system and software engineering practices.

Part II – Execution of the work

# Technical Bodies and other stakeholders

## Reference TB

The work of this STF is embedded within the ETSI MTS TDL Working Group.

## Other interested ETSI Technical Bodies

In principal we expect interest in TDL and TOP from ETSI Technical Bodies that already investigated into TTCN-3. But other TBs that are interested into expressive test objective specifications are in focus, too. The following ETSI TBs are expected to contribute to the STF by providing feedback on the developed TDL methodology: NFV, INT, ITS, ERM, oneM2M, 3GPP.

## Other stakeholders

Additionally, the following organizations are expected to be interested in the outcome from this STF: OMA, TCCA (former TETRA Association), Ipv6Forum. Standardisation bodies from other domains such as automotive run similar initiatives in providing solutions for their specific needs in testing. These initiatives should be also interested in the results of the proposed ETSI STF.

# Base documents and deliverables

## Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| ES 203 119-1 Ver. 1.4.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 1: Abstract Syntax and Associated Semantics | Published |  |
| ES 203 119-2 Ver. 1.3.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 2: Graphical Syntax | Published |  |
| ES 203 119-3 Ver. 1.3.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 3: Exchange Format | Published |  |
| ES 203 119-4 Ver. 1.3.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 4: Structured Test Objective Specification (Extension) | Published |  |
| ES 203 119-6 Ver. 1.1.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 6: Mapping to TTCN-3 | Published |  |
| ES 203 119-7 Ver. 1.1.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 7: Extended Test Configurations | Published |  |
| TR 103 119 Ver. 1.1.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Reference Implementation | Published |  |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1* | RES/ES 203 119-1 V1.5.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 1: Abstract Syntax and Associated Semantics |
| D2* | RES/ES 203 119-2 V1.4.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 2: Graphical Syntax |
| D3* | RES/ES 203 119-3 V1.4.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 3: Exchange Format |
| D4* | RES/ES 203 119-4 V1.4.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 4: Structured Test Objective Specification (Extension) |
| D5* | RES/ES 203 119-6 V1.2.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 6: Mapping to TTCN-3 |
| D6* | RES/ES 203 119-7 V1.2.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Part 7: Extended Test Configurations |
| D7 | RTS/TR 103 119 V1.2.1 | Methods for Testing and Specification (MTS); The Test Description Language (TDL); Reference Implementation and User Guidelines |

* Work items of the TDL standard series which are not affected by CRs will not be updated.

## Deliverables schedule:

The general timeline of this STF is defined as follows:

M0:	Start of work:	16-Sep-2019

M1:	Stable drafts:	15-Jan-2020	MTS#79

M2:	Final drafts:	15-May-2020	MTS#80

M3:	End of Work:	30-Jun-2020

RES/ES 203 119-1 Test Description Language (TDL), Meta-Model and Semantics

Start of work	16-Sep-2019

Stable draft	15-Jan-2020	(input to MTS#79)

Final draft	15-May-2020	(input to MTS#80)

Publication	30-Jun-2020

RES/ES 203 119-2 Test Description Language (TDL), Graphical Syntax

Start of work	16-Sep-2019

Stable draft	15-Jan-2020	(input to MTS#79)

Final draft	15-May-2020	(input to MTS#80)

Publication	30-Jun-2020

RES/ES 203 119-3 Test Description Language (TDL), Exchange Format

Start of work	16-Sep-2019

Stable draft	15-Jan-2020	(input to MTS#79)

Final draft	15-May-2020	(input to MTS#80)

Publication	30-Jun-2020

RES/ES 203 119-4 Test Description Language (TDL), Structured Test Objective Specification

Start of work	16-Sep-2019

Stable draft	15-Jan-2020	(input to MTS#79)

Final draft	15-May-2020	(input to MTS#80)

Publication	30-Jun-2020

RES/ES 203 119-6 Test Description Language (TDL), Mapping to TTCN-3

Start of work	16-Sep-2019

Stable draft	15-Jan-2020	(input to MTS#79)

Final draft	15-May-2020	(input to MTS#80)

Publication	30-Jun-2020

RES/ES 203 119-7 Test Description Language (TDL), Extended Test Configurations

Start of work	16-Sep-2019

Stable draft	15-Jan-2020	(input to MTS#79)

Final draft	15-May-2020	(input to MTS#80)

Publication	30-Jun-2020

TR 103 119 Test Description Language (TDL), Reference Implementation and User Guidelines

Start of work	16-Sep-2019

Early draft	15-Jan-2020	(input to MTS#79)

Final draft	15-May-2020	(input to MTS#80)

Publication	30-Jun-2020

# Work plan, time scale and resources

## Organization of the work

The major goal of this STF is to handle existing and incoming user requests for updates to the TDL standards and the TDL open source project. It is essential for the continued growth of the TDL user community that TDL is maintained and the TDL open source project is aligned with these changes. It targets stakeholders both within ETSI and within the industry. The work is organized around the activities necessary to maintain the TDL standards and the TDL open source project (TOP) based on feedback from various stakeholders who have been adopting TDL early on. The activities are focused on maintaining the existing standards and the tool implementations within TOP according to new and changing requirements as well as providing further information and guidelines to streamline the adoption of TDL.

Intermediate stable drafts and final drafts will be delivered at milestones set in regular intervals which coincide with the plenary sessions of TC MTS. Once draft versions of the TDL updated standards become available, they will be sent out to ETSI MTS and parties outside of ETSI for review and feedback. There are multiple milestones intended for soliciting feedback such that there is enough room for delivering enhanced and improved TDL standards and updates of the tools that fit the needs of different organizations and users.

The working group MTS TDL will act as a steering group (SG) for the proposed STF and take an active role in overseeing and advising the work of the STF. It will plan regular meetings between the STF working sessions to monitor the progress of the work and provide technical advice.

## Task description

Task 0 – Project Management

Objectives

Planning, organisation, and preparation of STF meetings

On-going reporting

Participation at TC/WG meetings

Delivery of the STF final report

Input

This ToR

Information from the preparatory meeting

TDL CRs in the ETSI Mantis system and TOP reports from the TOP Bugzilla system

Expertise availability information and other project management data

Output

Session planning

Materials for SG and TC meetings

Progress reports

Final report

Interactions

The STF leader will interact with the MTS TDL working group and the MTS

Communicating with other stakeholders and STFs

Additional support will be provided by the ETSI secretariat

Resources required

4 800 EUR (planning, reporting, coordination)

Task 1 – Evolution of TDL

Objectives

Resolving open CRs

Design of new features according to the submitted CRs, e.g.

  - Inheritance support to improve reusability of TDL specifications

  - Improved separation of globally ordered vs locally ordered test descriptions

  - Test data specification for parameterised test descriptions

  - Dependency specification between test descriptions

Mapping of new TDL features to TTCN-3

Affected parts: MM, TO, GR, XF

Input

CRs from ETSIs Bug Tracker (Mantis)

ES 203 119-1 V1.4.1 Test Description Language; Meta-Model and Semantics

ES 203 119-2 V1.3.1 Test Description Language; Graphical Syntax

ES 203 119-3 V1.3.1 Test Description Language; Exchange Format

ES 203 119-4 V1.3.1 Test Description Language; Structured Test Objective Specification

ES 203 119-6 V1.1.1 Test Description Language (TDL); Mapping to TTCN-3

ES 203 119-7 V1.1.1 Test Description Language (TDL); Extended Test Configurations

TR 103 119 V1.1.1: The Test Description Language (TDL); Reference Implementation

Output

Revised versions of the input documents (updated as needed, parts for which no changes are required will not be revised)

Interactions

The SG is involved to provide technical advice in case there are or conflicting opinions on technical matters

Additional discussions with users and tool vendors (via Mantis) according to the submitted CRs

Resources required

28 000 EUR (CRs resolution)

Task 2 – TOP Maintenance and Enhancements

Objectives

Resolving about 17 open CRs

Align TOP implementation with changes in the standards according to Task 1

Update to latest Eclipse version

Improving user experience: standard data type library

Input

CRs from the TOP issue tracking system

Revised versions of the input documents from Task 1 (working and final drafts)

Output

New releases for the TOP plugins incorporating the resolved CRs

Interactions

The SG is involved to provide technical advice in case there are or conflicting opinions on technical matters

Additional discussions with users and tool vendors (via Mantis) according to the submitted CRs

Resources required

42 000 EUR (CRs resolution, alignment with incoming changes to the standards and the operational environment)

Task 3 – Validation and User Guidelines

Objectives

Validate the consistency of TDL documents against TOP implementations

Resolve any inconsistencies

Provide user guidelines to work with TOP tools that cover typical user stories, e.g. how to create a test objective specification, how to refine a test objective to a test description, how to apply the TDL-to-TTCN-3 mapping

Update online documentation, wiki, examples

Input

Revised versions of the input documents from Task 1 (working and final drafts)

New releases of the TOP plugins from Task 2 (interim versions)

Existing examples and online documentation

Output

Updated online documentation

Updated examples

Feedback for the finalisation of Task 1 and Task 2

Interactions

The MTS TDL working group is involved to provide technical advice in case of conflicting opinions on technical matters

Additional discussions with users and tool vendors (via Mantis) according to the submitted CRs

Resources required

16 800 EUR (CRs resolution, alignment with incoming changes to the standards)

## Milestones

Milestone 0 – Start of Work

Team of experts is set up and ready to work. STF workplan and timeline is available, sessions are planned.

Milestone 1 – Stable Drafts

Workable solutions for all deliverables on TDL (Task 1) are available and ready for review at MTS#79. TOP tools are updated accordingly (Task 2). Technical Report on reference implementation updated. Task 3 on validation has started.

Progress Report to be approved by MTS#79

Milestone 2 – Final Drafts

Tasks 1, 2, and 3 completed. All deliverables on TDL and TOP, including user guide, are in their final drafts and STF Final Report to be approved by MTS#80. TOP is updated to the latest versions (source code, documentation) and ready to use. All open CRs are closed or postponed with justification.

Milestone 3 – Deliverables Approved & Published

Task 0 completed. All deliverables are in the state for publication as checked by the ETSI Secretariat.

## Task summary

| N | Task / Milestone / Deliverable | Target date | Estimated cost |
| --- | --- | --- | --- |
|  |  |  | EUR |
| M0 | Start of work | 16-Sep-2019 |  |
| T0 | Project Management | 16-Sep-2019 – 30-Jun-2020 | 4 800 |
| T1 | Evolution of TDL | 16-Sep-2019 – 31-May-2020 | 28 000 |
| T2 | TOP Maintenance and Enhancements | 16-Sep-2019 – 31-May-2020 | 42 000 |
| T3 | Validation and User Guidelines | 01-Dec-2019 – 31-May-2020 | 16 800 |
| M1 | Stable drafts (MTS#79) | 15-Jan-2020 |  |
| M2 | Final drafts (MTS#80) | 15-May-2020 |  |
| M3 | Deliverables approved & published, STF closed | 30-Jun-2020 |  |
| Total | 91 600 |

| Task/ Milest. | Description | S | O | N | D | J | F | M | A | M | J |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M0 | Start of work |  |  |  |  |  |  |  |  |  |  |
| T0 | Project Management |  |  |  |  |  |  |  |  |  |  |
| T1 | Evolution of TDL |  |  |  |  |  |  |  |  |  |  |
| T2 | TOP Maintenance and Enhancements |  |  |  |  |  |  |  |  |  |  |
| T3 | Validation and User Guidelines |  |  |  |  |  |  |  |  |  |  |
| M1 | Stable drafts (MTS#79) |  |  |  |  |  |  |  |  |  |  |
| M2 | Final drafts (MTS#80) |  |  |  |  |  |  |  |  |  |  |
| M3 | Deliverables approved & published, STF closed |  |  |  |  |  |  |  |  |  |  |

## Working methods and travel cost

The nature of the work requires a mixture of independent preparatory work by the individual experts assigned to each task as well as coordinated working sessions where all experts exchange and discuss new findings and make decisions on open technical issues. Prior experience with work on TDL has shown that 1-2 coordinated working sessions per milestone with individual and coordinated homework in between deliver satisfactory results and fit into the experts’ general availability while keeping the travel overhead for the experts at an acceptable level. One or more working sessions may take place at ETSI in order to facilitate close collaboration with stakeholders at the ETSI premises as needed. Depending on the availability and potential travel restrictions for the experts, the hosting for the remaining working sessions may be distributed among the experts.

The progress of the STF shall be presented at TB meetings with the STF leader or at least one appointed expert attending in person at the TB meetings. Other experts may join the TB meetings online as necessary. Regular coordination meetings will be organised online between working sessions or in conjunction with TB meetings for technical discussions between the STF and MTS TDL. The experts may attend other events such as conferences or other TB meetings as mission travel on behalf of the STF in order to interface with stakeholders.

Travel costs for working sessions will be included in the contract compensation. Travel costs for attending the TB meetings and associated SG meetings as well as other mission travel will be reimbursed to the expert directly from the travel budget upon agreement and approval of the mission travel.

# Expertise required

## Team structure

Up to 4 experts to ensure the following mix of competences (Tasks 1, 2, and 3):

- Deep understanding of the existing TDL and its application;

- Deep understanding of black-box testing and testing of communicating real-time systems;

- Experiences in modelling and description techniques such as TTCN-3, UML, MSC;

- Experiences in UML meta-modelling;

- Experiences in the design of software languages and compiler/transformation techniques, including model-transformation techniques;

- Experiences in the model-based implementation of software languages including concrete graphical and textual syntax implementation, syntactical and semantic model validation.

Part III:	Financial conditions

# Maximum budget

## Manpower cost

The following table summarizes the needed efforts per task, which provides the base estimation for the manpower costs to be expected.

| T0 | Project Management | 4 800 |
| --- | --- | --- |
| T1 | Evolution of TDL | 28 000 |
| T2 | TOP Maintenance and Enhancements | 42 000 |
| T3 | Validation and User Guidelines | 16 800 |
|  |  | 91 600 |

The total manpower costs of this proposed STF can be estimated to be about 91 600 EUR.

## Travel cost

| Expected travels | Cost estimate (EUR) |
| --- | --- |
| Participation at MTS#79 | 1 000 |
| Participation at MTS#80 | 1 000 |
| Participation to UCAAT 2020 (October 2020) | 1 000 |
| Total cost | 3 000 Euro |

## Other Costs

No other costs are foreseen.

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from ETSI Members to STF work

Direct financial contribution (co-funding)

Support to the STF work (e.g. provision of test-beds, organization of workshops, events)

Steering meetings with MTS TDL (number of meetings / participants / duration)

Number of delegates directly involved in the review of the deliverables

Contributions/comments received from the reference TBs

Contributions/comments received from other TBs

Contribution from the STF to ETSI work

Contributions to TC/WG meetings (number of documents / meetings / participants)

Contributions to other TBs

Presentations in workshops, conferences, stakeholder meetings

Liaison with other stakeholders

Stakeholder participation in the project (category, business area)

Cooperation with other standardization bodies

Potential interest of new members to join ETSI

Liaison to identify requirements and raise awareness on ETSI deliverables

Comments received on drafts (e.g. on WEB site, mailing lists, etc.)

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Comments from Quality review by TB

Comments from Quality review by ETSI Secretariat

Time recording

For reporting purposes, the STF experts shall fill in the time sheet provided by ETSI with the days spent for the performance of the services.

In the course of the activity, the STF Leader shall collect the relevant information, as necessary to measure the performance indicators. The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 1.0 | 28-Feb-2019 | Kristoffersen | First draft |  |
| 1.1 | 15-Mar-2019 | Makedonski | Second draft |  |
| 1.2 | 16-Apr-2019 | Ulrich | Final draft |  |
| 1.3 | 29-Apr-2019 | Youssouf Sakho | TB Approved |  |
| 1.4 | 24-May-2019 | Ulrich | Budget aligned | Cost figures and timeline updated |
| 1.5 | 25-June-2019 | Youssouf Sakho | Board Approved | Updates before CL publication |