|  | ToR STF DM (TC ATTM / WG SDMC) |
| --- | --- |
|  | Version: 0.61 |
|  | Author: Dominique Roche – Date:12 June 2019 |
|  | Last updated by: Youssouf Sakho– Date:20 November 2019 |
|  | page 1 of 19 |

Terms of Reference – Specialist Task Force

STF DM (TC ATTM / WG SDMC)

“Analysis to Standardization of Sustainable Digital Multiservice Communities”

Summary information

| Approval status | Approved by TC ATTM by Remote Consensus on 03 September 2019 Approved by Board#124 (24-26 September 2019) |
| --- | --- |
| Funding | Maximum budget: 61 000 € ETSI FWP |
| Time scale | November 2019 to June 2020 |
| Work Items | DTR/ATTMSDMC-8 : TR 105 177 DTR/ATTMSDMC-9 : TR 105 178 |
| Board priority | Emerging domains for ETSI |

Part I – Reason for proposing the STF

# Rationale

The continuing and increasing migration of people moving from rural areas to live permanently in cities has generated, for the city administration, an exponential increase in the demand of services. The integration of technology to optimize and make the services in the city more efficient and thus satisfy the growing service demand has encouraged the proliferation of Smart Communities. Smart Communities build upon the opportunity to rationalize investments and integrate several sectors of the society, solutions and systems.

However, this economic and social approach is generating the major challenge of exchanging data, interconnecting services and systems. The standardisation of data exchange platforms among the different sectorial systems is essential is to:

reduce operational costs and increase service efficiency for existing Smart Communities;

encourage new community entrants by providing confidence in the early decision-making phases.

Most major European metropolises and some rural communities are now aware of the urgency and importance of the large-scale rollout of new and smart services which will be both citizen-centric and dedicated to promoting sustainable and resilient Communities.

Despite this urgency, the multitude of solutions proposed by manufacturers and service providers in very diverse functional areas do not allow Communities, and other local authorities, to commit with confidence to industrial-scale rollout.

Communities need guarantees and continuity for major investments. They need reliable indicators and benchmarks shared by their entire community which reveal their level of maturity as “Smart Communities”, or to the steps they need to take to become one. Smart Communities also need to outline the solutions proposed for measuring whether the process is «working». This is reflected in the dramatic rise in the number of “Plugtests™” which allow suppliers to work on practical scenarios such as centralised energy management and territorial-level traffic, as seen during the recent ETSI IoT/M2M workshops.

Given these expectations, manufacturers and suppliers are driven by the same pressing need to move from the demonstrator level to industrial-scale rollout. Interoperability is the key to cutting costs, especially operating expenditure.

The process taking into account the needs of Communities must be initiated in order to be able to lead this bottom-up approach.

ETSI TC ATTM SDMC acts as a hub between Communities and the standardisation area. It builds upon community activities and supports the longer-term upscaling and sustainability of their deployments. TC ATTM SDMC gathers feedback from field tests from Communities funded within the SCC-01.

NOTE: 	SCC-01: Smart Cities and Communities solutions integrating energy, transport, ICT sectors through lighthouse (large scale demonstration – first of the kind) projects

In addition, ETSI TC ATTM SDMC takes input from the 120 EUROCITIES Knowledge Society Forum (KSF) cities.

The STF Team will be supported by the administrative structure of Eurocities, an NGO which at this time represents more than 140 major European cities and first rural communities in order to consolidate and to rationalize demands.

The STF Team will rely on a Pivotal Point of Interoperability (PPI)-type approach as advocated in the report of the European Commission on standards for Smart Cities and Communities (SCCs) supporting the action H2020 CSA3 Espresso.

NOTE: 	ESPRESSO = Enhancing Synergies for disaster PRevention to Empower Smart citieS and cOmmunities

The STF will identify, consolidate and create reports dedicated to this approach and described results of analysis of dat.

# Objective

Further to some last ETSI standard development on sustainable digital multiservice communities two important subjects for “Smart Community” development and expansion have been taken into account to  support the best deployment and implementation of the most efficient solution in the field :

The first is an ETSI Technical Report, addressing “Benefit Analysis of Ethernet and Power over Coaxial Cables in IP Video Surveillance Case Studies” and performing benefit analysis and the beneficial impact on the environment for selected use cases (such as mass transit systems) comparing the replacement of legacy coaxial cables with new cables with the re-use of legacy coaxial cables to support Ethernet and Power over coaxial equipment for IP Video Surveillance.

The second is an ETSI Technical Report, addressing “Life Cycle Analysis comparison between internal and “cloud-based” hosting solutions” and addressing:

- energy consumption,

- green-house gas (GHG) emission;

- water consumption,

- waste management from production to end-of-life management.

In order to issue these two deliverables by early 2020, several specialists should join the STF team. Specialists will be experts on city governance, telecommunications, electronics, mobile devices (including 5G) and video surveillance.

The STF schedule is summarized as follows:

initial drafts to be issued by Q1, 2020;

stable drafts to be issued by Q1, 2020;

final drafts to be issued by Q2, 2020.

# Relation with ETSI strategy and priorities

This STF is requested in order to support the deployment efficient solutions of sustainable digital multiservice in Communities, including 5G and broadband networks.

The deliverables of the STF will build upon existing ETSI ENs to include further detail and requirements in relation to efficient engineering and Global KPIs for sustainable digital multiservice Communities (ETSI EN 305 174 Series & ETSI EN 305 200 Series) as well as TSs  on ICT infrastructure (ETSI TS 110 174 Series) to support both the deployment of services and the most efficient access to information to support the digital multiservice communities .

# Context of the proposal

## ETSI Members support

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Airbus DS SLC | Alberola Jean-Marc | Approved in ATTM#25 Plenary & Confirmed in OEU#16 |
| eG4U | O’Keeffe Pat | Approved in ATTM#25 Plenary |
| Orange | Bouffant Olivier | Approved in ATTM#25 Plenary |
| SBS aisbl | Babinov Georgi | Support of ATTM in ATTM#25 Plenary |
| SIAE Microelettronica SpA | Macchi Roberto | Approved in ATTM#25 Plenary |
| Skylane Optics | Philippe Bolle | Approved in ATTM#25 Plenary & Confirmed in OEU#16 |

## Market impact

Interoperable and standardized solutions supported by the right specifications and reports will bring confidence to communities. This will enable them to make progressive and long-term investments towards their Smart Community objectives.

This commitment will consequently enable manufacturers to deploy their solutions much more quickly and to industrialize services and processes by generating value.

The proposal is therefore to initialize this virtuous circle in which each of the actors (i.e. communities, companies and citizens) will have results that suit them in the end which will constitute de-facto a breeding ground favorable to large scale deployment.

The European network of Smart Communities and Communities (SCCO1) aggregates the replication needs regarding H2020 lighthouse project (9 projects for 57 cities).

A main issue identified is the renewal of the existing video surveillance systems and data management systems in European Communities in order to make them “smart & efficient”. Communities cannot afford the total replacement with fully new video surveillance infrastructures.

## Tasks for which the STF support is necessary

ETSI needs specific technical expertise that is not currently present within the associated technical committees. For example, these specialists will assist in identifying, consolidating or even creating reports accordingly to the Rationale above.

Therefore, under this proposed action ETSI will perform the work described above with the support of an ETSI Specialist Task Force (STF).

The work of this STF will be essential to aid the drafting and preparation of the required deliverables as rapidly as possible in order to maximise the resulting benefits and to publish the required solutions by early 2020 (as ETSI Technical Reports) in order to be taken into account by the European communities (metropolises and rural areas) in the list of European ETSI Reports attached to the foreseen new European Community projects (e.g. Transportation security, Community video surveillance, Citizen cards, Mobility as a service app, etc.) supporting the development of efficient and smart ICT products and services.

The STF will develop the draft technical content for the planned deliverables through consultation with stakeholders by means of active liaisons with technical committees of official organizations (European/International Standardization Organizations, fora), meetings, workshops and desk-based research in order to ensure that field needs, and the most improved solutions are taken into account and resulting in state of the art standards.

In order to complete the work in due time (final target being Q2, 2020), the STF will base its work on current ETSI specifications (existing or in development) with the support of the involved ETSI committee ATTM SDMC. Other available European and international standards/specifications will be also considered for this task.

TC ATTM SDMC acts as a hub between Communities and the standardisation area. It builds upon city activities and supports the longer-term upscaling and sustainability of their deployments. TC ATTM SDMC gathers feedback from field tests and studies from Communities and ICT users, in addition, the 120 EUROCITIES Knowledge Society Forum (KSF) cities.

## Related voluntary activities in the TB

TC ATTM SDMC and TC ATTM AT2 will provide contributions in order to support the development of the STF deliverables.

## Previous funded activities in the same domain

TC ATTM has had no benefit of STF support in this domain.

## Consequences if not agreed

If the STF will not be accepted the publication of these deliverables will be delayed.

Failure to deliver the proposed deliverables risks further proliferation of Non-efficient and non-standard solutions. This slows down the establishment of new Smart Communities which impacts both operators (in terms of deployment of infrastructure and technology) and those responsible for community development within the communities themselves

Part II – Execution of the work

# Technical Bodies and other stakeholders

## Reference TB

TC ATTM WG SDMC will be responsible for the technical guidance of the STF. This group will support the STF with some specific additional specialists on community networking (experts from Communities).

## Other interested ETSI Technical Bodies

Several ETSI actors will be involved in this activity in order to ensure integration of their needs and knowledge.

ETSI TC SmartM2M and One M2M will be able to support the STF study by M2M.

ETSI ISG CIM will be able to support the STF study by CIM knowledge and on service implementation works.

ETSI ISG OEU will be able to support the STF study by ICT Users’ field knowledge.

## Other stakeholders

Several other stakeholders will be involved in this activity in order to ensure integration of their needs and knowledge.

The oneM2M forum will be able to support the STF study by M2M.

CENELEC Technical Committee CLC/TC 215 will be invited to support the STF study by knowledge on equipment installation.

Cooperation will be ensured with ITU-T SG20 on smart city deployment.

# Base documents and deliverables

## Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| ETSI EN 305 174 series | Broadband Deployment and Lifecycle Resource Management | Published |  |
| ETSI EN 305 200 series | Energy management; Operational infrastructures; Global KPIs | Published |  |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | DTR/ATTMSDMC-8 TR 105 177 | Working title: Benefit Analysis of Ethernet and Power over Coaxial Cables in IP Video Surveillance Case Studies Scope: The present document will perform benefit analysis and the beneficial impact on the environment for selected use cases (such as mass transit systems) comparing the replacement of legacy coaxial cables with new cables with the re-use of legacy coaxial cables to support Ethernet and Power over coaxial equipment for IP Video Surveillance. |
| D2 | DTR/ATTMSDMC-9 TR 105 178 | Working title: Life Cycle Analysis comparison between internal and external “cloud-based” hosting solutions Scope: The present document will provide a comparison between both internal and external “cloud-based” solutions with a life cycle analysis addressing: energy consumption; green-house gas (GHG) emission; water consumption; waste management from production to end-of-life management. |

## Deliverables schedule:

DTR/ATTMSDMC-105177

Start of work	28-Nov-2019

Early draft	31-Jan-2020

Stable draft	31-Mar-2020

Final draft	30-Apr-2020

TB Approval	15-May-2020

Publication 	30-Jun-2020

DTR/ ATTMSDMC-105178

Start of work	28-Nov-2019

Early draft	31-Jan-2020

Stable draft	31-Mar-2020

Final draft	30-Apr-2020

TB Approval	15-May-2020

Publication 		30-Jun-2020

# Work plan, time scale and resources

## Organization of the work

The STF work and its programming schedules will be supervised by a Steering Committee (SC).

As mentioned above, the proposed action will be directed and supervised by a Steering Committee taken from:

Chairman of ETSI TC ATTM and its Working Groups and extended as required to include specific additional ETSI specialists, e.g. “Plugtests™” specialists (ETSI CTI), Home Networking experts;

Chairman of ETSI TC SmartM2M and its Officials and One M2M representative in order to support the STF study by M2M knowledge;

Chairman of ETSI ISG CIM and officials in order to support the STF study by CIM knowledge on service implementation works;

Chairman of ETSI ISG OEU and Officials in order to support the STF study by ICT Users’ field knowledge;

Relevant ETSI Technical Officers;

The STF will report on its milestones to Steering Committee and ETSI TC ATTM.

The STF work will be divided into 7 tasks and 4 milestones will be scheduled. The milestones will be as following:

- Start-up activities [Milestone 1]

- Table of contents, scope, early drafts & Progress Report to SC and TC ATTM [Milestone 2]

- Stable drafts & Progress Report to SC and TC ATTM [Milestone 3]

- Final drafts & Final Report to SC and TC ATTM [Milestones 4].

Conclusions & Publication

## Task description

The proposed action will be performed as described in the following tasks:

Task 1 – Establish Specialist Task Force (STF)

Objectives

The purpose of this Task 1 is to establish the Steering Committee (SC) and the STF team.

Input

The STF providers will be selected and recruited following the agreed ETSI procedures. The ETSI STF providers will be recruited following the issuing of an ETSI Collective Letter.  This will also be available from the ETSI STF page on the ETSI Portal and via the ETSI website.

The STF must be able to issue the appropriate operational ETSI Technical Reports to support deployment, the life, and the end of life of efficient and sustainable digital multiservice Communities.

Output

The STF will include providers, which must be prepared to work in close cooperation to share the tasks under the guidance of the reference Technical Bodies.

One of the providers will act as STF Leader and will be responsible for the consolidation of the documentation, coordination the STF activities and the provision of the required progress reports to the steering committee. This provider will also be responsible for the drafting of the Progress and Final Reports to the Steering Committee.

The other providers must be able to perform specific tasks (e.g. fixed and mobile equipment and networks,  data centres, video surveillance systems).

Interactions

The ETSI Director-General has the responsibility for the selection of the providers in consultation with the Chairman of TC ATTM. The ETSI Secretariat and the Chairman of TC ATTM, possibly assisted by the STF-SC, will assess the qualifications of the applicants for the STF during the selection.

Resources required

The STF will consist of providers with strong competence and knowledge in Smart Community services and ICT technologies and operational sites and networks.

Task 2 – Start-up activities [Milestone 1]

Objectives

The purpose of this task is to start the work in order to issue the deliverables requested in clause 6.2.

Input

In order to start this work the following activities will be performed a kick-off Meeting between the SC members and STF team to:

ensure a clear understanding of the objective(s) of this action;

identify and engage participants/partners that are able:

- to assist in the survey of existing source material;

- to support the development of results which link research activities into evolving convergence strategies with coordinated standardization activities and the identification of best-practice official documents.

Output

The STF will propose its work schedule to SC for approval and in compliance with the action grant [Milestone 1]:

the SC will approve the STF work schedule;

the STF will manage the start-up of the work.

Interactions

ETSI STF management team will organize the kick-off meeting.

Resources required

STF team and SC members will participate in kick-off meeting in ETSI premises.

Task 3 – Project Management

Objectives

The purpose of this task is to manage the project.

Input

The STF Team leader will be in charge of this task fromTask 2 (Start-up activities) until Task 7 (Conclusions, Publication & Final Report to SC and TC ATTM).

Output

The Project Management will include production of progress and final reports.

Interactions

STF Team leader will manage the project with support of ATTM and SDMC Chairmen.

Resources required

The Project Management will be done by STF Team leader.

Task 4 – Research, analysis - Consultation and dissemination - Table of contents, scope - Early drafts- Progress Report to SC and TC ATTM [Milestone 2]

Objectives

The purpose of this task is to:

determine source material availability in support of the objective/goal of the action to:

include the outputs of the H2020 projects (e.g. smart Communities standardization);

include and, where appropriate, enlarge upon the outputs of EC and national governments initiatives on green smart Communities;

- identify areas of source material shortfall with regard to the objective/goal of the action.

- determination of source material availability and the identification of areas of source material shortfall will require significant input

- STF will issue tables of contents and scopes of the early draft deliverables stated in clause 6.2.

Input

Analyse results of the research and issue task 3 report.

STF will analyse results of the research.

Consultation and dissemination will come from the following stakeholders:

the service development and supply industry;

users, operators included;

standardization bodies (from the SDOs, fora and elsewhere e.g. oneM2M, TM Forum, ANSI, ITU, 3GPP).

STF will provide these tables of contents and scopes of the deliverables to the SC and to ETSI TC ATTM for comment.

STF will improve the tables of contents and scopes of the deliverables further to the comments received from the SC and ETSI TC ATTM.

STF will provide these initial draft versions of the deliverables to SC, and ETSI TC ATTM for comment and review.

An Progress Report will be provided to SC and TC ATTM 4 months after the start of the action to report on the activity performed until that date along with the latest versions of the draft TSs.

Output

The Progress Report will cover the activity leading up to the data resulting from analysis covering:

documentation addressing broadband deployment (international, regional, national);

research tools in support of the objective of the action;

the availability of standards and associated documents from standardization bodies (SDOs, fora and elsewhere).

The final version of tables and scopes will be provided to the SC, and ETSI TC ATTM and the ETSI work programme will be updated.

In order to achieve consultation and dissemination the STF will open active liaisons with technical committees of official organizations (European/International Standardization Organizations, fora).

Further to finalization of the final version of tables and scopes an open Workshop will be organized in ETSI premises at the end of this task 4 in order to present the STF work and the future deliverables.

As a result of the comments received the STF will improve the draft versions of the deliverables and will improve versions of initial draft versions of the.

STF will provide a Progress Report to SC by end of this task 4 period [Milestone 2].

Interactions

STF Team leader will manage research and analysis with STF Team and Communities involved in eG4U.

STF will manage meetings (physical or audio) in order to ensure that they take into account field needs and the most improved solutions.

STF will work with SC and ETSI TC ATTM.

STF will develop the technical content of the deliverables through consultation with stakeholders by means of active liaisons with technical committees of official organizations (European/International Standardization Organizations, fora) and desk-based research in order to ensure that field needs and the most recent solutions are taken into account.

Resources required

The STF leader will manage this task.

The STF leader will manage liaisons as meetings with ATTM and ATTM SDMC Chairmen.

The STF managed by STF leader will develop the draft versions of deliverables.

The STF Team leader will issue the Progress Report and provide it to SC and TC ATTM.

Task 5 – Stable drafts [Milestone 3]

Objectives

In order to issue stable drafts of the requested deliverables the STF will complete technical content of the initial drafts coming from task 4.

Input

The STF will develop these stable drafts through consultation with stakeholders by means of active liaisons with technical committees of official organizations (European/International Standardization Organizations, fora).

Output

The STF will provide the stable drafts of the deliverables to the SC, and ETSI TC ATTM for comments.

The STF will provide a Progress Report to SC by mid of Task 8 period [Milestone 3].

Interactions

The STF will finalize these developments in cooperation with ETSI ISG OEU (ICT Users) by means of presentations and idea exchanges in a workshop with providers and users in order to ensure that they fully take into account field needs and most improved solutions.

Resources required

The STF managed by STF leader will develop the draft versions of deliverables.

The STF leader will issue the Progress Report.

Task 6 – Final drafts - Final Report for delivery to the SC and TC ATTM [Milestone 4]

Objectives

The STF will further improve the stable drafts of the deliverables in the light of further comments from the ETSI TCs.

Input

The STF will prepare and provide the final drafts of the deliverables to ETSI TC ATTM for TC approval prior to ETSI approval.

Output

STF will provide Final Report for delivery to the SC and TC ATTM [Milestone 4] with:

a report on the activities performed;

a report on the performance indicators as defined in clause 6

The publication versions of 2 TSs as defined in clause 7.

Interactions

ETSI will circulate deliverables at the ETSI TC ATTM level. That means that ETSI members will have the opportunity to provide comments which may require further resolution.

Resources required

The STF managed by STF leader will develop the final draft versions of deliverables.

The STF leader will issue the Progress Report.

Task 7 – Conclusions, Publication & Final Report to SC and TC ATTM

Objectives

Further to the development of Task 6 STF will provide Final Progress Report to SC and TC ATTM. This report will include STF conclusions.

Input

The STF will take into account the last comments from ETSI TC ATTM in order to support this TC for resolution of these comments.

Output

Further to the voting results, ETSI will publish the adopted ETSI Technical Specifications.

Interactions

The STF will assist ETSI TC ATTM to resolve received comments from National Standardization.

Resources required

The STF Team leader will issue the Final Report.

It is estimated that there will be a number of missions performed throughout the action involving reporting to TB meetings, SC meetings plus other missions to the ITU and to an ISO/IEC meeting in Europe. The missions will be mainly performed by the STF leader with other missions shared between the experts as required.

## Milestones

Milestone 1 – Start-up activities

The purpose of this Milestone 1 is to start the work in order to issue the deliverables requested in clause 6.2.

Milestone 1 will be reached by mid of November 2019.

Milestone 1 activities will be done with SC.

Milestone 2 – Table of contents, scope - Early drafts & Progress Report to SC and approved by TC ATTM

The STF will issue tables of contents and scopes of the draft deliverables stated in clause 6.2.

A Progress Report will be provided to SC and approved by TC ATTM.

Milestone 2 will be reached by end of January 2020.

Milestone 2 will be done by the STF.

Milestone 3 – Stable drafts & Progress Report to SC and approved by TC ATTM

The STF will issue stable draft versions of the deliverables requested in clause 6.2.

A Progress Report will be provided to SC and approved by TC ATTM.

Milestone 3 will be reached by end of March 2020.

Milestone 3 will be done by the STF.

Milestone 4 – Final drafts, conclusions, Publication & Final Report to SC and approved by TC ATTM

The STF will issue final draft versions of the deliverables requested in clause 6.2.

The STF will provide Final Report for delivery to the SC and to be approved by TC ATTM.

Milestone 4 will be reached by June 2020.

Milestone 4 will be done by the STF.

## Task summary

| N | Task / Milestone / Deliverable | Target date |  |
| --- | --- | --- | --- |
|  |  |  | Estimated cost |
| T1 | Establish Specialist Task Force | Oct-Nov 2019 |  |
| T2 | Start-up activities | Nov 2019 |  |
| M1 | Start-up activities | Nov 2019 | 0 |
| T3 | Project Management (incl. production of progress and final reports) | Nov 2019 – May 2020 | 6 000 |
| T4 | Research, analysis to determine source material Consultation, dissemination: open active liaison with stakeholders Development of Table of contents and scope to be presented to an ETSI Workshop Early drafts on: - Benefit Analysis of Ethernet and Power over Coaxial Cables in IP Video Surveillance Case Studies - Life Cycle Analysis comparison between internal and external “cloud-based” hosting solutions | Nov 2019 – Jan 2020 | 29 000 |
| M2 | Tables of contents, scopes of the early draft deliverables and Progress Report to SC and ATTM will be approved by ATTM | 31-Jan-2020 |  |
| T5 | Stable drafts on: - Benefit Analysis of Ethernet and Power over Coaxial Cables in IP Video Surveillance Case Studies - Life Cycle Analysis comparison between internal and external “cloud-based” hosting solutions | Mar 2020 | 10 000 |
| M3 | Stable drafts of the deliverables will be issued Progress Report approved by TC ATTM | 31-Mar-2020 |  |
| T6 | Final drafts on: - Benefit Analysis of Ethernet and Power over Coaxial Cables in IP Video Surveillance Case Studies - Life Cycle Analysis comparison between internal and external “cloud-based” hosting solutions | Apr 2020 | 10 000 |
| M4 | Final Report made available for SC review Final drafts and Final Report to be approved by TC ATTM Deliverables published. STF closed | 30-June-2020 |  |
| T7 | Conclusions, Publication STF closed | June 2020 |  |
| Total | 55 000 |

|  | Month |
| --- | --- |
|  | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 |
| Task / Milest. | Description | 1 | 2 | 3 | 4 | 5 | 7 | 8 | 9 | 10 |
| T1 | Establish Specialist Task Force |  |  |  |  |  |  |  |  |  |
| T2 | Start-up activities |  |  |  |  |  |  |  |  |  |
| M1 | Start-up activities |  |  |  |  |  |  |  |  |  |
| T3 | Project Management |  |  |  |  |  |  |  |  |  |
| T4 | Research, analysis to determine source material Consultation, dissemination Development of Table of contents and scope to be presented to an ETSI Workshop Early drafts of deliverables: - Benefit Analysis of Ethernet and Power over Coaxial Cabling in IP Video Surveillance Case Studies - Life Cycle Analysis comparison between internal and external “cloud-based” hosting solutions Progress Report to SC and TC ATTM |  |  |  |  |  |  |  |  |  |
| M2 | Tables of contents and scopes of the draft deliverables will be issued Early drafts of the deliverables will be issued Progress Report approved by TC ATTM |  |  |  |  |  |  |  |  |  |
| T5 | Stable drafts of deliverables |  |  |  |  |  |  |  |  |  |
| M3 | Stable drafts of the deliverables will be issued |  |  |  |  |  |  |  |  |  |
| T6 | Final drafts of deliverables |  |  |  |  |  |  |  |  |  |
| M4 | Final drafts of the deliverables will be issued Final Report to SC and TC ATTM approved by TC ATTM |  |  |  |  |  |  |  |  |  |
| T7 | Conclusions, Publication |  |  |  |  |  |  |  |  |  |

## Working methods and travel cost

The STF work will be performed as described in §7.4:

- Task 1:	No meeting

- Task 2:	One meeting of SG to be done

- Task 3:	No face to face meeting to be scheduled, coordination session remotely done

- Task 4:	Stakeholder consultation, coordination session remotely done

- Task 5:	No face to face meeting to be scheduled, coordination session remotely done

- Task 6:	No face to face meeting to be scheduled, coordination session remotely done

- Task 7:	No face to face meeting to be scheduled, coordination session remotely done

# Expertise required

## Team structure

The following relevant expertise is required in STF Team:

One provider acting as STF leader, with a proven record of standards project delivery:

Possess a strong knowledge of project management, report writing, consensus building, presentation skills, working in an international environment;

Have hands-on experience in the implementation of communications sites (data centres included), networks, systems and services deployed in community areas.

Three providers, with the following qualifications:

Hands-on experience in the engineering and the implementation of communications networks, sites (data centres included), systems (video surveillance included) and services;

Good knowledge of telecommunications legislation;

Good knowledge of the use of Key Performance Indicators;

At least one with a strong knowledge of deployment and operational core and fixed networks;

At least one with a strong knowledge of deployment and operational core and mobile networks;

At least one with a strong knowledge of deployment and operational data centres, and servers, and storage;

At least one with a strong knowledge of environmental area;

At least one with a strong knowledge of waste/end of life;

At least one with a strong knowledge of operational implementation in community areas.

Part III:	Financial conditions

# Maximum budget

## Manpower cost

The maximum budget allocated to this STF will be 55 000 €.

## Travel cost

The estimate of the maximum travel costs allocated to this STF will be 6 000 €.

The STF Leader (or nominated representative from within the STF) will be required to attend multiple meetings of TC ATTM Plenary and possibly of the NGO Eurocities in order to report the documents in development and/or completed by the STF.

| Expected travels | Travel number | Cost estimate |
| --- | --- | --- |
| TC ATTM Plenary | 2 | 2 000 Euros |
| CENELEC | 1 | 1 000 Euros |
| ITU-T | 1 | 1 500 Euros |
| Eurocities | 1 | 1 500 Euros |
| Total cost |  | 6 000 Euros |

## Other Costs

No other cost has required.

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from ETSI Members to STF work

Steering Group review meetings, at least 3 meetings

Contribution / Voluntary work from ETSI TBs : TC ATTM, TC SmartM2M, ISG CIM, and ISG OEU will provide contributions in order to support development of deliverables

Workshops to promote STF activities, between 1 to 2 events

Participation of Member delegates in meetings / workshops events related to STF work [e.g. types (e.g. city service specialists, environmental specialists, network specialists) and number of participants]

Contribution of Member delegates [e.g. types (e.g. standards, presentations) and number of documents presented by delegates, types (e.g. standards, presentations) and number of documents presented by the STF for comments]

Approval of deliverables from the Reference TB according to schedule

Publication of deliverables (TSs) according to schedule

Respect of time scale, with reference to start/end dates in the approved action grant

Contribution from the STF to ETSI work

Presentations to ETSI TBs in TB plenary sessions and WG meetings

Contribution to other standardization bodies by attending body meetings (face to face or remote participation)

Liaison with communities (e.g. metropolises, towns) to identify requirements and raise awareness on the project deliverables

Contributions to TC/WG meetings (number of documents / meetings / participants)

Contributions to other TBs

Presentations in workshops, conferences, stakeholder meetings

Liaison with other stakeholders

Stakeholder representation in the project (e.g. field actors from Communities, specialists of urban area) to support improvement of proposed draft standards

Presentations to ETSI TBs in TB plenary sessions and WG meetings: mainly in TC ATTM Plenaries (Nov 2018: Apr 2019) and TC ATTM AT2 (Nov 2018: Apr 2019) and TC ATTM SDMC (Nov 2018: Apr 2019)

Liaison activities performed by the STF (e.g. workshops/ conferences/events)

Contribution to other standardization bodies by attending body meetings (face to face or remote participation)

Potential interest of new members to join ETSI, e.g. providers of smart Communities equipment

Liaison to identify requirements and raise awareness on ETSI deliverables

Comments received on drafts (e.g. on WEB site, mailing lists, etc.)

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Comments from Quality review by TB

Comments from Quality review by ETSI Secretariat

Time recording

For reporting purposes, the STF experts shall fill in the time sheet provided by ETSI with the days spent for the performance of the work.

In the course of the activity, the STF Leader shall collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 12-Jun-2019 | D. Roche | Stable Draft |  |
| 0.2 | 06-Aug-2019 | Y. Sakho |  | Update before submission to Board#124 |
| 0.3 | 26-Aug-2019 | D. Roche |  | Update before submission to Board#124 |
| 0.4 | 24-Sep-2019 | Y. Sakho | Board Approved | Update before CL publication |
| 0.5 | 11-Oct-2019 | Y. Sakho | Board Approved | Update before CL publication |
| 0.6 | 20-Nov-2019 | Y. Sakho | Board Approved | Update during Prep. Meeting: Editorials Change in the definition of the definition of WI deliverables |
| 0.61 | 20-Nov-2019 | Y. Sakho F. Cucchietti | Board Approved | Update after Prep. Meeting |