STF 701 – STAN4CR2 project

Technical Description (Part B)

(SMP STAND Standard)

Version 2.0

15 January 2025

INTRODUCTION:

This proposal, submitted by ETSI, CEN, and CENELEC, is currently undergoing minor adjustments based on feedback from EISMEA.

It covers the full scope of work of ETSI /CEN/CENELEC internal staff and subcontractors.

The present call for expertise convers only subcontracting activities under ETSI responsibility.

PROJECT FACT SHEET

STF 701 / [2024-13]

| Reference Body | TC CYBER |
| --- | --- |
| EC/EFTA Funding | Subcontracting Activities Manpower: 746 500 € Travels (estimated): 32 000 € Total Subcontracting Budget (estimated): 778 500 € |
| Project Duration | 15 months |
| WP#; Task in BC; Task names; Amount. WP1: Project management and coordination; T00; T1.1 Overall project management; 0€. T01; T1.2 Legal and Financial management; 0€. T02; T1.3 Selection of the Rapporteurs; 0€. WP2: Vertical standards development; T03; T2.1 Vertical rapporteurs’ Project Management *; 98 081€. T04; T2.2 Contribution of vertical Rapporteurs **; 571 000€. T05; T2.3 Edition of standards; 0€. WP3: Stakeholder engagement and outreach; T06; T3.1 Coordination of Rapporteurs contributions*; 22 419€. T07; T3.2 Development of the stakeholder engagement strategy **; 15 000€. T08; T3.3 Organisation of dissemination activities for stakeholder engagement and outreach **; 40 000€. |

* Tasks T2.1 & T3.1 are interdependent and must be completed by the same service provider.

** Tasks T2.2, T3.2 and T3.3 are interdependent and must be completed by the same service provider.

## TECHNICAL DESCRIPTION (PART B)

## COVER PAGE

| PROJECT |  |
| --- | --- |
| Project name: | Standardization for Cyber Resilience |
| Project acronym: | STAN4CR2 |
| Project Duration | 15 months |
| Project Start Date | 2025-04-01 |
| Fixed start date Justification: | The work on this project needs to start as early as possible for the ESOs to meet the deadlines set in the EC Standardisation Request in support of the Cyber Resilience Act. |
| Coordinator contact: | Jan Ellsberger - ETSI |

TABLE OF CONTENTS

TECHNICAL DESCRIPTION (PART B)	4

COVER PAGE	4

PROJECT SUMMARY	5

1. RELEVANCE	5

1.1 Background and general objectives	5

1.2 Needs analysis and specific objectives	6

1.3 Complementarity with other actions and innovation	7

2. QUALITY	7

2.1 Concept and methodology	7

2.2 Consortium set-up	8

2.3 Project teams, staff and experts	8

2.4 Consortium management and decision-making	13

2.5 Project management, quality assurance and monitoring and evaluation strategy	13

2.6 Cost effectiveness and financial management	14

2.7 Risk management	16

3. IMPACT	17

3.1 Impact and ambition	17

3.2 Communication, dissemination and visibility	17

3.3 Sustainability and continuation	18

4. WORKPLAN, WORK PACKAGES, ACTIVITIES, RESOURCES AND TIMING	19

4.1 Work plan	19

4.2 Work packages, activities, resources and timing	20

Work Package 1	20

Work Package 2	24

Work Package 3	27

Subcontracting	30

5. OTHER	33

5.1 Ethics		33

5.2 Security		33

6. DECLARATIONS	33

#@APP-FORM-SMPSTAND@#

#@PRJ-SUM-PS@#  [This document is tagged. Do not delete the tags; they are needed for the processing.]

## PROJECT SUMMARY

Project summary

The STAN4CR2 project plays a pivotal role in supporting the implementation of the Cyber Resilience Act (CRA), which aims to strengthen cybersecurity for hardware and software products across the EU. Focused on advancing harmonised European standards, the project drives the development of key deliverables of the CRA Standardization Request. This includes introducing Rapporteurs in the relevant working groups within CEN, CENELEC and/or ETSI, providing coordination across diverse topics, and fostering engagement with stakeholders. Through the delivery of draft Harmonized standards, the project will facilitate compliance with the new Cyber Resilience Act regulation, particularly for small and medium-sized enterprises. By promoting public awareness and collaboration, the project helps to build trust, enhance innovation, and bolster the competitiveness of the EU Single Market, ensuring resilience in the face of evolving cyber threats.

#§PRJ-SUM-PS§# #@REL-EVA-RE@# #@PRJ-OBJ-PO@#

## 1. RELEVANCE

### 1.1 Background and general objectives

The Cyber Resilience Act (CRA) aims to address the increasing cybersecurity threats faced by hardware and software products by setting essential cybersecurity requirements for manufacturers, with stricter assessments for important and critical products. The European Commission is in the process of consulting with stakeholders to develop standards supporting the CRA. The approach includes horizontal standards for a generic framework and vertical standards tailored to specific product risks. The cross-border nature of cyber threats necessitates EU-level action to ensure a competitive single market and boost trust in digital products. Harmonized standards and international standards will facilitate compliance, particularly for small and medium-sized enterprises. Timely development and availability of these standards are crucial for effective implementation, especially for important digital products. In today's dynamic market landscape, the need for a robust standardization strategy has become paramount. The evolving nature of cybersecurity-related technologies demands a strategy that is not only adaptive but also anticipates the complexities associated with groundbreaking advancements. The STAN4CR2 project aims to support and accelerate the standardization efforts within the EU, fostering collaboration and coherence in the rapidly evolving cyber security landscape, aiming to prevent security incidents and minimise the impacts of such incidents, including in relation to the health and safety of users. In order to cover the full scope of the CRA standardization request, this project will complement the efforts done under the STAN4CR project, funded by the EC and EFTA, ensuring that coordination is in place between the two projects. European standardization efforts will be dedicated to developing the remaining vertical standards complementing the work on horizontal standards being developed under the WG-9 within the CEN-CENELEC Joint Technical Committee 13 (CEN-CLC/JTC 13) “Cybersecurity and Data Protection”. Given the broad scope of “products including digital elements” and the scarcity of cybersecurity expertise, several Technical Groups of CEN CENELEC and ETSI are expected to jointly contribute to this effort in a coordinated manner. The project STAN4CR2 is positioned to provide essential coordinating and administrative resources via CEN, CENELEC and ETSI. This project’s goal is to facilitate a seamless and inclusive standardization process safeguarding at the same time appropriate connection and alignment between different horizontal and vertical workstreams. This project will also focus on carrying out stakeholders' consultations aiming to increase access and gather feedback to enrich discussion, with the objective of have an increased diversity of views, improved public awareness of standardization activities, dissemination activities, and broader engagement with relevant stakeholders. The timely development of standards will benefit industry, including Small and Medium Enterprises, policymakers, and society at large by providing a solid foundation for the integration of state of art standards into everyday applications of many digital products. Furthermore, the developments of standards to support the CRA will contribute to the resilience and competitiveness of the EU Single Market by enhancing cybersecurity measures, promoting innovation, and fostering trust among consumers and businesses alike.

### 1.2 Needs analysis and specific objectives

The CRA stands as pivotal legislation aimed at tackling the escalating cybersecurity challenges confronting hardware and software products. It establishes crucial cybersecurity requirements for manufacturers, particularly emphasizing stringent assessments for significant and critical products. The timely formulation of standards under the CRA not only serves the interests of industries, policymakers, and society at large but also furnishes a robust framework for the seamless integration of cutting-edge standards into the everyday functionality of numerous digital products. To address the stated objectives and aligning with the proposal outlined in the call, the project is envisioned to be structured around three primary needs and objectives: drafting standardization deliverables, providing administrative support, and engaging stakeholders through outreach efforts. These tasks intersect across various work packages within the project framework to respond to the deliverables requested around the following topics. (The numbers used in the list below correspond to the deliverable numbers in the Standardisation Request in support of the implementation of the CRA, to be developed jointly by the ESOs.) Table 1 List of deliverables #; Topic. 16; European standard(s) on essential cybersecurity requirements for identity management systems and privileged access management software and hardware, including authentication and access control readers, including biometric readers. 17; European standard(s) on essential cybersecurity requirements for standalone and embedded browsers. 18; European standard(s) on essential cybersecurity requirements for password managers. 19; European standard(s) on essential cybersecurity requirements for software that searches for, removes, or quarantines malicious software. 20; European standard(s) on essential cybersecurity requirements for products with digital elements with the function of virtual private network (VPN). 21; European standard(s) on essential cybersecurity requirements for network management systems. 22; European standard(s) on essential cybersecurity requirements for Security information and event management (SIEM) systems. 23; European standard(s) on essential cybersecurity requirements for boot managers. 24; European standard(s) on essential cybersecurity requirements for public key infrastructure and digital certificate issuance software. 25; European standard(s) on essential cybersecurity requirements for physical and virtual network interfaces. 26; European standard(s) on essential cybersecurity requirements for operating systems. 27; European standard(s) on essential cybersecurity requirements for routers, modems intended for the connection to the internet, and switches. 31; European standard(s) on essential cybersecurity requirements for smart home general purpose virtual assistants. 32; European standard(s) on essential cybersecurity requirements for smart home products with security functionalities, including smart door locks, security cameras, baby monitoring systems and alarm systems. 33; European standard(s) on essential cybersecurity requirements for Internet connected toys covered by Directive 2009/48/EC that have social interactive features (e.g. speaking or filming) or that have location tracking features. 34; European standard(s) on essential cybersecurity requirements for personal wearable products to be worn or placed on a human body that have a health monitoring (such as tracking) purpose and to which Regulation (EU) 2017/745 or Regulation (EU) 2017/746 do not apply or personal wearable products that are intended for the use by and for children. Three work packages are therefore proposed to organize the required work during the duration of the project: Work Package 1 (WP-1) 1 “Project Management and Coordination” will be co-led by the CEN-CENELEC and ETSI and will consist in overall coordination, management, and reporting. This Work Package will also include the selection of the rapporteurs and experts among the applications received following an open call for expertise. Work Package 2 (WP-2) “Drafting Standardisation Deliverables” will be co-led by CEN-CENELEC and ETSI and will consist of the recruitment of Rapporteurs and Experts to draft, consolidate contributions and comments, and facilitate consensus to develop the European standard(s) on the different topics listed above. The ESOs joint Work Programme is currently being coordinated between CEN-CENELEC and ETSI relevant Technical Groups and will be finalized according to the deadline of Article 3 the Standardisation Request. The deliverable development work will comply with the ESOs internal Directives and involve cooperation between technical groups in the framework of the Cooperation Agreement between CEN-CENELEC and ETSI. For the sake of time, this collaboration will start in Mode 4 between relevant technical groups and could potentially continue in a Joint Technical Bodies operating under Mode 5. Finally, Work Package 3 (WP-3) will focus on stakeholder engagement and outreach. The main objective of this work package is to coordinate the project's dissemination efforts, complementing the work of the rapporteurs, who will divide their time between standard development and stakeholder engagement activities. WP-3 deliverables include webinars and open consultations. These dissemination activities will cover the CRA scope comprehensively and encourage a wider audience to participate in the development of harmonized standards in support of CRA. For each group of deliverables of WP-2, open consultations will be organized online within the working groups of the technical committee once the draft standards reach a sufficient level of maturity. In addition, a couple of webinars will be held online or at least in hybrid mode to ensure broad participation of stakeholders.

#§PRJ-OBJ-PO§# #@COM-PLE-CP@#

### 1.3 Complementarity with other actions and innovation

The project will consider and/or build upon various activities in different fields of cybersecurity and data protection, topics currently being developed by CEN-CLC/JTC 13 “Development of standards for cybersecurity and data protection”. This JTC has been dedicated to the development of work related mainly to, management systems, frameworks, methodologies, data protection and privacy, services and products evaluation standards suitable for security assessment for large companies and small and medium enterprises (SMEs), competence requirements for cybersecurity and data protection, security requirements, services, techniques and guidelines for ICT systems, services, networks and devices, including smart objects and distributed computing devices. CEN-CLC/JTC 13 is a strategic partner of the European Commission and other EU agencies and bodies as well as Member States national administration and bodies. It also cooperates with all the partners in standardisation field both from international (ISO, IEC, ITU) and European (ETSI) point of view, as well as other National Standardization Bodies relevant to JTC13 scope, on international level (e.g. NIST, JISC, SAC etc.). For the contributions related to industrial processes, the CLC/TC 65X ‘Industrial-process measurement, control and automation’ will draw on specialized knowledge to support the development of standards for industrial processes. CLC/TC 65X will continue to advance the "Security for Industrial Automation and Control Systems" standards in parallel with the IEC, with the goal of aligning these standards with the Cyber Resilience Act (CRA) and addressing any existing gaps. Through these efforts, CLC/TC 65X promotes consistent, cross-sector security standards, contributing to a more resilient and interoperable industrial ecosystem. The project will also leverage expertise in ETSI Technical Committee on Cybersecurity (TC CYBER), that will be the lead Technical Committee in ETSI for this project. ETSI TC CYBER acts as the centre of expertise in ETSI for Cyber Security and its standardisation activities cover: - Security of infrastructures, devices, services and protocols; - Advice, guidance and operational security requirements to users’ manufacturers and network and infrastructure operators; - Security tools and techniques; - Security mechanisms to protect privacy; - Security specifications and guidelines; - Quantum-safe cryptography. TC CYBER will liaise with other groups in ETSI, such as the Technical Committee on Electronic Signatures and Trust Infrastructures (TC ESI) on topics related to identity management systems, including authentication and access control readers, including biometric readers, and on public key infrastructure and digital certificate issuance software; as well as the Technical Committee on Secure Element Technologies (TC SET) on topics related to microprocessors and microcontrollers with security-related functionality, secure elements and smart cards. Finally, TC CYBER will liaise with 3GPP groups where relevant to provide the needed expertise and state of the art knowledge for vertical mobile communications services

#§COM-PLE-CP§# #§REL-EVA-RE§# #@QUA-LIT-QL@# #@CON-MET-CM@#

## 2. QUALITY

### 2.1 Concept and methodology

In coordination with the horizontal standards being developed by the CEN-CLC/JTC 13 the project’s main objective is to develop the first wave of vertical standards while at the same time ensuring enough dissemination and outreach activities are put in place to maximise stakeholder involvement beyond those participating in the working groups developing the deliverables. The draft standards will be produced in the context of responsible technical committees, following the deliverable elaboration principle of seeking consensus and within a fixed time schedule and with appropriate quality checks. The technical committees working on the different standards will meet and coordinate regularly to ensure the alignment and consistency of their deliverables. To involve stakeholders beyond the technical committee participation, rapporteurs will take a key role in dissemination activities. Rapporteurs are the best placed expert to take the lead in creation of dissemination material for online open consultations, webinars and deep-dive work sessions where interaction with stakeholders will take place. Results from this call are concrete proposals for harmonised standards specified in the lines defined in Table 1 of present EISMEA call considering that in some cases, this could include technical specifications or reports as well as data formats or roadmaps. On top of the ESOs usual editorial quality review of deliverables, the quality of the project’s deliverables will be ensured according to the best practices defined between the ESOs and the European Commission for Standardisation request deliverables, including the use of checklists, internal peer reviews, and independent assessments.

#§CON-MET-CM§# #@CON-SOR-CS@#

### 2.2 Consortium set-up

The coordinator of this topic will be ETSI and the role of CEN and CENELEC is defined as other Beneficiaries. The management, coordination and organization implementation of the project is performed by the 3 ESOs, within their area of responsibility, whereby the processing of the technical contents of the standards to be developed is the responsibility of the corresponding technical committees and working groups. Each of the work packages also conceives the development of core tasks key to the success of this project. These are allocated to the WP leaders and are surveyed by each WP coordinator, whose role primarily involves facilitating coordination and communication among various stakeholders, including ESOs governance bodies, relevant external organizations, National Standards Bodies (NSBs) or National Committees (NCs), secretariats, and working groups of relevant Technical Committees. This includes maintaining contact with the project's Commission liaison. WP 1 will provide administrative support such as document and meeting management, as well as financial oversight to ensure the project's agility and suitability. Coordinators are responsible for quality control of standards and standardization deliverables, adhering to established guidelines and checklists. It also involves monitoring all project activities, including those of rapporteurs, technical committees, and working groups, to ensure coherence and effective communication. Furthermore, Coordinators facilitate knowledge dissemination by updating participating Technical Committees on field developments, including relevant legislation, technical advancements, and best practices, ensuring that the involved technical committees are carrying their work in close cooperation with all relevant Technical Committees. Coordination work related to the horizontal standards will be supported by the existing project STAN4CR.

### 2.3 Project teams, staff and experts

| Project teams and staff |  |  |
| --- | --- | --- |
| Name and function | Organisation | Role/tasks/professional profile and expertise |
| Project Managers: Lucia Lanfri TBD | CENELEC CENELEC | - Coordination of the work of the Rapporteurs, involved Technical Committees (from CEN CENELEC and/or ETSI) and the European Commission; when necessary, - Arrange meetings as required in order to meet the target dates and deal with issues arising relating to the work programme, - Coordination, advice and guidance on standardization procedures and processes to all involved parties (e.g. subcontractors, experts, members and convenors), - Preparation, coordination and execution of the tenders in order to select the required subcontractors; preparation of contracts with subcontractors, - Planning, monitor and manage the financial budget of the project(s), - Preparation of progress, final and meeting reports, - Responding to external inquiries concerning the standardization activities/committees, - Monitor progress of the tasks and taking corrective actions, - Ensure information exchange with relevant CEN, CENELEC and ETSI technical committees, - Any other occurring tasks emerging from the work under contract (e.g. consensus-related issues). |
| Technical Officer Laure Pourcin | ETSI | - Act as prime ETSI Secretariat contact for the standardization activity in response to the SR CRA. - Supervise the operation of the standardization activity under the ETSI Directives and Technical Working Procedures, - Coordinate the CRA SR standardisation work with the ESOs Project Managers and the European Commission. Monitor progress of work programme. - Advise the group on the application of the relevant drafting rules, quality controls, stakeholders’ involvement, and common best practice. - Ensure that deliverables are fit for purpose, and in line with the relevant directives, drafting rules and quality recommendations, and accompany them through the drafting and publication phases. - Act as secretary where appropriate, provide official reports of the group’s meetings, highlighting actions and decisions. - Ensure that decisions, actions, approval of new work items and deliverables are properly recorded and communicated within the Secretariat. - Monitor activities of other relevant groups, both inside and outside of ETSI and advise of relevant activities as required. |
| Management Nooshin Amirifar | CENELEC | - Oversee coordination meetings - Liaising with relevant parties regarding deliverables, issues, delays, and advice on best practices. - Oversee the coordination and execution of the tenders in order to select the required subcontractors; preparation of contracts with subcontractors. |
| Financial project Manager Nicoleta Taran | CEN | - Coordinate activities to support or assist the project managers and the stakeholders in terms of administrative, operational, and technical services, - Support for procurement of the processes related to all calls for tender, - Support in the preparation, implementation, and follow-up of meetings as well as other events, related to the financial aspects, - Monitor deadlines and project dates, - Contribution to the technical and financial report. |

| Communications Project Manager TBD | CEN | - Contribution to the event organization and management. - Offer support in compiling all rapporteur work offered as dissemination material by providing an adequate format suitable to support the different dissemination events. |
| --- | --- | --- |
| Legal Project Manager | CEN | - Support in creation of contracts for Rapporteurs. |
| Editor - TBD | CENELEC | - Edition of Standards. |
| Project Manager -TBD | DKE | - Contribute to the coordination and execution of the tenders to select the required subcontractors related to the activities of the CLC/TC 65X. |

Other project participants will be nominated by the ESOs without cost to the project such as:

- Official representatives of CEN/CLC/ETSI technical groups (i.e. Chair, Vice Chairs, Convenors) and Secretaries/Technical Officers from the involved of CEN/CLC/ETSI technical groups.

They will be responsible for developing the standards.

- ETSI Funded Activities Team

  - Management of the project costs and funding

  - Responsible for the Reporting to ETSI Management and EC/EFTA.

  - Management of audit processes on Funded projects

  - Management of contractual aspects with the experts

  - Monitoring of the administrative and financial tasks of the projects

  - Validation of milestones and payments.

- ETSI EditHelp Team,

  - Perform the editorial quality review of Standards.

  - Manage the approval process.

  - Publish the standards.

Outside resources (subcontracting, seconded staff, etc)

This project proposes to incorporate at least 6 dedicated experts assigned as Project Leaders (Rapporteurs) to fulfil one or more functions associated with the project deliverables. Rapporteurs will play two important roles: - Act as project leaders and rapporteurs of the deliverables (link to WP-1) - Promote knowledge dissemination (link to WP-3) Typical tasks of Project Leaders (Rapporteurs) are leading and moderating iterative drafting sprints, collecting and integrating stakeholder feedback, organising calls among other rapporteurs as needed, drafting and editing text and addressing comments, liaising with each other under coordination of the Convenor of the working group, reporting to the Convenor and working group, contributing to stakeholder outreach and engagement, supporting the publication of mature drafts for open consultations and the production of material for webinars and deep-dive work sessions . The call for rapporteurs shall be launched by the WP-2 beneficiaries CEN-CENELEC & ETSI respectively and a selection panel will appoint the independent experts. These procedures will take place in line with the EU financial regulation, most likely a public call for tender will be launched in order to ensure a diverse participation and involvement of cybersecurity experts. Rapporteurs will be selected for work related to the vertical standards as per specified in this EISMEA call. The work carried out by these Rapporteurs will be done in close coordination with the developments on the horizontal standards related to “General Design”, “Vulnerability handling” and “Security and Control”. The work on horizontal standards to respond to the standardisation request will take place within CEN-CLC/JTC 13 WG-9 and is covered by a separate Action Grant STAN4CR. The ESOs will implement their respective purchasing processes to recruit at least 3 rapporteurs in CEN CENELEC and at least 3 rapporteurs and one Project Manager in ETSI. CEN/CENELEC Procurement A call for proposal/tender is an essential part of any formal procurement plan aiming at obtaining the best value for money. Due consideration must be given to the manner in which the call is released, how to effectively describe the service/good CENELEC is requesting (with a clearly defined aim), and by which criteria CENELEC will judge timely, eligible bids. All acquisitions of goods/services for CENELEC shall comply with the following processes, according to the below-described expenditure limits. The following thresholds will be applicable: Up to €1.000: Any expenditure for goods/services up to €1.000 may be purchased as payment against invoices without prior acceptance of a tender Between €1.001 and €15.000: Any expenditure for goods/services up to €15.000, no formal call for tenders is required, only a consultation of one offer is required. Between €15.001 and €60.000: Any expenditure for goods/services between €15.001 and €60.000 shall require requesting at least 3 (three) (if so many available) offers from possible vendors or consultants. Proper documentation and adherence to all the principles of procurement herein apply. A selection report will be issued to identify the bids received, the selection criteria/methodology applied, and the bid selected. Over €60.000: Any expenditure for goods/services for over €60.000 shall require an open call for tender to be published on CEN-CENELEC website for a duration of at least 35 calendar days. Eligible timeframe - bids received before or after the procurement process due date are not eligible and will not be taken into consideration for evaluation process. Artificial Limit Compliance - These above expenditure limits are meant to ensure the proper use of procurement processes to obtain the best and most cost-effective service/good. Artificial splitting of contracts or projects in order to avoid the implications of another procurement process category is strictly prohibited. Selection shall be made in a neutral and transparent manner and in accordance with the criteria pre-determined in the initiation phase or as per the call for tenders. Cost-effectiveness and quality shall figure heavily in any weighted selection process. From €15.001, the selection process should be performed through an Evaluation Committee who will ensure that the selection process is performed in compliance with the principles of the Treaty on the Functioning of the European Union (TFEU), such as equal treatment, non-discrimination, proportionality, and transparency. Ethics and Sustainability and will issue a motivated decision on the selection process of a supplier/subcontractor. Rapporteurs are to be reimbursed from the corresponding budget within their WP in order to cover the travel and accommodation expenses incurred for traveling to dissemination events organised within of WP-3. ETSI Procurement According to ETSI Technical working procedure on the selection of the service providers, ETSI will issue a call for expertise to get the necessary skills and resources as described below. The ETSI Staff will be integrated to guarantee the proper support and management. The selection panel will comprise ETSI Secretariat (Director of Funded Activities, ETSI Technical Officers), and the Officials of the involved technical groups (i.e. ETSI TC CYBER, TC ESI, TC SET). They will review the potential candidates and select those who best meet the workplan, including the assignment of the project leader. The review of the applicant will be based on multiple criteria such as technical competencies, skills, working experience, proposed contribution to tasks & related costs, the explanation of the parts of the tasks and the scope that the service provider will cover, the way to achieve the objectives in this Project and proposed approach/methodology for the execution of the tasks, the approach to the management of the quality, the approach to the management of the risks and their mitigation, the implementation schedule, etc. ETSI Secretariat will ensure during implementation that there is no duplication of efforts with any other EU Grant, in particular CYBERSTAND.eu, thus avoiding any issue with double funding. A Project Manager will be appointed from one of the Service Providers. The Project Manager will possess: - project management experience, - report-writing skills, - knowledge of the EU cybersecurity standardisation ecosystem, - experience of consensus building, - presentations skills, - experience of working in an international environment, - experience in liaising with other international organisations. Using the ETSI-defined call for expertise and contractor selection process outlined above, the selected experts will begin the project with the preparatory meeting at the end of the second month of the project (M2).

### 2.4 Consortium management and decision-making

The figure below provides an overview over the relevant committees and stakeholder of this proposal. ETSI is the coordinator of the proposal and the contact point for the European Commission. CEN & CENELEC will be co-beneficiaries. The 3 ESOs will oversee the coordination and management of this project, framing related deliverables under work package 1 (WP-1) “Project Management and Coordination”. WP-1 will lead and oversee the work streams dedicated to the development of different vertical standards deliverables (WP-2) and WP-3 dedicated to the corresponding project dissemination and stakeholder engagement. Each of these work packages focuses on its respective deliverables, with ETSI Secretariat and CCMC ensuring effective coordination to avoid duplication or undesired overlap. A ESOs CRA coordination group will be established to guide this initiative. This group will include convenors or members of the Technical Committees, involved, and will operate under WP-1, and will not request funding and will assist WP-1 in coordinating and aligning activities. All activities carried out within an established Technical Committee adhere to the governance and regulations of their individual working groups, where the secretary and convenor serve as the primary points of contact for CEN-CENELEC & ETSI. At the same time, the execution of tasks within the work packages, completed by rapporteurs, will be supervised by WP-1. Besides the work on standards, all Rapporteurs will produce a progress report and dissemination material which will serve as basis for the stakeholder involvement and outreach activities organised by WP-3. WP-1 will oversee the progress of the rapporteurs and collecting, curating, and editing the dissemination material, establishing liaison with WP-3 in order to coordinate efforts for the outreach events for stakeholder involvement.

#§CON-SOR-CS§# #@PRJ-MGT-PM@#

### 2.5 Project management, quality assurance and monitoring and evaluation strategy

In line with the ESO’s Quality Management System (QMS), the project will follow internal procedures to approve and manage progress. The deliverables will be developed according to the ESO’s projects timeline and deadlines. For the monitoring of the project, recurrent project team meetings are planned to follow the development of the projects and monthly coordination meetings are foreseen. An overall project plan including relevant milestones will be prepared including all standardization deliverables in scope. The target dates for the publication of the deliverables are documented in the ESOs work programme database and are continuously updated during the development. The overall project plan and timeline will be the responsibility of the WP1 Project Manager and be monitored by the WP 2 and 3 coordinators. They will review the key milestones defined in the project plan, consider the workload of the experts according to the active projects and their availability by keeping the overall workload of the working group in mind, circulate working drafts to be commented, oversee that schedules working group meetings regularly, ensures continuous exchange with the rapporteurs and technical committees secretariat/experts, fulfil key responsibilities, continuously report to the TC secretariat about the status and anticipated potential problems. This should ensure that sufficient analysis has been performed, financial and human resources are secured, and necessary information is provided at various stages of the project using specific templates and approval processes. In case of change during the project impacting scope, resources or timeline, a change request will be submitted officially to ESO leading the project. The ESOs CRA coordination group will evaluate the progress of the project by compiling the following data: Evaluation Method - Regular Reporting: Establishing a routine (e.g., quarterly) reporting system where each work package leader provides updates on progress, challenges, and next steps. This should include both quantitative data and qualitative insights. - Stakeholder Feedback: This corresponds to the follow up actions related to the WG webinars and deep-dive work sessions (WP-3) and consists of implementing a structured feedback system where stakeholders can provide their insights and satisfaction levels with the project's outputs and engagement efforts (for instance, via quick surveys). - Performance Reviews: Conduct semi-annual reviews against the project objectives and milestones. Use these sessions to adjust strategies and redistribute resources if necessary. Indicators Quantitative Indicators - Deliverables Completion Rate: Track the percentage of deliverables completed versus planned in each work package (WG dissemination, enquiry, formal vote). This helps in assessing productivity and adherence to timelines. - Stakeholder Participation Numbers: Measure the number of stakeholders participating in the WG open consultations, webinars, and deep-dive work sessions (WP-3). - Budget Adherence: Monitor the expenditure against the budget allocated for each work package to manage financial resources effectively. Qualitative Indicators - Quality of Standards: Assess the quality of the standards based on feedback from technical experts and end-users (EC and HAS assessment). - Innovativeness of Solutions: Evaluate how innovative solutions have been incorporated throughout the project. Self-assessment. - Team Collaboration Quality: Qualitatively evaluate how effectively the project teams across different work packages collaborated and shared knowledge. Evaluation by the ESOs CRA coordination group.

#§PRJ-MGT-PM§# #@FIN-MGT-FM@#

### 2.6 Cost effectiveness and financial management

ETSI is the coordinator of the proposal and the contact point for the European Commission. CEN & CENELEC will be co-beneficiaries. Each beneficiary will manage technical, contractual, and financial aspects of the project with the EC/EISMEA and EFTA. First, the cost effectiveness of the project will be ensured by the different control mechanisms set through the different entities of the project, covering in particular the following aspects: - Control over resourcing and financial aspects - Control over the technical aspects and issues Secondly, the project will be supported by an experienced team ensuring the best value for money. As far as the financial or resourcing aspects are concerned and as long as the scope of the project does not extend outside the one described in this document, the final delivery will be secured. Internal staff The time worked on this project by CEN & CENELEC and ETSI staff paid by the project will be recorded in our time recording system within a specific code allowing precise identification of the number of hours worked on this project. The time worked and related costs for this project will be considered by the CEN-CENELEC and ETSI Finance Department to avoid overlapping with other existing funding agreements such as the Operating Grant, related Action Grants such as STAN4CR and CYBERSTAND.eu, or any other EC/EFTA funded project. For the allocation of the financial resources by the affiliated entity DKE, a preliminary assessment has been carried out to estimate duties to be performed and their respective cost. An estimation of the time spent in relationship to the complexity of each task has also been performed to assess the consistency. For this, experience and knowledge gained in the coordination and management of complex standardization projects have been considered. Time spent will have to be recorded in Timesheets and all costs related to their outside resources will have to be justifiable. Subcontractors Nonetheless, the work programme requires additional expertise/support via subcontractors that will be handled by CEN, CENELEC and ETSI. For these, the budget was determined based on the project complexity, expert evaluation from the working group and experience from former standardization projects with similar analytical processes. Cost-effectiveness is a key factor of the procurement process. The management of the financial resources is allocated to the consortium member that is responsible for the respective tasks. A comparison is made on a regular basis to determine whether the resources used correspond to the progress of the project. To avoid the risk of subordinate relationship under French labour law that could trigger negative consequences for ETSI, on advice of its lawyers, ETSI has abandoned the principle of a daily rate to contract its experts and ETSI works now under the principle of service contracts. The contractor is bound by delivering the agreed service for the price determined. It is the responsibility of the service provider to make available the necessary experts to deliver the expected service. Each subcontractor is allocated to specific tasks with an expected level of contribution. The financial resources allocated to the subcontractor are calculated on this principle. At the start of the project, ETSI develops a baseline cost plan, calculated with the cost of the tasks and the scheduled progress of task at each milestone cut-off date. This baseline cost plan provides the costs at each milestone cut-off date. The milestone payment schedule for each subcontractor is then calculated considering the baseline cost plan and the expected level of contribution. The milestone payment schedule is contractual. The subcontractors’ payments are submitted to the validation of the project milestones by ETSI. Travels are strongly reduced, as teleconferences will be the most common tool for organising technical meetings. Travels are accounted to allow for face-to-face participation in the ETSI, CEN and CENELEC Technical Groups and for coordination. ETSI, CEN and CENELEC warrant that neither the project as a whole nor any part of it have benefited from any other EU Grant thus avoiding any trouble with double funding.

#§FIN-MGT-FM§# #@RSK-MGT-RM@#

### 2.7 Risk management

| Risk No | Description | Work package No | Proposed risk-mitigation measures |
| --- | --- | --- | --- |
| 1 | Low: Personnel change at ETSI | 1 | ETSI sees few changes in its personnel already mitigated by sharing expertise and knowledge in ETSI Secretariat, enabling other colleagues to step in to maintain the ETSI work. |
| 2 | Medium: Lack of consensus in the project team on certain decisions | 1 | Most of the project team members hired in the project should have the right experience of open collaboration in previous projects. A ESOs CRA coordination group will be established to guide this initiative, in Chairs and convenors of the Technical Committees, involved, and will escalate to the ESOs governance bodies any blocking issue. |
| 3 | Low: Any remaining uncertainties related to the leads to technical descriptions could lead to misalignments in the developed content of the standards | 2 | Frequent exchanges are held with the EC to get information about specific technical content of the CRA and its link to the policy objectives, based for instance on lessons learned during the drafting of the CRA, impact assessments and stakeholder consultations. |
| 4 | Medium: The adequate rapporteurs are not found due to general lack of experts in the cybersecurity area. | 2 | The call for tender for the project subcontractors is timely prepared and widely disseminated. |
| 5 | High: The development of the different deliverables is delayed due to challenging timelines being under the average timeframes for standard development. | 2 | Establish periodic control meetings to monitor progress, track milestones, allocate resources effectively, and ensure timely communication and coordination. |
| 6 | Medium: lack of engagement from the subcontracted experts | 2 | Establish clear communication channels, set expectations and deliverables upfront, conduct regular check-ins, and implement performance monitoring to ensure engagement from subcontracted experts. |
| 7 | High: After deeper analysis, the development of certain deliverables is not encouraged/supported by the interested stakeholders | 2 | Establish early identification mechanisms and report immediate to the EC. Allow for flexibility in scope of work and task allocation among the beneficiaries to adapt to unforeseen changes. |
| 8 | Medium: Low stakeholders participation number | 3 | Refinement of the stakeholder engagement strategy and outreach plan, leveraging partners. Promote the open consultations, webinars and deep-dive work sessions via industry associations (e.g. ECSO) and EU agencies (e.g. ENISA) as well as national cybersecurity agencies. |

#§RSK-MGT-RM§# #§QUA-LIT-QL§# #@IMP-ACT-IA@#

## 3. IMPACT

### 3.1 Impact and ambition

Short-term effects of this project are expected to be reflected in the immediate increase in the efficiency and productivity of the technical committees and working groups involved in producing standards for the CRA. This would result in quicker progress on deliverables and better coordination among team members. Medium-term effects include the establishment of streamlined processes and improved communication channels within the committees and working groups. As a result, there would be a more cohesive approach to addressing the various workstreams outlined in the project's deliverables, leading to more comprehensive and higher-quality standards being developed. In the long term, the project could lead to the establishment of a sustainable framework for standards development in support of the CRA. This might include the development of best practices, capacity-building initiatives, and long-term strategies for ongoing collaboration and coordination among stakeholders. Ultimately, the long-term goal would be to ensure the continued effectiveness and relevance of the standards produced. Timely establishment of the standards stands to advantage various industries, policymakers, and society. It lays a robust groundwork for seamlessly incorporating European cutting-edge standards into the daily usage of numerous digital products. Additionally, creating standards to bolster the Cyber Resilience Act (CRA) will fortify and enhance the competitiveness of the EU Single Market. This will be achieved through bolstering cybersecurity measures, encouraging innovation, and nurturing trust among both consumers and businesses.

#§IMP-ACT-IA§# #@COM-DIS-VIS-CDV@#

### 3.2 Communication, dissemination and visibility

As above specified, two important pillars are foreseen for dissemination activities: One is carried out by the rapporteurs within WP-2, developing dissemination material alongside the production of the corresponding deliverables. The other pillar is carried out within WP-3 which focuses on the organisation of events, such as webinars or deep dive sessions. Because these two pillars are closely related and are highly interdependent; WP-1 will play an important role as coordinator, overseeing the activities done by the rapporteurs, ensuring timely delivery of the dissemination material, and coordinating efforts with WP-3. Moreover, the whole project is in close cooperation with the European Commission and directly related to the CRA SReq. Relevant documents will be shared via email and a centralized collaboration platform. The results will be promoted on different channels such as on NC’s webpages, CEN-CENELEC and ETSI’s webpages and open working areas, but it will be also part of exchanges with important partner countries, if applicable and necessary. The support of the European commission and EFTA will be always visible such as promoting the European commission and EFTA’s logo on reports, presentations and mentioning in presentations. The European commission and EFTA representatives are always welcomed to participate in the meetings and give their input. For the WP-2 when the draft standards are reaching a sufficient level of maturity a webinar will be organized with the aim to reach a broader audience. Consortia, SME associations, Digital Innovative Hubs, Market Surveillance Authorities, Annex III organisations, EU related Cyber projects and Universities will be invited to interact with WG experts and Rapporteurs. As above mentioned, the communication and dissemination activities aim to promote the project's activities/results and maximize their impact. These efforts target specific groups including stakeholders, policymakers, and the public. The dissemination strategy is built around two main pillars: Dissemination by Rapporteurs (WP-2): The rapporteurs will develop dissemination materials alongside the production of the corresponding deliverables. This will include user-friendly formats such as summaries, discussion papers, and presentations to ensure the information is accessible to a broad audience. Organization of Events (WP-3): This includes organizing webinars, deep dive sessions, and webinars to engage stakeholders actively. These events will provide platforms for interactive discussions and feedback, enhancing the project's visibility and impact. Coordination and Oversight: WP-1 will play a crucial role as the coordinator, overseeing the activities performed by the rapporteurs and ensuring the timely delivery of dissemination materials. Coordination efforts with the leaders of WP-4 will be critical to maintain consistency and coherence in dissemination activities. Engagement with the European Commission: The entire project will be closely coordinated with the European Commission and directly aligned with the CRA SReq. Communication will be facilitated through National Committees (NCs) and CEN-CENELEC and the NSBG and NSOG of ETSI Relevant documents will be shared per correspondence. Results will be promoted on various channels including NC’s webpages, CEN-CENELEC’s webpage, ETSI webpages and open working area and as part of exchanges with key partner countries, if applicable and necessary. Ensuring Visibility of EU Funding: The support of the European Commission and EFTA will be prominently displayed, including the use of the European Commission and EFTA’s logo on reports, presentations, and other dissemination materials. Mentions of the European Commission and EFTA’s support will be included in presentations and other public communications. Representatives from the European Commission will be invited to participate in meetings and provide their input, ensuring their involvement is visible and recognized. By leveraging these strategies, we aim to ensure comprehensive communication and dissemination of the project's outcomes, maximizing visibility and impact across all relevant audiences.

#§COM-DIS-VIS-CDV§# #@SUS-CON-SC@#

### 3.3 Sustainability and continuation

In the post-funding phase, it will be of importance to maintain the infrastructure established during the project, such as working groups under the diverse TC, communication channels, coordination mechanisms, and capacity-building initiatives. The creation of guidelines together with dissemination activities like webinars and deep-dive work sessions are key to ensure expertise transfer to the relevant stakeholders. Promotion, dissemination, and utilization of the standards developed under this project will increase the impact and sustainability of the project in the long term.

#§SUS-CON-SC§#

#@WRK-PLA-WP@#

## 4. WORKPLAN, WORK PACKAGES, ACTIVITIES, RESOURCES AND TIMING

### 4.1 Work plan

Work plan

The project is structured in six different work packages (WP) running in parallel throughout the project period: - WP 1: CEN CENELEC ETSI Project management and coordination. Under this Work Package, CEN CENELEC and ETSI will oversee of monitoring the overall project and production of deliverables, maintaining regular coordination meetings with the ESOs CRA coordination group and act as a main communication channel with the European Commission. This Work Package will also support the dissemination and stakeholder engagement activities carried out by WP-3 by compiling the dissemination material produced by the rapporteurs so that can be used as a baseline for the stakeholder engagement activities. This work package is also dedicated to providing with the support needed from editors, legal and financial aspects. - WP 2: Vertical standards development. Dedicated to the drafting standards according to Table 1 of this document. - WP 3: Stakeholder engagement and outreach, related to the engagement strategy and delivery of webinars and deep-dive work sessions.

### 4.2 Work packages, activities, resources and timing

WORK PACKAGES

### Work Package 1

| Work Package 1: Project management and coordination |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  | M0 – M15 | Lead Beneficiary: |  | ETSI |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |
| - Overall, this task ensures the successful implementation of the project by systematically mapping its trajectory, effectively subcontracting actions, and maintaining transparent communication reports. - The project management team will work cohesively to ensure that the project progresses seamlessly, meeting its objectives within the defined parameters. |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name |  |  | Description |  | Participants |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |
| T1.1 | Overall project management |  |  | This task covers the project management for the overall project. It includes (M1-M15): - mapping of the project and its progress, - identify potential risks and establish mitigation strategies, - identify suitable subcontractors through a rigorous selection process, - coordination and consolidation of interim and final reports, - overall coordination of WP-2 and 3, - constitution of a rapporteur selection panel and the ESO CRA coordination group. - monitoring subcontractor performance to ensure adherence to project timelines and quality standards. |  | ETSI CENELEC CEN | COO BEN BEN | No |
| T1.2 | Legal and Financial management |  |  | This task covers the subcontracting process: - setting up a subcontracting process. - management of subcontracts (rapporteurs): - elaboration of relevant financial documents. - offer support during the preparation of the call for tender. - offer support during the evaluation of applications (formal correctness, drafting selection reports). - facilitate the negotiation and establishment of subcontracting agreements. |  | ETSI CENELEC CEN | COO BEN BEN | No |
| T1.3 | Selection of the Rapporteurs |  |  | This task is dedicated to overseeing a strict process of selection of the rapporteur and development of criteria to ensure that the selected experts shall: - meet the criteria of neutrality and respect for EU values and principles, - are in possession of strong academic credentials and relevant expertise in the cybersecurity domain allowing them to carry out their tasks, - are in familiarity with the New Legislative Framework and procedures of the European Standardisation Organisation. |  | ETSI CENELEC CEN DKE | COO BEN BEN AE | No |

| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description | Due Date (month number) | Means of Verification |
| MS1 | Subcontracting procurement process | 1 | ETSI CENELEC | A process for the subcontracting is described: - Selection criteria is specified - Call for tender is launched - Selection procedure is followed - Documentation is prepared for signature of the subcontract | M2 | Signed subcontracts |
| MS2 | Delivery of the EISMEA progress Report | 1 | ETSI | - the activities performed until month 12 - the latest drafts of the deliverables available - the plan for the future activities to complete the deliverables - Standard EISMEA reporting (English) | M13 | Submission of the report on the EISMEA portal |
| MS3 | Delivery of the EISMEA final report | 1 | ETSI | - The activities performed for the whole duration of the project - Achieved results and Key Performance Indicators (KPIs) - Financial report | M15 | Submission of the report on the EISMEA portal |

| Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type | Dissemination Level | Due Date (month number) | Description (including format and language) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1.1 | Annual Report | 1 | ETSI | R — Document, report | SEN — Sensitive | M13 | PDF, English Overall progress report of the project status including description of issues encountered and actions taken to mitigate. |
| D1.2 | Final Report | 1 | ETSI | R — Document, report | SEN — Sensitive | M15 | PDF, English Report including comprehensive analysis of how the project's objectives have been met, including a review of key performance indicators (KPIs). |

Any background information held or owned by the ESOs and deemed necessary to implement the action or exploit any results produced under said action shall not be shared or reproduced or used in any form or by any means without the written permission of the ESOs. Background information subject to third party intellectual property rights may only be shared, reproduced, or used to the extent authorised by law and subject to prior written permission of the rightsholder(s).

### Work Package 2

| Work Package 2: Vertical standards development |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  | M0 – M15 | Lead Beneficiary: |  | ETSI |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |
| - Development of vertical standards in alignment with the horizontal work carried out at the WG9. This work package aims to cover all lines specified in the above Table 1. |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name |  |  | Description |  | Participants |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  | Name | Role (COO, BEN, AE, AP, OTHER) |  |
| T2.1 | Vertical rapporteurs’ Project Management |  |  | This task covers the activities related to the management of the rapporteurs. It includes (M1-M15): - Allocation of selected rapporteurs to the identified working group within CEN, CENELEC and/or ETSI, - Induction of the rapporteurs to their tasks, - Overseeing monthly reporting of rapporteurs to the convenor or chair of the relevant technical groups. Overseeing rapporteur readiness and availability to contribute to activities related to WP-3, - Coordinate with the corresponding secretariat and convenor in order to ensure a coherent approach is adopted between horizontal and vertical standards. - Support communication between experts, CEN, CENELEC and/or ETSI secretariat and the Commission Services. |  | ETSI CEN CENELEC | COO BEN BEN | Yes (subcontracting) No No |
| T2.2 | Contribution of vertical Rapporteurs |  |  | This task covers the work done by the rapporteurs, acting as project leaders to advance the efforts towards the development of the vertical standards, leading and moderating iterative drafting sprints: - collecting and integrating stakeholder feedback, - drafting and editing text and addressing comments, - liaising with each other under coordination of the Convenor or chair of the relevant technical groups, - reporting to the coordinating Convenor and working group. - contributing to stakeholder outreach and engagement and open consultations (link to WP-3). |  | Rapporteur (subcontractor) | SUB | Yes, subcontracting |
| T2.3 | Edition of standards |  |  | This task includes review and edition of standards after approval by the WG convenor. |  | ETSI CENELEC | COO BEN | No |

| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Milestone No (continuous numbering not linked to WP) | Milestone Name | Work Package No | Lead Beneficiary | Description |  | Due Date (month number) | Means of Verification |
| MS1 | Project leaders (Rapporteurs) are assigned to the working group | 2 | ETSI CENELEC | The first meetings take place where project leaders (rapporteurs) are assigned to the corresponding groups. |  | M2 | Meeting reports and attendance list. |
| MS2 | Mature draft sent to HAS consultants | 2 | ETSI CENELEC | The first working draft is dispatched to internal quality control and HAS consultant. |  | M6 | HAS consultant acknowledgement of receipt |
| MS3 | Where applicable, a draft of the standards for enquiry/final draft | 2 | ETSI CENELEC | This milestone is achieved when a draft is ready for submission to enquiry. |  | M9 | Submitted document drafts |
| Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type | Dissemination Level | Due Date (month number) | Description (including format and language) |
| D2.1 | Proposal for standards covering lines -16-34 of the draft Stand. Req. (see 1.2). | 2 | ETSI CENELEC | R — Document, report | SEN — Sensitive | M15 | Draft standards covering essential requirements listed in 1.2. - PDF, English |

Any background information held or owned by the ESOs and deemed necessary to implement the action or exploit any results produced under said action shall not be shared or reproduced or used in any form or by any means without the written permission of the ESOs. Background information subject to third party intellectual property rights may only be shared, reproduced, or used to the extent authorised by law and subject to prior written permission of the rightsholder(s).

### Work Package 3

| Work Package 3: Stakeholder engagement and outreach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Duration: |  |  | M0 – M15 |  | Lead Beneficiary: |  |  |  | ETSI |  |  |  |  |  |
| Objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The primary goal of this work package is to execute activities centred around stakeholder engagement strategy including online open consultations, webinars, and deep-dive work sessions delivery. These efforts aim to disseminate preliminary outcomes of our standardization activities to gather feedback, which will inform in-depth work sessions. This involves orchestrating discussions and gathering input from external stakeholders, organizing their contributions in a structured manner for the working group responsible for drafting the respective deliverable. All tasks within Work Package 3 are closely coordinated with the relevant rapporteurs and working groups. The ESOs supervise financial management and provides general oversight throughout the process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities and division of work (WP description) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task No (continuous numbering linked to WP) | Task Name |  |  |  |  | Description |  |  |  | Participants |  |  |  | In-kind Contributions and Subcontracting (Yes/No and which) |
|  |  |  |  |  |  |  |  |  |  | Name |  | Role (COO, BEN, AE, AP, OTHER) |  |  |
| T3.1 | Coordination of Rapporteurs contributions |  |  |  |  | This task includes the involvement of a CEN, CENELEC and/or ETSI project manager to liaise the rapporteurs to prepare the dissemination material for the online open consultations and events. These tasks include: - ensuring coherence of the content of the dissemination material. - advice on timelines and alignment between the different events. |  |  |  | ETSI CEN CENELEC |  | COO BEN BEN |  | Yes, subcontracting No No |
| T3.2 | Development of the stakeholder engagement strategy |  |  |  |  | These tasks include the development on a stakeholder outreach plan including the following activities: - develop a roadmap outlining the timelines and content of the open consultations and stakeholder outreach between M1 and M15. - propose a collaboration plan to coordinate dissemination activities with WP-1 and project leaders (Rapporteurs). - propose methodology to gather structured feedback to rapporteurs. |  |  |  | ETSI CEN CENELEC Rapporteurs |  | COO BEN BEN SUB |  | Yes, Subcontracting |
| T3.3 | Organisation of dissemination activities for stakeholder engagement and outreach |  |  |  |  | These tasks include the organisation of dissemination activities such as: - organisation of webinars to introduce external stakeholders to the preliminary outcomes of standardisation activities. - set up of a web page for displaying drafts available for open consultations. - organisation of deep-dive work sessions, following the feedback obtained through dissemination activities, to collect input in a structured manner. |  |  |  | ETSI CEN CENELEC Rapporteurs |  | COO BEN BEN SUB |  | Yes, Subcontracting (Partly) No No Yes, Subcontracting |
| Milestones and deliverables (outputs/outcomes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone No (continuous numbering not linked to WP) |  | Milestone Name |  | Work Package No |  |  | Lead Beneficiary | Description |  |  | Due Date (month number) |  | Means of Verification |  |
| MS1 |  | Open consultations take place |  | 3 |  |  | ETSI CENELEC | The working drafts are available for open consultation and comments. |  |  | M5 |  | Draft is available for review. |  |

| Deliverable No (continuous numbering linked to WP) | Deliverable Name | Work Package No | Lead Beneficiary | Type | Dissemination Level | Due Date (month number) | Description (including format and language) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D3.1 | Roadmap detailing the dissemination activities for stakeholder engagement | 3 | ETSI CENELEC | R — Document, report | SEN — Sensitive | M3 | PDF, English Report roadmap |
| D3.2 | Open area for consultation | 3 | ETSI CENELEC | R — Document, report | SEN — Sensitive | M5 | Platform such as a webpage or website |
| D3.3 | Report on stakeholder engagement and outreach | 3 | ETSI CENELEC | R- Document report | SEN – Sensitive | M15 | Report of all dissemination activities |

Any background information held or owned by the ESOs and deemed necessary to implement the action or exploit any results produced under said action shall not be shared or reproduced or used in any form or by any means without the written permission of the ESOs. Background information subject to third party intellectual property rights may only be shared, reproduced, or used to the extent authorised by law and subject to prior written permission of the rightsholder(s).

Estimated budget — Resources

See detailed budget table/calculator* (annex 1 to Part B).

*Note: Indirect Costs are only applicable to the Affiliated Entities as the three ESOs are covered by Operational Grants for these purposes. This being, the rate applied to the overall estimated Direct Costs is not the 7% flat rate, but rather approx. 0.04%. Further details can be found on the Detailed Budget Table (Annex 1 to Part B)

### Subcontracting

| Subcontracting |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Work Package No | Subcontract No (continuous numbering linked to WP) | Subcontract Name (subcontracted action tasks) | Description (including task number and BEN/AE to which it is linked) | Estimated Costs (EUR) | Justification (why is subcontracting necessary?) | Best-Value-for-Money (how do you intend to ensure it?) |
| 2 | S2.1 | Project Manager Task 2.1 | ETSI – Project Manager, for overall work programme coordination | Estimation: 215 days at 600 € for 1 project manager 128 500 € | Subcontracting is necessary to cope with the coordination and management workload of this project. | Subcontractors are selected on a case-by-case basis in the context of an open call through a clearly defined process (typically one or more of the following, publication of the call through ETSI Collective letters (see section 2.3 above) to the membership, Technical Body mailing lists or explicit calls for tender). Travel costs are included in the subcontracting cost. |
| 2 | S2.2 | Rapporteurs Task 2.2 | CENELEC – Rapporteurs, acting as project leaders to advance the efforts towards the development of the vertical standards, leading and moderating iterative drafting sprints: | Estimation: 650 days at 1000€* for 3 rapporteurs 650.000€ | Subcontracting is necessary to recruit the right cybersecurity experts and ensure that the deliverables are ready on time. | Public call for tender, ensuring strict processes described in section 2.3 are met and ensuring they meet the criteria of neutrality and respect for EU values and principles, are in possession of strong academic credentials and relevant expertise in the cybersecurity domain allowing them to carry out their tasks, and are in familiarity with the New Legislative Framework and procedures of the European Standardisation Organisation. |

| 2 | S2.3 | Rapporteurs Task 2.2 | ETSI - Rapporteurs, to advance the efforts towards the development of the vertical standards, leading and moderating iterative drafting sprints: | Estimation: 650 days at 1000€* for 3 rapporteurs 650.000€ | Expertise is not available in ETSI Secretariat or from voluntary members. Subcontracting is necessary to recruit the right cybersecurity experts and ensure that the deliverables are ready on time | Subcontractors are selected on a case-by-case basis in the context of an open call through a clearly defined process (typically one or more of the following, publication of the call through ETSI Collective letters (see section 2.3 above) to the membership, Technical Body mailing lists or explicit calls for tender), ensuring they are in possession of the relevant expertise in the cybersecurity domain. Travel costs are included in the subcontracting costs. |
| --- | --- | --- | --- | --- | --- | --- |

* This rate was established based of the offers received during the Call for Experts for the STAND4CR project and is better aligned with current market conditions.
Timetable

| Timetable (projects up to 2 years) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTIVITY | MONTHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12 | M 13 | M 14 | M 15 |
| Task 1.1 - Overall project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 1.2 - Legal and Financial management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 1.3 - Selection of the Rapporteurs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2.1 - Vertical rapporteurs’ management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2.2 - Contribution of vertical Rapporteurs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2.3 - Edition of standards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.1 - Coordination of Rapporteurs contributions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.2 - Development of the stakeholder engagement strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3.3 - Organisation of dissemination activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

#§WRK-PLA-WP§#

#@ETH-ICS-EI@#

## 5. OTHER

### 5.1 Ethics

Ethics

Not applicable.

#§ETH-ICS-EI§# #@SEC-URI-SU@#

### 5.2 Security

Security

Not applicable.

#§SEC-URI-SU§# #@DEC-LAR-DL@#

## 6. DECLARATIONS

| Double funding |  |
| --- | --- |
| Information concerning other EU grants for this project Please note that there is a strict prohibition of double funding from the EU budget (except under EU Synergies actions). | YES/NO |
| We confirm that to our best knowledge neither the project as a whole nor any parts of it have benefitted from any other EU grant (including EU funding managed by authorities in EU Member States or other funding bodies, e.g. EU Regional Funds, EU Agricultural Funds, etc). If NO, explain and provide details. | YES |
| We confirm that to our best knowledge neither the project as a whole nor any parts of it are (nor will be) submitted for any other EU grant (including EU funding managed by authorities in EU Member States or other funding bodies, e.g. EU Regional Funds, EU Agricultural Funds, etc). If NO, explain and provide details. | YES |

Financial support to third parties (if applicable) If in your project the maximum amount per third party will be more than the threshold amount set in the Call document, justify and explain why the higher amount is necessary in order to fulfil your project’s objectives.

N/A

#§DEC-LAR-DL§#

Annex I	Response to the Request for Proposals
CfE – STF 701 (REFERENCE BODY TC CYBER)
Deadline: 31 March 2025

If you are an ETSI Member *

ETSI membership status (Indicate your status):

 Full

 Associate

 Observer

If you are not an ETSI Member *

Please indicate:

Full name of the ETSI member supporting the application (list of ETSI members on etsi.org):

-________________________

Official contact name of the ETSI member supporting the application:

-________________________

Note: A formal confirmation of the support from the Official contact is required (e.g. by e-mail sent to STFLINK@etsi.org) and an “ETSI Member Support Letter” will be required if you are selected.

| Contractor information * |  |  |  |
| --- | --- | --- | --- |
| Contractor name *: Indicate the Company/Organization Name |  |  |  |
| Contact person for the technical aspects |  | Contact person for Decision on ETSI financial offer to this project (if any) |  |
| Title |  | Title |  |
| First name |  | First name |  |
| Last name |  | Last name |  |
| Role |  | Role |  |
| e-mail |  | e-mail |  |
| Phone |  | Phone |  |

|  | Yes | No |
| --- | --- | --- |
| Do you or any employee of your Company/Organization hold an elected or appointed position in the Reference Body requesting the STF? | o Indicate in which position: ----------------------------------- | o |
| If you are self-employed candidate: Do you currently have other contracts in progress with ETSI? | o | o |

All fields marked with an asterix (*) are mandatory

1.1	Introduction

A short presentation of the technical structure responsible for this activity, e.g.:

- Business area, number of employees, link to WEB site,

- Department(s)/team(s)/experts in charge of the technical activities related to this Project,

- Reference to products/services of your Company/Organization or supporting Member to which the standards developed by this Project will apply,

- Motivation for your Company/Organization or supporting Member to participate in this Project.

1.2	Proposed approach

Proposed contribution to tasks & related cost

Identify the tasks to which your Company/Organization is proposing to contribute by filling-in the table below:

| Tasks No | Tasks Description | Max Budget Allocated in Euro | Amount in Euro (mandatory) | % of whole Task (mandatory) |
| --- | --- | --- | --- | --- |
| T00 | T1.1 Overall project management | 0 € |  |  |
| T01 | T1.2 Legal and Financial management | 0 € |  |  |
| T02 | T1.3 Selection of the Rapporteurs | 0 € |  |  |
| T03 | T2.1 Vertical rapporteurs’ Project Management | 98 081 € |  |  |
| T04 | T2.2 Contribution of vertical Rapporteurs | 571 000 € |  |  |
| T05 | T2.3 Edition of standards | 0 € |  |  |
| T06 | T3.1 Coordination of Rapporteurs contributions | 22 419 € |  |  |
| T07 | T3.2 Development of the stakeholder engagement strategy | 15 000 € |  |  |
| T08 | T3.3 Organisation of dissemination activities for stakeholder engagement and outreach | 40 000 € |  |  |
|  |  | 746 500 |  |  |

Amount in Euro (mandatory): Indicate the price offered for your contribution to the task(s)

% of whole task (mandatory):  Indicate to which percentage of the execution of the whole task your offer corresponds

Provide a description of the proposed approach, competences, reference to related activities:

- Explain which part of the task is corresponding to the requested percentage that your Company/Organization will handle,

- Explain the scope that your Company/Organization will cover,

- Explain your approach to the management of the quality and,

- Explain your approach to the management of the risks and their mitigation,

Describe and justify the proposed costs to achieve this project objectives

1.3	Proposed Topic

Please specify for which Topic your company proposes to take responsibility as rapporteur (you may select several topics; the final assignment will be agreed during the selection and preparatory meeting)

Topics listed in grey rows are not available for direct selection as they will be handled by CEN/CENELEC.

| # | Topic | Selection |
| --- | --- | --- |
| 16 | European standard(s) on essential cybersecurity requirements for identity management systems and privileged access management software and hardware, including authentication and access control readers, including biometric readers |  |
| 17 | European standard(s) on essential cybersecurity requirements for standalone and embedded browsers |  |
| 18 | European standard(s) on essential cybersecurity requirements for password managers |  |
| 19 | European standard(s) on essential cybersecurity requirements for software that searches for, removes, or quarantines malicious software |  |
| 20* | European standard(s) on essential cybersecurity requirements for products with digital elements with the function of virtual private network (VPN) |  |
| 21* | European standard(s) on essential cybersecurity requirements for network management systems |  |
| 22* | European standard(s) on essential cybersecurity requirements for Security information and event management (SIEM) systems |  |
| 23* | European standard(s) on essential cybersecurity requirements for boot managers |  |
| 24 | European standard(s) on essential cybersecurity requirements for public key infrastructure and digital certificate issuance software |  |
| 25* | European standard(s) on essential cybersecurity requirements for physical and virtual network interfaces |  |
| 26* | European standard(s) on essential cybersecurity requirements for operating systems |  |
| 27* | European standard(s) on essential cybersecurity requirements for routers, modems intended for the connection to the internet, and switches |  |
| 31 | European standard(s) on essential cybersecurity requirements for smart home general purpose virtual assistants |  |
| 32 | European standard(s) on essential cybersecurity requirements for smart home products with security functionalities, including smart door locks, security cameras, baby monitoring systems and alarm systems |  |
| 33 | European standard(s) on essential cybersecurity requirements for Internet connected toys covered by Directive 2009/48/EC that have social interactive features (e.g. speaking or filming) or that have location tracking features |  |
| 34 | European standard(s) on essential cybersecurity requirements for personal wearable products to be worn or placed on a human body that have a health monitoring (such as tracking) purpose and to which Regulation (EU) 2017/745 or Regulation (EU) 2017/746 do not apply or personal wearable products that are intended for the use by and for children |  |

*Scope excludes the industrial OT broad vertical which will be handled by CEN/CENELEC.

Annex II	 Terms and Conditions
CfE – STF 701 (REFERENCE BODY TC CYBER)
Deadline: 31 March 2025

2.1	Submission of Proposals

All proposals in response to this CfE shall be submitted before the deadline indicated in this Collective Letter, using exclusively the WEB application on the ETSI Portal at the following address: https://portal.etsi.org/cfe.

Proposals shall be composed of Curriculum Vitae of the proposed service providers’ personnel and the Annex I of this CfE duly filled-out.

Proposals that will be partial or incomplete at the deadline will not be accepted.

By applying, applicants accept the Terms and Conditions in Annex II, and Annex III.

2.2	Modification and Withdrawal of Proposals

Applicants may, without prejudice to themselves, modify or withdraw their proposal by written request, provided that the request is received by ETSI prior to the due date and time, at the address to which their proposal was submitted. The applicant may submit a new proposal provided that such new proposal is received prior to the deadline for responding which is specified in this Collective Letter.

2.3	Assessment of Proposals

The ETSI Director-General, in consultation with the Reference Body Chairman, is responsible for the selection of the service providers that will be contracted to perform this Project work. The ETSI Director-General and the Reference Body Chairman may be assisted by a Selection Panel to assess the applications received and make the final decision.

As per article 1.10.4 of the ETSI Directives, the Director-General may discard proposals that could be identified as creating potential conflict of interest.

The ETSI Secretariat will only communicate to the applicants the result of the selection (accepted or not accepted). Should applicants need more information on the rationale for the selection, they must address a formal request to the ETSI Director-General.

The following evaluation criteria will be applied to all proposals, in order of priority:

- Evidence that the applicant has the necessary structure and expertise to ensure delivery

- Reference to current or previous activities in the specific technical domain of this project

- Critical review of the most efficient way to achieve the objectives in this Project ToR

- Effective proposed approach/methodology for the execution of the tasks

- Implementation schedule

- Clear pricing policy

Compliance with the first two (2) criteria is mandatory.

Proposals that are not considered compliant with these criteria will be discarded.

Priority will be given to technical quality of the proposals. Pricing considerations will be taken into account to ensure that the best value for money is achieved. Compatibility with the maximum budget allocated to this Project will be verified before placing a Service Contract.

Following the assessment process, ETSI reserves the right to grant contracts to other than the cheapest proposals, to accept or reject any offer completely or in part, or to reject all proposals, without providing the reasons. If no offer is accepted, ETSI may decide to abandon the work or proceed in any other manner ETSI may select.

2.4	IPR and confidentiality Agreements

The information provided in this CfE, as well as the fact that the applicant has received the CfE, is considered confidential and protected under copyright laws. The applicant may not discuss, share, or use the information in this CfE for any purpose other than the response to this CfE.

ETSI will not disclose the content of any proposals to other applicants or any other party, with the exception of the persons involved in the assessment process described in §2.3 above.

However, ETSI reserves the right to make use of the information provided in this proposal to improve this project definition for the purpose of this CfE or any other manner in which ETSI may decide to proceed to select the service providers.

If successful, the applicant will be required to sign a Service Contract, which includes IPR and Confidentiality clauses aligned with the relevant policies in the ETSI Directives.

2.5	Preparation cost

ETSI will not be responsible for any costs or expenses that the applicant may incur in preparing and/or submitting the proposal.

2.6	Service Contract

A Service Contract will be proposed to the applicants that will be selected to perform the work.

Details on the Terms and Conditions of this contract can be found on the ETSI Portal, at the following address: https://portal.etsi.org/STF/STFs/Contracts.aspx

Annex III	Standardisation request to the European Committee for Standardisation (CEN), the European Committee for Electrotechnical Standardisation (Cenelec) and the European Telecommunications Standards Institute (ETSI) in support of Regulation (EU) 2024/2847 of the European Parliament and of the Council of 23 October 2024 on horizontal cybersecurity requirements for products with digital elements and amending Regulations (EU) No 168/2013 and (EU) No 2019/1020 and Directive (EU) 2020/1828 (Cyber Resilience Act)

CfE – STF 701 (REFERENCE BODY TC CYBER)
Deadline: 31 March 2025

https://ec.europa.eu/growth/tools-databases/enorm/mandate/606_en