ToR SPLU 196 (Ref. Body TC ESI)

Version: 2.0

Author: Laurent Velez – Date: 2025-09-15

Last updated by: ETSI Secretariat – Date: 2025-09-19

page 1 of 4

Terms of Reference – PLUGTESTSTM Technical Proposal

SPLU 196 (Ref. Body TC ESI)

Electronic Attestation of Attributes (EAA) Plugtests

Summary information

| Event Name | Electronic Attestation of Attributes (EAA) Plugtests |  |
| --- | --- | --- |
| Event start date | 04 May 2026 |  |
| Event end date | 01 June 2026 |  |
| Format of the event | EAA creation and verification |  |
| Type of event | remotely |  |
| Place of the Event (if so) |  |  |
| Reference Body /ISG involved | Ref. Body TC ESI |  |
| In collaboration with/with the support of | EC (eIDAS2 regulation) |  |
| Standardised methodologies, techniques and best practices used: | • EG 202 237: Generic Methodology for Interoperability Testing |  |
| ETSI Funding | Maximum budget : 40 000 EUR |  |
| Time scale | From | 2025-11-03 |
|  | To | 2026-09-30 |

Part I –Technical Proposal

# Rationale & Objectives

European Union Member States have established the necessary technical infrastructure to process electronically signed documents required for accessing online services provided by or on behalf of public sector bodies.

Regulation (EU) No 910/2014 (the eIDAS Regulation) governs trust services and stipulates that when a Member State requires an advanced electronic signature or seal for accessing such services, it must recognise the following:

- Advanced electronic signatures and seals,

- Advanced electronic signatures and seals based on a qualified certificate,

- Qualified electronic signatures and seals in specific formats,

- Or alternative formats validated using designated reference methods.

This framework ensures that all relevant standards are presented in a clear, coherent, and accessible manner to promote maximum interoperability. It includes the evolution of existing specifications into European Norms and the development of implementation guidelines.

Under eIDAS, legal requirements have been defined for the European Digital Identity Wallet (EUDI Wallet) and for new Trusted Services, such as the issuance of Electronic Attestation of Attributes (EAA).

The EUDI Wallet is a flagship EU initiative aimed at providing citizens with secure, user-friendly, and privacy-respecting access to digital services across Europe. Proposed by the European Commission in June 2021 as part of the eIDAS Regulation revision, it was officially adopted under eIDAS 2.0 (Regulation EU 2024/1183) in May 2024.

The wallet will enable European citizens to:

- Prove their identity,

- Store and share official documents (e.g., diplomas, driving licenses, medical records),

- Access public and private services directly from their mobile devices.

It will be interoperable across all EU Member States, facilitating seamless cross-border interactions in areas such as travel, education, healthcare, and employment.

Currently, ETSI ESI is developing several standards to support the lifecycle of EAAs, including Trusted Services for their issuance and validation, and for the EUDI Wallet overall.

To facilitate testing, an EAA Plugtests event is proposed. The goal is to assess the interoperability of EAAs generated by products implementing Technical Specification ETSI TS 119 472-1.

Scope of the Plugtests:

- The formats tested will include those based on SD-JWT VC and ISO 18013-5.

- Each participant will generate EAAs according to specific test cases and requirements, and upload them to a portal.

- Other participants will then validate these EAAs and submit their verdicts.

- Test cases will be based on the attribute metadata requirements outlined in Clause 4 of TS 119 472-1 for each format.

This testing will help identify potential issues that could lead to discrepancies in EAA creation or verification.

Three types of tests are planned:

- Generation and Cross-Verification Tests
Participants generate a set of valid EAAs with defined characteristics. Other participants then verify these EAAs. The Plugtests portal automatically updates interoperability matrices accessible to all participants.

- Verification-Only Tests
ETSI provides a set of invalid EAAs for various reasons. Participants attempt to verify these EAAs to ensure their tools correctly identify them as invalid.

- Conformance Tests (if possible)
Participants upload EAAs to a conformance checker for verification.

As a remote event, participants will not need to travel to ETSI premises. All EAA exchanges and verifications will be conducted via a dedicated portal.

Testing will not occur in real time; the portal will be available 24/7 throughout the event, allowing participants from all time zones to generate, upload, and verify signatures at their convenience.

# Expertise required / Budget allocated

## Task summary

Task description:

| Task No. | Task description |
| --- | --- |
| T0 | Technical Project Management |
| T1 | Developing interoperability tests for EAA |
| T2 | Developing a signature portal based on the portal used for previous Plugtests would require new functionalities and capabilities. Enhancements in performance and security are also foreseen. |
| T3 | Supporting the preparation and remote integration phases, including participation in regular conference calls; |
| T4 | Support for participants with portal updates and issues. |
| T5 | Answering participants’ questions on the testing and on the specifications; |
| T6 | Assisting with the consolidation and formatting of the test results and reported issues to produce the Plugtests Report. |

## Expertise required / Team structure

(Up to) 4 participants to ensure the following mix of competences:

| Priority | - Qualifications and competences (example here below) |
| --- | --- |
| High | Practical experience with Advanced Electronic Signature Testing |
| High | Expertise in all the ETSI TC ESI Specifications covered by the testing |
| High | Expertise in EUDI Wallet |
| High | Experience with Signature Plugtests portal and infrastructure |
| High | Programming skills in languages and technologies, among: Linux, Python, Vue.js, Docker, JavaScript, XML/XLST, PHP, Bash, Security. |
| High | - Previous experience in interoperability events. Familiar with the ETSI interoperability testing methodology. |

## Budget allocated:

Budget table:

| Task No. | Task description | Total in EUR | Milestone cut off date |
| --- | --- | --- | --- |
| T0 | Technical Project Management | ETSI CTI |  |
| T1 | Developing interoperability tests for EAA. | 17 100 |  |
| T2 | Developing a Plugtests portal based on the portal used for previous Plugtests. New functionalities and capabilities would be required. Enhancements in performance and security are also foreseen. | 6 000 |  |
| T3 | Supporting the preparation and remote integration phases, including participation in regular conference calls; | 3 000 |  |
| T4 | Support for participants with portal updates and issues. | 1 000 |  |
| T5 | Answering participants’ questions on the testing and on the specifications; | 9 000 |  |
| T6 | Assisting with the consolidation and formatting of the test results and reported issues to produce the Plugtests Report. | 3 900 |  |
| MA | All tasks achieved, event closed |  | 2026-09-30 |
| TOTAL |  | 40 000 |  |

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 1.0 | 2025-09-15 | Laurent Velez |  |  |
| 2.0 | 2025-09-19 | ETSI Secretariat | Final | Update before CL publication |

Annex I	Response to the Request for Proposals
CfE – SPLU 196 (TC ESI) Deadline: 2025-10-23

| Contractor name * Indicate the Company/Organisation Name |  |
| --- | --- |

| Contractor information * |  |  |  |  |
| --- | --- | --- | --- | --- |
| Contact person for the technical aspects |  | Contact person for Decision on ETSI financial offer to this project (if any) |  |  |
| Title |  | Title |  |  |
| First name |  | First name |  |  |
| Last name |  | Last name |  |  |
| Role |  | Role |  |  |
| e-mail |  | e-mail |  |  |
| Phone |  | Phone |  |  |
|  |  | Yes |  | No |
| Do you or any employee of your Company/Organisation hold an elected or appointed position in the Reference Body requesting the SPLU 196 creation? |  | o Indicate in which position: ----------------------------------- |  | o |
| If you are self-employed candidate: Do you currently have other contracts in progress with ETSI? |  | o |  | o |

1.1	Introduction

A short presentation of the technical structure responsible for this activity, e.g.:

- Business area, number of employees, link to WEB site,

- Department(s)/team(s)/experts in charge of the technical activities related to this Project,

- Motivation for your Company/Organisation or supporting Member to participate in the Project.

1.2	Proposed approach

Proposed contribution to tasks & related cost

Identify the tasks to which your Company/Organisation is proposing to contribute by filling-in the table below:

| Tasks_No | Tasks_Description | Max_Budget_Allocated_in_Euro | Amount_in_Euro (mandatory) | %_of_whole_Task_(mandatory) |
| --- | --- | --- | --- | --- |
| 00 | Technical Project Management | ETSI CTI | . | . |
| 01 | Developing interoperability tests for EAA | 17 100 | . | . |
| 02 | Developing a signature portal based on the portal used for previous Plugtests would require new functionalities and capabilities. Enhancements in performance and security are also foreseen. | 6 000 | . | . |
| 03 | Supporting the preparation and remote integration phases, including participation in regular conference calls; | 3 000 | . | . |
| 04 | Support for participants with portal updates and issues. | 1 000 | . | . |
| 05 | Answering participants’ questions on the testing and on the specifications; | 9 000 | . | . |
| 06 | Assisting with the consolidation and formatting of the test results and reported issues to produce the Plugtests Report. | 3 900 |  |  |
| TOTAL |  | 40 000 |  |  |

Amount in Euro (mandatory): Indicate the price offered for your contribution to the task(s)

% of whole task (mandatory):  Indicate to which percentage of the execution of the whole task your offer corresponds

Provide a description of the proposed approach, competences, reference to related activities:

- Explain which part of the task is corresponding to the requested percentage that your Company/Organisation will handle,

- Explain the scope that your Company/Organisation will cover,

- Explain your approach to the management of the quality and,

- Explain your approach to the management of the risks and their mitigation,

- Describe and justify the proposed costs to achieve this project objectives.

Annex II	 Terms and Conditions
CfE – SPLU 196 (TC ESI) Deadline: 2025-10-23

2.1	Submission of Proposals

All proposals in response to this CfE shall be submitted before the deadline indicated in this Collective Letter, using exclusively the WEB application on the ETSI Portal at the following address: https://portal.etsi.org/cfe.

Proposals shall be composed of Curriculum Vitae of the proposed service providers’ personnel and the Annex I of this CfE duly filled-out.

Proposals that will be partial or incomplete at the deadline will not be accepted.

The Terms and Conditions in this Annex will apply.

2.2	Modification and Withdrawal of Proposals

Applicants may, without prejudice to themselves, modify or withdraw their proposal by written request, provided that the request is received by ETSI prior to the due date and time, at the address to which their proposal was submitted. The applicant may submit a new proposal provided that such new proposal is received prior to the deadline for responding which is specified in this Collective Letter.

2.3	Assessment of Proposals

The ETSI Director-General, in consultation with the CTI Director, is responsible for the selection of the service providers that will be contracted to perform the Project work. The ETSI Director-General and the CTI Director may be assisted by a Selection Panel to assess the applications received and make the final decision.

As per article 1.10.4 of the ETSI Directives, the Director-General may discard proposals that could be identified as creating potential conflict of interest.

The ETSI Secretariat will only communicate to the applicants the result of the selection (accepted or not accepted). Should applicants need more information on the rationale for the selection, they must address a formal request to the ETSI Director-General.

The following evaluation criteria will be applied to all proposals, in order of priority:

- Evidence that the applicant has the necessary structure and expertise to ensure delivery

- Reference to current or previous activities in the specific technical domain of this project

- Critical review of the most efficient way to achieve the objectives in the Project’s ToR

- Effective proposed approach/methodology for the execution of the tasks

- Implementation schedule

- Clear pricing policy

Compliance with the first two (2) criteria is mandatory.

Proposals that are not considered compliant with these criteria will be discarded.

Priority will be given to technical quality of the proposals. Pricing considerations will be taken into account to ensure that the best value for money is achieved. Compatibility with the maximum budget allocated to this STF will be verified before placing a Service Contract.

Following the assessment process, ETSI reserves the right to grant contracts to other than the cheapest proposals, to accept or reject any offer completely or in part, or to reject all proposals, without providing the reasons. If no offer is accepted, ETSI may decide to abandon the work or proceed in any other manner ETSI may select.

2.4	IPR and confidentiality Agreements

The information provided in this CfE, as well as the fact that the applicant has received the CfE, is considered confidential and protected under copyright laws. The applicant may not discuss, share, or use the information in this CfE for any purpose other than the response to this CfE.

ETSI will not disclose the content of any proposals to other applicants or any other party, with the exception of the persons involved in the assessment process described in §2.3 above.

However, ETSI reserves the right to make use of the information provided in this proposal to improve the project definition for the purpose of this CfE or any other manner in which ETSI may decide to proceed to select the service providers.

If successful, the applicant will be required to sign a Service Contract, which includes IPR and Confidentiality clauses aligned with the relevant policies in the ETSI Directives.

2.5	Preparation cost

ETSI will not be responsible for any costs or expenses that the applicant may incur in preparing and/or submitting the proposal.

2.6	Service Contract

A Service Contract will be proposed to the applicants that will be selected to perform the work.

Details on the Terms and Conditions of this contract can be found on the ETSI Portal, at the following address: https://portal.etsi.org/Portals/0/TBpages/STFs/Docs/SPLU_Service_Contract_%20Template_V1.0_Clean_Final.pdf