ToR TTF T058 (TC MTS / WG AI)

Version: 0.4

Author: Dr. Jürgen Großmann, Dr. Philip Makedonski, Finn Kristoffersen, Taras Holoyad – Date: 2025-10-14

Last updated by: ETSI Secretariat – Date: 2025-12-

page 1 of 12

Terms of Reference – Testing Task Force

TTF T058 (TC MTS / WG AI)

Evaluation and Enhancement of the Harmonized Documentation Approach ETSI TR 104 119

Summary information

| Approval status | Approved by TC MTS / WG AI (Doc Ref: MTS(25)000040r1) |  | YES |
| --- | --- | --- | --- |
| Reference Body | TC MTS / WG AI |  |  |
| ETSI Funding | Maximum budget: 96 500 EUR |  |  |
| Minimum of 4 ETSI Members Support | YES |  |  |
| Time scale | From | 2026-02-02 |  |
|  | To | 2027-03-31 |  |
| Work Items | See clause 3.2 below Revision of ETSI TR 104 119 |  |  |
| TTF Roadmap reference | https://docbox.etsi.org/MTS/AI/05-Contributions/2025/MTSAI(25)000016_Harmonized_Documentation_Approach_for_Trustworthy_AI_Roadmap.docx |  |  |

Part I –TTF Technical Proposal

# Rationale & Objectives

## Rationale

The ETSI TC MTS provides technologies, tools, and guidelines on conformance and interoperability testing and certification of protocols and other systems, including AI systems, that are under standardisation at various ETSI groups and committees.

The European AI regulation (EU) 2024/1689 classifies AI use by risk level and imposes documentation, auditing, and process requirements on providers and deployers of AI systems. Thus, ‘high-risk’ AI systems must undergo a rigid conformity assessment and providers and deployers must provide a technical documentation demonstrating major properties of the AI system before they can enter the European market.

ETSI TR 104 119 establishes a foundational documentation approach to support transparency, accountability, and quality assurance across the lifecycle of AI-enabled systems, particularly those classified as high-risk under the EU AI Act. While ETSI TR 104 119 specifies the documentation items, stakeholders, and lifecycle integration of documentation artifacts, it remains a guideline-level deliverable without thorough validation.

ETSI TR 104 119 currently lacks both validation in operational settings and ready-to-use documentation templates that would help operationalise the documentation approach and provide clear guidance for industrial application. The complexity and specificity of AI deployments in regulated domains such as healthcare, finance, and the telecommunication industry present different documentation challenges and regulatory constraints. To ensure that the ETSI TR 104 119 is truly fit-for-purpose under the EU AI Act, it must be supported by practical documentation templates and evaluated across representative use cases that reflect the real needs and compliance realities of high-risk AI applications.

## Objectives of the work to be executed

This proposal is a follow-up of TTF 038 and aims to identify and execute a set of targeted evaluations of ETSI TR 104 119 across selected critical domains. By developing practical templates and applying the documentation approach in multiple, sector-specific AI system contexts, the TTF will assess the relevance, usability, and completeness of both the existing documentation approach and the newly developed templates, providing feedback for refinement and stronger regulatory alignment.

The main objectives of the proposed follow-up work are:

- Identify representative high-risk AI use cases in critical and regulated sectors such as healthcare, finance, or telecommunication in which the documentation approach can be applied and evaluated.

- Develop templates covering various documentation requirements such as Instruction for Use, Human Oversight, Lifecycle and Maintenance Information etc., which are in accordance with the framework developed in ETSI TR 104 119, and which allow industry to document their AI systems in compliance with the EU AI Act.

- Apply the templates and the documentation approach to the use cases, tailoring them to the sector-specific risk profiles, lifecycle practices, and regulatory expectations.

- Evaluate the applicability of the templates and the documentation approach to the EU AI Act, focusing on transparency obligations, conformity assessment needs, documentation sufficiency for notified bodies, and support for market surveillance.

- Engage relevant stakeholders from each domain (e.g., AI developers, AI providers, regulators, auditors) to review and provide structured feedback on the documentation templates and the documentation approach.

- Revise ETSI TR 104 119 with findings across domains, aiming to identify common strengths, domain-specific gaps, and opportunities to improve the generalisability and regulatory alignment of the templates and the documentation approach.

## Previous funded activities in the same domain

This proposal is a direct continuation of the work initiated by ETSI TTF 038 that developed by ETSI TR 104 119 on behalf of TC MTS/MTS AI. While ETSI TR 104 119 provides a comprehensive guideline, there has been no prior funded activity specifically aimed at testing its application across multiple regulated sectors or assessing its operational compatibility with the EU AI Act. This proposal represents the first effort to systematically evaluate the approach in realistic, high-risk environments.

It also complements existing ETSI work, such as ETSI TR 103 910 (Trustworthy AI assessment framework) and ETSI TS 104008 (Conformity assessment methodology), by focusing on the documentation dimension that underpins and enables successful regulatory oversight and certification.

## Consequences if not agreed

If this proposal is not agreed, the ETSI TR 104 119 will remain weakly validated in practice, reducing confidence in its relevance for high-risk AI applications. This could limit adoption by industry and conformity bodies and weaken ETSI’s influence on regulatory implementation of the EU AI Act. Without cross-sector evaluation, critical feedback needed to refine and generalise the approach will be lost.

# ETSI Members Support

| # | ETSI Member | Supporting delegate |
| --- | --- | --- |
| 1 | Fraunhofer FOKUS | Dr. Jürgen Großmann |
| 2 | Institut für Informatik, Universität Göttingen | Dr. Phillip Makedonski |
| 3 | Cinderella ApS | Finn Kristoffersen |
| 4 | CERTH | Dr. Marija Jankovic |
| 5 | Bundesnetzagentur | Taras Holoyad |

# Deliverables

## Base documents

| Document | Title | Status |
| --- | --- | --- |
| ETSI TR 103 910 | Methods for Testing and Specification (MTS); AI Testing;Test Methodology and Test Specification forML-based Systems | Published |
| ETSI TS 104008 | MTS Continuous Auditing Based Conformity Assessment for AI-enabled systems | Stable Draft |
| ETSI TR 104 119 | Specification (MTS); AI Testing; Guidelines for Documentation of AI-enabled Systems | Published t |
| (EU) 2024/1689 | European AI regulation AI regulation (EU) 2024/1689 | Published |
|  | Ethics Guidelines for Trustworthy AI (HLEG AI) https://digital-strategy.ec.europa.eu/en/library/ethics-guidelines-trustworthy-ai | Published |
|  | OECD AI Principles “Ministerial Statement on Trade and Digital Economy”, Ministry of Foreign Affairs of Japan, 09.06.2019. https://www.mofa.go.jp/files/000486596.pdf | Published |

## New deliverables

Objective:

Revision of TR 104 119 by elaboration and evaluation of documentation templates and application examples for AI ACT compliant documentation with ETSI TR 104 119.

Deliverables:

- Documentation templates as an enhancement for TR 104 119.

| Deliv. | Work Item code Standard number | Working title | Expected date for publication |
| --- | --- | --- | --- |
| D1* | TS 104 119 | Revision of TR 104 119 Scope: TS 104119 specifies a harmonized documentation approach for AI-enabled systems that ensures the continuous and consistent documentation of quality and quality-related attributes throughout the system lifecycle. It extends and supersedes ETSI TR 104 119 by formalizing the documentation process and introducing structured, AI Act-compliant templates covering essential documentation requirements and items such as the AI system description, data and model documentation, human oversight, risk management, and conformity assessment support. | 4/2027 |

* Additional deliverables can be added to capture informative content from the TTF's work that cannot be integrated into a new revision of TR 104 119.

# Maximum budget

## Task summary/Manpower Budget

| Task | Task short description | Description | Budget (EUR) |
| --- | --- | --- | --- |
| T0 | Project management | Coordinate the overall project, ensure alignment with ETSI procedures, and manage communication with all stakeholders. | 8.000 |
| T1 | Use-case selection and planning | Identify and select representative high-risk AI use cases in critical sectors (e.g., healthcare, finance, telecommunications). Collaborate with external stakeholders such as industry partners and regulators to select the use cases. Develop a detailed plan for how the documentation approach will be applied and evaluated for each case. | 10.000 |
| T2 | Develop and apply documentation templates | Develop and apply documentation templates and examples in line with ETSI TR 104 119 that cover the different documentation requirements of the AI-Act. Apply these templates to the selected use cases tailoring them to real-world operational practices, domain- specific characteristics, and compliance requirements. | 35.000 |
| T3 | Compliance & quality evaluation. | Evaluate the extent to which the developed templates and the documentation approach meet the requirements of the EU AI Act. Collect structured feedback from stakeholders on the clarity, user-friendliness, and completeness of the documentation produced. Identify gaps, redundancies, and best practices. | 17.000 |
| T4 | Synthesis and TR 104 119 revision. | Consolidate insights across all use cases and domains to identify common lessons learned, strengths, and domain-specific improvement needs. Revise ETSI TR 104 119, including improved templates and guidance to enhance its generalisability and regulatory alignment. | 22.000 |
| TOTAL |  |  | 92.000 |

## Travel budget

| Expected travels | Cost estimate (EUR) |
| --- | --- |
| Participation at 3 MTS by the TTF Leader or a representative of the TTF Leader | 3.000 |
| Participation at UCAAT 2026 to promote the templates for AI Act compliant documentation | 1.500 |
| TOTAL | 4.500 |

## Other budget line

None.

Part II – Details on TTF Technical Proposal

# Tasks, Technical Bodies and other stakeholders

## Organization of the work

The working group MTS AI will, acting as a steering group, oversee and advise the work of the proposed TTF. It will plan regular meetings between the TTF working sessions to monitor the progress of the work and provide technical advice.

During the TTF project lifetime regular online conference calls will be organised, where each project member presents their work and progress is checked, coordinated by the TTF Leader. These F2F work sessions will be organised by the TTF Leader to allow for strategic alignment, complex problem-solving, and cross-functional coordination. Participation in the F2F work sessions is mandatory unless there are serious reasons not to attend. By default, the work sessions take place at ETSI, but participating companies may also organise the F2F work sessions. If possible, the work sessions should be collocated with the MTS meetings.

All deliverables will be subject to established quality management approaches within ETSI, including multi-stage drafting with early, stable, and final drafts presented to the technical reference bodies, as well as disseminated for feedback to other relevant technical bodies and stakeholders.

Outcomes of the project will be disseminated in other venues such as the ETSI UCAAT, ETSI AI Conferences, etc. to gather further feedback from interested parties.

All deliverables are new work items. Final drafts for all deliverables are expected at the end of the project as the work will be done in strong cooperation with MTS AI to synchronize on the progress with other activities. The multi-stage drafting will help to ensure that required content is provided sufficiently early to avoid blocking the work on dependent deliverables.

## Other interested ETSI Technical Bodies

Due to the high importance of AI for ICT in general and for ETSI standards in particular, it is assumed that many TCs will have dedicated interest in the results of the TTF. An overview of all AI related TCs can be found on the corresponding ETSI sites. In order to spread the results as broadly as possible, MTS will make use of existing coordination tools at ETSI. This includes the coordinated dissemination of the TTF results via OCG AI as well as via selected TCs with special interest such as TC SAI and TC DATA.

## Other stakeholders

For the coordination of standardization work, exchanges with ISO/IEC JTC1 SC42 "Artificial Intelligence" as well as CEN-CENELEC JTC 21 "Artificial Intelligence" can be targeted, so that duplication of work can be avoided, and a focus can be placed on the topics relevant to AI in the European legislative proposal.

With regard to ISO/IEC JTC1 SC42 "Artificial Intelligence", an exchange on topics relevant to test requirements, basic standards, data, trustworthiness, and computational approaches can take place. As well, coordination with the European committee CEN-CENELEC JTC 21 "Artificial Intelligence" should take place on topics such as conformity assessment, risk management and classification of artificial intelligence. Due to ETSI's strong focus on telecommunications, coordination with CEN-CENELEC and ISO/IEC is important since the industrial policy goals and the European Commission's priority legal requirements can be achieved efficiently together.

Part III: Execution of Work

# Work plan, time scale and resources

## Task description

| Task 0 | # Project Management |
| --- | --- |
| Objectives | Planning, organisation, and preparation of TTF meetings On-going reporting Participation at TC/WG meetings Delivery of the TTF final report |
| Input | This ToR Information from the preparatory meeting Expertise availability information and other project management data |
| Output | Session planning Materials for WG and TC meetings Progress reports Final report |
| Interactions | The TTF leader will interact with the MTS AI Working Group and the MTS Communicating with other stakeholders and TTFs Additional support will be provided by the ETSI secretariat |
| Resources required | Resource planning, reporting, and coordination 8.000 € |

| Task 1 | # Use-Case Selection and Planning |
| --- | --- |
| Objectives | Identify at least 2 representative high-risk AI use cases across key sectors (such as healthcare, finance, telecommunications). Collaborate with stakeholders (industry, regulators, conformity bodies) to select relevant cases. Define evaluation plans describing how ETSI TR 104 119 and the documentation templates will be applied. Establish indicators for the use case selection. |
| Input | ETSI TR 104 119 and related deliverables (TR 103910, TS 104008). EU AI Act (EU 2024/1689) requirements. Stakeholder input from preparatory workshops. |
| Output | A list of selected, validated use cases. Detailed evaluation and implementation plans per use case. Mapped regulatory relevance for each domain. |
| Interactions | Regular consultation with MTS AI and participating ETSI Members. Coordination with external partners (industry, regulators) for access to use-case data. Information exchange with related standardization initiatives (CEN/CENELEC JTC 21, ISO/IEC JTC1 SC42). |
| Resources required | Identification, coordination, and planning of representative use cases. 10 000 EUR |

| Task 2 | # Develop and Apply Documentation Templates |
| --- | --- |
| Objectives | Develop AI Act-compliant documentation templates and examples in line with ETSI TR 104 119. Tailor templates to selected use cases considering domain-specific risks and lifecycle processes. Demonstrate the application of the documentation approach in realistic industrial contexts (use cases). |
| Input | Use-case descriptions from Task 1. Requirements and feedback from domain stakeholders. |
| Output | Reusable documentation templates and filled examples. Guidance for sector-specific adaptation. |
| Interactions | Validation with MTS AI and domain experts. Iterative review cycles with use case stakeholder (e.g. AI developers, auditors, and regulators). |
| Resources required | Template design, testing, and documentation within representative use cases. 35 000 EUR |

| Task 3 | # Compliance and Quality Evaluation |
| --- | --- |
| Objectives | Assess the developed templates and the revised documentation approach regarding coverage of EU AI Act requirements. Collect structured feedback from stakeholders on clarity, sufficiency, and user-friendliness. Identify documentation gaps, redundancies, and best practices. |
| Input | Completed templates and documentation from Task 2. Compliance checklists/requirements derived from EU AI Act (EU 2024/1689). Stakeholder review input (providers, deployers, conformity assessment bodies). |
| Output | Evaluation report on compliance and quality. Gap analysis and improvement recommendations. Summary of stakeholder feedback and validation results. |
| Interactions | Interaction with regulatory experts for conformity validation. Coordination with ETSI WG AI to ensure methodological consistency. |
| Resources required | Compliance analysis, evaluation reporting, and stakeholder workshops. 17 000 EUR |

| Task 4 | # Synthesis and Revision of ETSI TR 104 119 |
| --- | --- |
| Objectives | Consolidate results and lessons learned from all use cases. Integrate the validated templates and guidance into a revised ETSI TR 104 119. |
| Input | Use cases, templates and evaluation from Task 1, 2, and 3. Feedback from stakeholders and MTS AI. Baseline version of ETSI TR 104 119. |
| Output | Revision of ETSI TR 104 119 as ETSI TS 104 119 including template annexes. Final synthesis report and improvement recommendations. Dissemination material for ETSI UCAAT and AI conferences. |
| Interactions | Regular exchanges with MTS AI Coordination with relevant TCs (SAI, DATA). Coordination with CEN/CENELEC JTC 21 and ISO/IEC JTC1 SC42 to ensure cross-standard alignment. |
| Resources required | Consolidation and editorial work for the revised ETSI TS 104 119. 22 000 EUR |

## Milestones

| Milestone | Description | Cut-Off Date |
| --- | --- | --- |
| A | 1st progress report to TC MTS & early draft | 2026-06-08 |
| Reference Body Deliverable | 1st progress report to be approved at MTS#98 & early draft of documentation templates and use-case plans |  |
| ETSI Deliverable | Early draft submitted to TC MTS |  |

| Milestone | Description | Cut-Off Date |
| --- | --- | --- |
| B | 2nd progress report to TC MTS & stable draft | 2026-10-31 |
| Reference Body Deliverable | 2nd progress report to be approved at MTS#99 & stable draft of documentation templates and initial evaluation results |  |
| ETSI Deliverable | Stable draft submitted to TC MTS |  |

| Milestone | Description | Cut-Off Date |
| --- | --- | --- |
| C | Final report to TC MTS & final draft | 2027-02-26 |
| Reference Body Deliverable | Final report & final draft of revised TR/TS 104 119 to be approved by TC MTS |  |
| ETSI Deliverable | Final draft approved by TC MTS |  |

| Milestone | Description | Cut-Off Date |
| --- | --- | --- |
| D | Deliverables published, TTF closed | 2027-03-31 |

## Task summary

| Code | Task / Milestone | Target Date |  | Estimated Cost (EUR) |
| --- | --- | --- | --- | --- |
|  |  | From | To |  |
|  | Start of work | 2026-02-02 |  |  |
| T0 | Project Management | 2026-02-02 | 2027-03-31 | 8.000 |
| T1 | Use-case selection and planning | 2026-02-02 | 2026-03-31 | 10.000 |
| T2 | Develop and apply documentation templates | 2026-02-02 | 2026-09-30 | 35.000 |
| T3 | Compliance & quality evaluation. | 2026-09-01 | 2026-11-30 | 17.000 |
| T4 | Synthesis and TR 104 119 revision. | 2026-04-01 | 2027-01-29 | 22.000 |
| MA | Early draft and 1st progress report | MTS#98 | 2026-06-08 |  |
| MB | Stable draft and 2nd progress report | MTS#99 | 2026-10-31 |  |
| MC | Final draft and final report |  | 2027-02-26 |  |
| MD | Deliverables published, TTF closed |  | 2027-03-31 |  |
| TOTAL |  |  |  | 92.000 |

|  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task/ Mil. | F | M | A | M | J | J | A | S | O | N | D |  | J | F | M |
| T0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Expertise required

## Team structure

This TTF should be made up of (up to) 5 experts to ensure the following mix of competences, and includes one project leader:

| Priority | - Qualifications and competences |
| --- | --- |
| High | - Artificial intelligence and machine learning training and operational expertise including quality assurance of AI. |
| High | - Knowledge of the European AI Act and associated standardization activities |
| High | - Expertise in the certification, auditing and documentation of industrial systems with focus on AI |
| Medium | - Familiarity with standards development and document revision workflows within ETSI and related bodies |
| Medium | - Experience with sector-specific AI deployments (e.g., healthcare, finance, telecommunications) and associated regulatory constraints |
| High | - Organizational and consensus building skills (project leader) |

All participants will have to demonstrate report writing skill and the ability to work in an international environment.

Part IV:	TTF performance evaluation criteria

# Performance Indicators

| Select relevant Performance indicators applicable for these ToR (X) |  |
| --- | --- |
| Contribution from ETSI Members to TTF work |  |
| Monthly steering group meetings with the MTS AI working group | x |
| Contributions/comments received from the MTS TB | x |
| Contribution from the TTF to ETSI work |  |
| Contributions to MTS meetings (number of documents / meetings / participants) | x |
| Contributions to other Reference Bodies | x |
| Presentations in workshops, conferences, stakeholder meetings | x |
| Liaison with other stakeholders |  |
| Stakeholder participation in the project (category, business area) | x |
| Cooperation with other standardization bodies |  |
| Potential interest of new members to join ETSI |  |
| Liaison to identify requirements and raise awareness on ETSI deliverables |  |
| Comments received on drafts (e.g. on WEB site, mailing lists, etc.) | x |
| Quality of deliverables |  |
| Approval of deliverables according to schedule | x |
| Respect of time scale, with reference to start/end dates in the approved ToR | x |
| Comments from Quality review by Reference Body | x |
| Comments from Quality review by ETSI Secretariat | x |

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 2025-06-11 | Jürgen Großmann | Draft | Initial ToR (Part I only) |
| 0.2 | 2025-10-14 | Jürgen Großmann | Final | Complete ToR |
| 0.3 | 2025-10-29 | ETSI Secretariat | Final | Update before ETSI internal kick off meeting |
| 0.4 | 2025-12-03 | ETSI Secretariat | Final | Final update before CL publication |

Annex I	Response to the Request for Proposals
CfE – TTF T058 (REFERENCE BODY MTS WG AI)

Deadline: 02 January 2026

| Contractor information * |  |  |  |  |
| --- | --- | --- | --- | --- |
| Contractor name *: Indicate the Company/Organisation Name |  |  |  |  |
| Contact person for the technical aspects |  | Contact person for Decision on ETSI financial offer to this project (if any) |  |  |
| Title |  | Title |  |  |
| First name |  | First name |  |  |
| Last name |  | Last name |  |  |
| Role |  | Role |  |  |
| e-mail |  | e-mail |  |  |
| Phone |  | Phone |  |  |
|  |  | Yes |  | No |
| Do you or any employee of your Company/Organisation hold an elected or appointed position in the Reference Body requesting the TTF T058 creation? |  | o Indicate in which position: ----------------------------------- |  | o |
| If you are self-employed candidate: Do you currently have other contracts in progress with ETSI? |  | o |  | o |

All fields marked with an asterix (*) are mandatory

1.1	Introduction

A short presentation of the technical structure responsible for this activity, e.g.:

- Business area, number of employees, link to WEB site,

- Department(s)/team(s)/experts in charge of the technical activities related to this Project,

- Reference to products/services of your Company/Organization or supporting Member to which the standards developed by this Project will apply,

- Motivation for your Company/Organisation or supporting Member to participate in this Project.

1.2	Proposed approach

Proposed contribution to tasks & related cost

Identify the tasks to which your Company/Organisation is proposing to contribute by filling-in the table below:

| Tasks No | Tasks Description | Max Budget Allocated (EUR) | Amount in Euro (mandatory) | % of whole Task (mandatory) |
| --- | --- | --- | --- | --- |
| 00 | Project management | 8 000.00 | . | . |
| 01 | Use-Case Selection and Planning | 10 000.00 | . | . |
| 02 | Develop and Apply Documentation Templates | 35 000.00 | . | . |
| 03 | Compliance and Quality Evaluation | 17 000.00 | . | . |
| 04 | Synthesis and Revision of ETSI TR 104 119 | 22 000.00 | . | . |
|  | Total: | 92 000.00 |  |  |

Amount in Euro (mandatory): Indicate the price offered for your contribution to the task(s)

% of whole task (mandatory):  Indicate to which percentage of the execution of the whole task your offer corresponds

Provide a description of the proposed approach, competences, reference to related activities:

- Explain which part of the task is corresponding to the requested percentage that your Company/Organisation will handle,

- Explain the scope that your Company/Organisation will cover,

- Explain your approach to the management of the quality and,

- Explain your approach to the management of the risks and their mitigation,

- Describe and justify the proposed costs to achieve this project objectives.

Annex II	 Terms and Conditions
CfE – TTF T058 (REFERENCE BODY MTS WG AI)

Deadline: 02 January 2026

2.1	Submission of Proposals

All proposals in response to this CfE shall be submitted before the deadline indicated in this Collective Letter, using exclusively the WEB application on the ETSI Portal at the following address: https://portal.etsi.org/cfe.

Proposals shall be composed of Curriculum Vitae of the proposed service providers’ personnel and the Annex I of this CfE duly filled-out.

Proposals that will be partial or incomplete at the deadline will not be accepted.

The Terms and Conditions in this Annex will apply.

2.2	Modification and Withdrawal of Proposals

Applicants may, without prejudice to themselves, modify or withdraw their proposal by written request, provided that the request is received by ETSI prior to the due date and time, at the address to which their proposal was submitted. The applicant may submit a new proposal provided that such new proposal is received prior to the deadline for responding which is specified in this Collective Letter.

2.3	Assessment of Proposals

The ETSI Director-General, in consultation with the Reference Body Chair, is responsible for the selection of the service providers that will be contracted to perform this Project work. The ETSI Director-General and the Reference Body Chair may be assisted by a Selection Panel to assess the applications received and make the final decision.

As per article 1.10.4 of the ETSI Directives, the Director-General may discard proposals that could be identified as creating potential conflict of interest.

The ETSI Secretariat will only communicate to the applicants the result of the selection (accepted or not accepted). Should applicants need more information on the rationale for the selection, they must address a formal request to the ETSI Director-General.

The following evaluation criteria will be applied to all proposals, in order of priority:

- Evidence that the applicant has the necessary structure and expertise to ensure delivery

- Reference to current or previous activities in the specific technical domain of this project

- Critical review of the most efficient way to achieve the objectives in this Project ToR

- Effective proposed approach/methodology for the execution of the tasks

- Implementation schedule

- Clear pricing policy

Compliance with the first two (2) criteria is mandatory.

Proposals that are not considered compliant with these criteria will be discarded.

Priority will be given to technical quality of the proposals. Pricing considerations will be taken into account to ensure that the best value for money is achieved. Compatibility with the maximum budget allocated to this Project will be verified before placing a Service Contract.

Following the assessment process, ETSI reserves the right to grant contracts to other than the cheapest proposals, to accept or reject any offer completely or in part, or to reject all proposals, without providing the reasons. If no offer is accepted, ETSI may decide to abandon the work or proceed in any other manner ETSI may select.

2.4	IPR and confidentiality Agreements

The information provided in this CfE, as well as the fact that the applicant has received the CfE, is considered confidential and protected under copyright laws. The applicant may not discuss, share, or use the information in this CfE for any purpose other than the response to this CfE.

ETSI will not disclose the content of any proposals to other applicants or any other party, with the exception of the persons involved in the assessment process described in §2.3 above.

However, ETSI reserves the right to make use of the information provided in this proposal to improve this project definition for the purpose of this CfE or any other manner in which ETSI may decide to proceed to select the service providers.

If successful, the applicant will be required to sign a Service Contract, which includes IPR and Confidentiality clauses aligned with the relevant policies in the ETSI Directives.

2.5	Preparation cost

ETSI will not be responsible for any costs or expenses that the applicant may incur in preparing and/or submitting the proposal.

2.6	Service Contract

A Service Contract will be proposed to the applicants that will be selected to perform the work.

Details on the Terms and Conditions of this contract can be found on the ETSI Portal, at the following address: https://portal.etsi.org/STF/STFs/Contracts.aspx

Regulation (EU) 2024/1689 of the European Parliament and of the Council of 13 June 2024 laying down harmonised rules on artificial intelligence and amending Regulations (EC) No 300/2008, (EU) No 167/2013, (EU) No 168/2013, (EU) 2018/858, (EU) 2018/1139 and (EU) 2019/2144 and Directives 2014/90/EU, (EU) 2016/797 and (EU) 2020/1828 (Artificial Intelligence Act) (Text with EEA relevance)

https://portal.etsi.org/TB-SiteMap/OCG/OCG-AI-Co-ordination